## ALU PROJECT_ZTE_UPGRADE(153)
No. | Name | SiteName | eNodB ID | Province | LON | LAT | Forecast OA Date | Upgrade Forecast Week | Upgrade Forecast Month | OA Actual | GAP OA Analysis
1 | SRP0949SRP | ANGKOR_VILLAGE | 1234 | Siem Reap | 103.8633 | 13.3513 | 2025-04-06 | WK14(31-Mar - 06-Apr) | April | 2025-04-06
2 | PNH00637MR | BACTUK | 1059 | Phnom Penh | 104.9133 | 11.564 | 2025-04-24 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
3 | SRP0258BSR | BANTEAY_SREY | 1522 | Siem Reap | 103.9543 | 13.571 | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-07
4 | PNH0622MCY | BEUNG_TUMPUN3 | 1456 | Phnom Penh | 104.9137 | 11.5269 | 2025-04-24 | WK17(21-Apr - 27-Apr) | April | 2025-04-18 | Implementation Under Plan
5 | SRP1886PUK | CHROAS | 3556 | Siem Reap | 103.6745 | 13.5161 | 2025-04-08 | WK15(07-Apr - 13-Apr) | April | 2025-04-08
6 | SRP2888SRP | CTL05_ANGKOR_KRAU | 2024 | Siem Reap | 103.8423 | 13.4404 | 2025-04-08 | WK15(07-Apr - 13-Apr) | April | 2025-04-08
7 | SRP2889SRP | CTL06_NOKOR_THOM | 2027 | Siem Reap | 103.8554 | 13.3965 | 2025-04-06 | WK14(31-Mar - 06-Apr) | April | 2025-04-06
8 | SRP1425SNK | BOSS | 1425 | Siem Reap | 104.1368 | 13.2391 | 2025-05-09 | WK15(07-Apr - 13-Apr) | May |  | Waiting WP Approval by TRC
9 | PNH0485SSK | BEUNG_KLEING2 | 1064 | Phnom Penh | 104.8887 | 11.5628 | 2025-04-24 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
10 | PNH0679SSK | BEUNG_KLEING4 | 1483 | Phnom Penh | 104.8794 | 11.5571 | 2025-04-24 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
11 | SRP1270SRP | BLDBRIGHT_UNIVERSITY | 1238 | Siem Reap | 103.8417 | 13.3444 | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-07
12 | SRP5636SRP | CTL17 | 4467 | Siem Reap | 103.7924 | 13.4017 | 2025-04-08 | WK15(07-Apr - 13-Apr) | April | 2025-04-08
13 | PNH1567TKK | DEAM_KOR_MARKET | 1087 | Phnom Penh | 104.9022 | 11.5551 | 2025-04-23 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
14 | SRP2148CKR | KNONG | 1604 | Siem Reap | 104.4278 | 13.0754 | 2025-04-08 | WK15(07-Apr - 13-Apr) | April | 2025-04-11
15 | SRP0536KRL | KRALANH2_SAMBUOR | 3357 | Siem Reap | 103.4147 | 13.5113 | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-11
16 | SRP1398AKT | PRASAT | 1660 | Siem Reap | 103.8038 | 13.6244 | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-08
17 | SRP1594CKR | CHI_KRAENG | 1528 | Siem Reap | 104.2556 | 13.1506 | 2025-04-08 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
18 | SRP0736CKR | CHREAV2 | 1618 | Siem Reap | 104.3374 | 13.2067 | 2025-04-08 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
19 | SRP5632AKT | CTL11 | 4463 | Siem Reap | 103.885 | 13.4794 | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-07
20 | SRP0259SNK | KG_KLAING | 3347 | Siem Reap | 104.1252 | 13.1054 | 2025-04-08 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
21 | SRP2171SNK | KOUK_SANGKAE | 3469 | Siem Reap | 104.0563 | 13.2526 | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
22 | SRP0329AKT | LEANG_DAI | 1568 | Siem Reap | 103.8761 | 13.5039 | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-07
23 | SRP0343SSM | MOUNG | 3480 | Siem Reap | 103.5414 | 13.7442 | 2025-04-09 | WK15(07-Apr - 13-Apr) | April |  | Implementation Under Plan
24 | PNH0061CAP | PSADEUMTKOV | 1116 | Phnom Penh | 104.9136 | 11.5314 | 2025-04-21 | WK17(21-Apr - 27-Apr) | April | 2025-04-18 | Implementation Under Plan
25 | SRP3319SRP | CTL07_SRAH_SRANG | 4418 | Siem Reap | 103.9019 | 13.4328 | 2025-04-08 | WK15(07-Apr - 13-Apr) | April |  | Implementation Under Plan
26 | SRP1182PBK | KAMPONG_PHUK | 1576 | Siem Reap | 103.9737 | 13.2096 | 2025-04-08 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
27 | SRP1387AKC | NOKORPHEAS | 3421 | Siem Reap | 103.7136 | 13.5973 | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-08
28 | SRP1314AKT | PEAK_SNENG_THMEI | 1657 | Siem Reap | 103.8801 | 13.5814 | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-10
29 | PNH6028PSC | PP229SE | 4650 | Phnom Penh | 104.8608 | 11.5347 | 2025-04-26 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
30 | PNH60007MR | PP253SE | 1099 | Phnom Penh | 104.9116 | 11.5679 | 2025-04-21 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
31 | PNH0625SSK | PP_THMEY3 | 1114 | Phnom Penh | 104.877 | 11.5733 | 2025-04-22 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
32 | SRP2668SRP | SI150 | 3865 | Siem Reap | 103.872 | 13.3664 | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-07
33 | SRP5635PUK | CTL16 | 4466 | Siem Reap | 103.7536 | 13.4264 | 2025-04-10 | WK15(07-Apr - 13-Apr) | April |  | Implementation Under Plan
34 | SRP1016BSR | PHUM_KHNA | 1565 | Siem Reap | 103.9424 | 13.5339 | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-07
35 | SRP0123BSR | PRAHDAK | 3368 | Siem Reap | 103.9397 | 13.4645 | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-07
36 | SRP1912KRL | ROUNG_KOU | 3501 | Siem Reap | 103.5227 | 13.6094 | 2025-04-09 | WK15(07-Apr - 13-Apr) | April |  | Implementation Under Plan
37 | SRP1557PUK | SAMRAONG_YEA | 1516 | Siem Reap | 103.7343 | 13.4095 | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-08
38 | BMC1094TPK | THNAL_DACH | 1094 | Banteay Meanchey | 103.0998 | 14.0094 | 2025-04-28 | WK18(28-Apr - 04-May) | April |  | Implementation Under Plan
39 | SRP0735CKR | SIEMREAP17 | 3384 | Siem Reap | 104.2927 | 13.0651 | 2025-04-10 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
40 | SRP1409SRP | SLA_KRAM | 1288 | Siem Reap | 103.8862 | 13.3604 | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-07
41 | PNH0651CKM | SINWA2 | 1143 | Phnom Penh | 104.9153 | 11.5467 | 2025-04-20 | WK16(14-Apr - 20-Apr) | April |  | Implementation Under Plan
42 | PNH1299SSK | SLAENG_ROLEUNG | 1504 | Phnom Penh | 104.8744 | 11.5653 | 2025-04-26 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
43 | SRP1556SNK | SRAMA_THUM | 3388 | Siem Reap | 104.1194 | 13.2029 | 2025-04-10 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
44 | PNH1285MCY | TUOL_PONGRO2 | 1307 | Phnom Penh | 104.874 | 11.5292 | 2025-04-25 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
45 | PNH2274MCY | VENGSRENG_WAREHOUSE2 | 1363 | Phnom Penh | 104.8641 | 11.5283 | 2025-04-18 | WK16(14-Apr - 20-Apr) | April |  | Implementation Under Plan
46 | SRP2330KRL | SI105 | 3859 | Siem Reap | 103.4163 | 13.6 | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-11
47 | SRP0506SRP | SIEMREAP10 | 1139 | Siem Reap | 103.8693 | 13.361 | 2025-04-06 | WK14(31-Mar - 06-Apr) | April | 2025-04-06
48 | PNH0245SSK | TEUK_THLA | 1477 | Phnom Penh | 104.8791 | 11.5625 | 2025-04-19 | WK16(14-Apr - 20-Apr) | April |  | Implementation Under Plan
49 | PNH0180PSC | VENG_SRENG | 2657 | Phnom Penh | 104.8458 | 11.5296 | 2025-04-25 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
50 | PNH0345MCY | VENG_SRENG_RD | 1439 | Phnom Penh | 104.8625 | 11.5319 | 2025-04-18 | WK16(14-Apr - 20-Apr) | April |  | Implementation Under Plan
51 | PNH1470TKK | SAMMAKI_MARKET | 1134 | Phnom Penh | 104.9022 | 11.569 | 2025-04-20 | WK16(14-Apr - 20-Apr) | April |  | Implementation Under Plan
52 | SRP0264VRI | SRE_NOY | 264 | Siem Reap | 104.0357 | 13.8064 | 2025-05-09 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
53 | SRP0425SRP | SIEMREAP6 | 1283 | Siem Reap | 103.8528 | 13.3504 | 2025-04-06 | WK14(31-Mar - 06-Apr) | April | 2025-04-06
54 | PNH0486MCY | ST_MEANCHEY3 | 1337 | Phnom Penh | 104.8799 | 11.533 | 2025-04-25 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
55 | SRP0440VRI | SVAY_SA | 1525 | Siem Reap | 103.7577 | 13.8002 | 2025-04-10 | WK15(07-Apr - 13-Apr) | April | 2025-04-10
56 | SRP1257SVL | TA_SIEM | 3528 | Siem Reap | 104.2447 | 13.6237 | 2025-04-10 | WK15(07-Apr - 13-Apr) | April | 2025-04-11
57 | SRP0552PUK | REUL | 1558 | Siem Reap | 103.7263 | 13.549 | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-08
58 | SRP1933SVL | TA_PENH | 1648 | Siem Reap | 104.203 | 13.5396 | 2025-04-10 | WK15(07-Apr - 13-Apr) | April | 2025-04-11
59 | BTB0775BVL | BATTAMBANG10 | 3248 | Battambang | 102.9138 | 13.3501 | 2025-04-25 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
60 | KGT1948SDN | LEAENG | 1592 | Kampong Thom | 105.3795 | 12.9102 | 2025-04-21 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
61 | KGT1419KPS | PHUM_KAMPONG_KOKROM | 3427 | Kampong Thom | 104.7771 | 12.6953 | 2025-04-20 | WK16(14-Apr - 20-Apr) | April |  | Implementation Under Plan
62 | OMC5656TPS | KANG_POL_6_TRAPEANG_PRASAT_TPS | 4478 | Oudor Meanchey | 104.307 | 14.1126 | 2025-04-27 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
63 | KGT0660SSN | KG_THOM3 | 3351 | Kampong Thom | 104.8891 | 12.7286 | 2025-04-22 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
64 | KGT2217SDN | RANG_KHNAY | 1594 | Kampong Thom | 105.501 | 12.9382 | 2025-04-20 | WK16(14-Apr - 20-Apr) | April |  | Implementation Under Plan
65 | KGT2038STK | KIRI_VON | 3417 | Kampong Thom | 104.9753 | 12.6526 | 2025-04-22 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
66 | PVH1679KLN | RUMCHEK | 1642 | Preah Vihear | 104.4982 | 13.8118 | 2025-04-30 | WK18(28-Apr - 04-May) | April |  | Implementation Under Plan
67 | KGT0672STG | BOENG_MEALEA2 | 3554 | Kampong Thom | 104.5599 | 13.1635 | 2025-04-22 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
68 | PVH1845RVG | CHI_AOK | 3452 | Preah Vihear | 104.9673 | 13.0933 | 2025-04-30 | WK18(28-Apr - 04-May) | April |  | Implementation Under Plan
69 | KGT1561KPS | KOUNN_TNAOT | 3562 | Kampong Thom | 104.961 | 12.8393 | 2025-04-21 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
70 | OMC0072SRG | OR_SMACH | 3281 | Oudor Meanchey | 103.6935 | 14.4195 | 2025-04-27 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
71 | OMC1803ALV | OU_KOKIR_KANDAL | 3566 | Oudor Meanchey | 104.0465 | 14.1776 | 2025-04-27 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
72 | KGT1586KPS | PEAM_KRAENG | 3569 | Kampong Thom | 104.8147 | 12.7127 | 2025-04-21 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
73 | PVH2247RVG | OU_POUR | 2247 | Preah Vihear | 105.0401 | 13.1928 | 2025-04-29 | WK18(28-Apr - 04-May) | April |  | Implementation Under Plan
74 | PNH4455MCY | KBAL_THNAL | 1435 | Phnom Penh | 104.9316 | 11.5281 | 2025-04-22 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
75 | OMC1477TPS | PHUM_POPEL | 3491 | Oudor Meanchey | 104.1883 | 14.2255 | 2025-04-27 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
76 | BTB0864TKL | PSAR_PRUM2 | 1301 | Battambang | 103.0618 | 13.3263 | 2025-04-25 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
77 | KGT1914SDN | RONTEAH | 1587 | Kampong Thom | 105.4229 | 12.944 | 2025-04-20 | WK16(14-Apr - 20-Apr) | April |  | Implementation Under Plan
78 | KGT0671PBL | SANTUK2 | 1651 | Kampong Thom | 104.7518 | 13.1831 | 2025-04-19 | WK16(14-Apr - 20-Apr) | April |  | Implementation Under Plan
79 | KGT1343PBL | TA_LEK | 3523 | Kampong Thom | 105.0247 | 13.0573 | 2025-04-19 | WK16(14-Apr - 20-Apr) | April |  | Implementation Under Plan
80 | SRP2156SNK | SANTEY | 2156 | Siem Reap | 104.091 | 13.2396 | 2025-05-09 | WK16(14-Apr - 20-Apr) | May |  | Waiting WP Approval by TRC
81 | PNH1276TKK | BEUNG_BAYAB | 1062 | Phnom Penh | 104.897 | 11.5907 | 2025-04-24 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
82 | PNH0989TKK | CHAMBER_OF_COMMERCE | 1402 | Phnom Penh | 104.8953 | 11.5693 | 2025-04-23 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
83 | PNH1331CAP | CHBAAMPOV_MKT | 1075 | Phnom Penh | 104.9346 | 11.5336 | 2025-04-23 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
84 | BTB2108APM | KAOH_CHIVEANG | 1577 | Siem Reap | 103.4979 | 13.3449 | 2025-04-10 | WK15(07-Apr - 13-Apr) | April | 2025-04-12
85 | PNH00237MR | ORUSSEY | 1106 | Phnom Penh | 104.918 | 11.5614 | 2025-04-22 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
86 | SRP0734CKR | PONGRO_LEU | 3570 | Siem Reap | 104.4134 | 13.2919 | 2025-04-08 | WK15(07-Apr - 13-Apr) | April | 2025-04-08
87 | KDL5951KDS | RDS_TOWER-02 | 4709 | Kandal | 104.9174 | 11.3653 | 2025-04-21 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
88 | PVH0763KLN | SVAY_LEU2 | 3325 | Preah Vihear | 104.5493 | 13.7041 | 2025-04-30 | WK18(28-Apr - 04-May) | April |  | Implementation Under Plan
89 | PNH0646PSC | AIRPORT3 | 1500 | Phnom Penh | 104.8322 | 11.5484 | 2025-04-25 | WK17(21-Apr - 27-Apr) | April | 2025-04-18 | Implementation Under Plan
90 | BMC1092PNP | PHNUM_LIEB_KEUT | 1092 | Banteay Meanchey | 105.0401 | 13.1928 | 2025-04-28 | WK18(28-Apr - 04-May) | April |  | Implementation Under Plan
91 | PNH2150CKM | HELSINKI_UNIVERSITY | 1091 | Phnom Penh | 104.9289 | 11.5432 | 2025-04-23 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
92 | BTB1595APM | KOH_CHIVEANG | 1656 | Siem Reap | 103.6642 | 13.2297 | 2025-04-10 | WK15(07-Apr - 13-Apr) | April | 2025-04-12
93 | PNH2282CAP | KOH_PICH2 | 1349 | Phnom Penh | 104.9396 | 11.5394 | 2025-04-22 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
94 | PNH4416CKM | PPX160 | 3202 | Phnom Penh | 104.9108 | 11.5531 | 2025-04-21 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
95 | PNH3276DPH | PSAR_KANDAL2 | 1680 | Phnom Penh | 104.9289 | 11.5691 | 2025-04-26 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
96 | PNH4453DPH | SARAVOAN | 1381 | Phnom Penh | 104.9283 | 11.5662 | 2025-04-20 | WK16(14-Apr - 20-Apr) | April |  | Implementation Under Plan
97 | PNH2349CKM | CHINA_HOSPITAL | 1302 | Phnom Penh | 104.9199 | 11.5531 | 2025-04-23 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
98 | PNH3345TKK | INDRAK_TEVY | 1094 | Phnom Penh | 104.8926 | 11.5756 | 2025-04-23 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
99 | SRP1030CKR | LVENG_RUSSEY | 1534 | Siem Reap | 104.4582 | 13.0533 | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
100 | PNH14897MR | PAILIN_HTL | 1189 | Phnom Penh | 104.9168 | 11.568 | 2025-04-22 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
101 | SRP1189CKR | PHUM_POR | 3492 | Siem Reap | 104.3835 | 13.1589 | 2025-04-08 | WK15(07-Apr - 13-Apr) | April | 2025-04-08
102 | PNH0483TKK | PP_UNIVERSITY | 1465 | Phnom Penh | 104.8943 | 11.5672 | 2025-04-22 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
103 | PNH0065DPH | SHERATON_HTL | 1138 | Phnom Penh | 104.9179 | 11.5761 | 2025-04-26 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
104 | SRP1885CKR | THNAL_TA_SET | 3537 | Siem Reap | 104.2981 | 13.1736 | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-07
105 | SRP1170PUK | PHUM_PRADAK | 3493 | Siem Reap | 103.5754 | 13.58 | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-10
106 | SRP0263PUK | PREY_CHRUK | 1574 | Siem Reap | 103.549 | 13.5351 | 2025-04-10 | WK15(07-Apr - 13-Apr) | April | 2025-04-11
107 | SRP0097PUK | PUORK | 1549 | Siem Reap | 103.6719 | 13.4719 | 2025-04-10 | WK15(07-Apr - 13-Apr) | April | 2025-04-10
108 | SRP2922SRP | SI001 | 3848 | Siem Reap | 103.849 | 13.3137 | 2025-04-08 | WK15(07-Apr - 13-Apr) | April | 2025-04-08
109 | SRP0330SSM | SREY_SNOM | 1518 | Siem Reap | 103.5172 | 13.8289 | 2025-04-10 | WK15(07-Apr - 13-Apr) | April | 2025-04-11
110 | SRP1612SNK | TA_YAEK | 3531 | Siem Reap | 104.1725 | 13.2954 | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
111 | PNH2212MCY | TNAOT_CHRUM2 | 1492 | Phnom Penh | 104.8987 | 11.53 | 2025-04-19 | WK16(14-Apr - 20-Apr) | April |  | Implementation Under Plan
112 | PNH2348RSK | TOUL_SANGKE2 | 1323 | Phnom Penh | 104.9088 | 11.5854 | 2025-04-25 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
113 | PNH1325RSK | SAMEAKKI_PP | 1452 | Phnom Penh | 104.914 | 11.596 | 2025-04-26 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
114 | SRP1169PUK | TA_TRAV | 3398 | Siem Reap | 103.6182 | 13.4862 | 2025-04-10 | WK15(07-Apr - 13-Apr) | April | 2025-04-10
115 | SRP2174SRP | TI_MUOY | 1606 | Siem Reap | 103.829 | 13.2362 | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-12
116 | PNH0899TKK | TOUL_KOK5 | 1443 | Phnom Penh | 104.9034 | 11.5755 | 2025-04-25 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan
117 | SRP1504SNK | TRAPEANG_THUM | 1523 | Siem Reap | 104.084 | 13.2727 | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-07
118 | SRP1659SVL | TUEK_LICH | 1562 | Siem Reap | 104.2163 | 13.469 | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-10
119 | PNH0246RSK | TUMNOP_TOULKOK | 1479 | Phnom Penh | 104.9004 | 11.5928 | 2025-04-19 | WK16(14-Apr - 20-Apr) | April |  | Implementation Under Plan
120 | SRP0586PBK | WESTERN_BARAY | 3405 | Siem Reap | 104.0533 | 13.2988 | 2025-04-08 | WK15(07-Apr - 13-Apr) | April | 2025-04-08
121 | BMC1389PPT | BALILEY2 | 1236 | Banteay Meanchey | 102.5683 | 13.6524 | 2025-05-01 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
122 | BMC1507MKB | BAT_TRANG | 1563 | Banteay Meanchey | 102.9927 | 13.5244 | 2025-05-01 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
123 | BMC0182OCV | KAUK_NIMITT | 3258 | Banteay Meanchey | 102.7632 | 13.6129 | 2025-05-04 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
124 | BMC1597PPT | KBAL_SPEAN_POIPET2 | 1251 | Banteay Meanchey | 102.5641 | 13.6594 | 2025-05-04 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
125 | BMC0693MKB | MONKUL_BOREY3 | 3197 | Banteay Meanchey | 103.0265 | 13.5435 | 2025-05-03 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
126 | BMC1928MKB | PHLOV_SIEM | 1509 | Banteay Meanchey | 103.0828 | 13.5485 | 2025-05-02 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
127 | SRP1238BSR | TOUL_KROUS | 3541 | Siem Reap | 104.0473 | 13.7182 | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-10
128 | PNH0493DPH | WAT_OUNALOM | 1175 | Phnom Penh | 104.9267 | 11.568 | 2025-04-18 | WK16(14-Apr - 20-Apr) | April |  | Implementation Under Plan
129 | BMC0553MKB | CHAMNOM | 3250 | Banteay Meanchey | 102.9422 | 13.4486 | 2025-05-04 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
130 | BMC1097PNP | CHEUNG_VOAT | 3251 | Banteay Meanchey | 103.182 | 13.5895 | 2025-05-04 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
131 | BMC1924PNP | KBAL_KHTING | 3462 | Banteay Meanchey | 103.0647 | 13.7103 | 2025-05-04 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
132 | BMC0281TPK | KOUK_ROMIET | 3268 | Banteay Meanchey | 102.8644 | 13.9848 | 2025-05-03 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
133 | BMC1284MKB | LUONG | 3195 | Banteay Meanchey | 103.031 | 13.5378 | 2025-05-03 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
134 | BMC1287SSP | O_AMBEL2 | 1258 | Banteay Meanchey | 102.963 | 13.6022 | 2025-05-03 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
135 | BMC0692SSP | O_AMBEL4 | 1260 | Banteay Meanchey | 102.956 | 13.5864 | 2025-05-02 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
136 | BMC0034PPT | POIPET | 1110 | Banteay Meanchey | 102.5533 | 13.659 | 2025-05-02 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
137 | BMC0758MLI | MALAY2 | 1559 | Banteay Meanchey | 102.738 | 13.4946 | 2025-05-03 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
138 | BMC0183PPT | NIMITT | 3275 | Banteay Meanchey | 102.6836 | 13.6253 | 2025-05-03 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
139 | BMC1452PPT | PREY_KUB | 1571 | Banteay Meanchey | 102.6097 | 13.7068 | 2025-05-02 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
140 | BMC1090MKB | ROHAT_TUEK | 3309 | Banteay Meanchey | 102.9784 | 13.4783 | 2025-05-02 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
141 | BMC2146PNP | RUESSEI_KANDAL | 1541 | Banteay Meanchey | 103.0992 | 13.6314 | 2025-04-29 | WK18(28-Apr - 04-May) | April |  | Waiting WP Approval by TRC
142 | BMC1923OCV | RUN | 3435 | Banteay Meanchey | 102.8288 | 13.7168 | 2025-04-29 | WK18(28-Apr - 04-May) | April |  | Waiting WP Approval by TRC
143 | BMC1770PNP | SRAMAOCH | 3512 | Banteay Meanchey | 103.1235 | 13.5705 | 2025-05-01 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
144 | BMC0151SCK | SVAY_CHEK | 3324 | Banteay Meanchey | 102.961 | 13.8044 | 2025-05-01 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
145 | BMC0397MKB | PHNOM_THOM | 3198 | Banteay Meanchey | 103.0154 | 13.4482 | 2025-05-02 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
146 | BMC1840PSK | ROUK | 3500 | Banteay Meanchey | 103.4117 | 13.6985 | 2025-04-29 | WK18(28-Apr - 04-May) | April |  | Waiting WP Approval by TRC
147 | BMC1592SCK | SLORKRAM | 1575 | Banteay Meanchey | 102.9607 | 13.754 | 2025-04-29 | WK18(28-Apr - 04-May) | April |  | Waiting WP Approval by TRC
148 | BMC1091MKB | SOEA | 3201 | Banteay Meanchey | 102.9296 | 13.3904 | 2025-04-29 | WK18(28-Apr - 04-May) | April |  | Waiting WP Approval by TRC
149 | BMC0280PSK | SRAH_CHIK | 3323 | Banteay Meanchey | 103.335 | 13.7501 | 2025-04-29 | WK18(28-Apr - 04-May) | April |  | Waiting WP Approval by TRC
150 | BMC1764PNP | TBAENG | 3534 | Banteay Meanchey | 103.1314 | 13.6916 | 2025-05-01 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC
151 | BMC1183PNP | TRABEK | 3543 | Banteay Meanchey | 103.0409 | 13.6465 | 2025-04-30 | WK18(28-Apr - 04-May) | April |  | Waiting WP Approval by TRC
152 | BMC1119PSK | TRAPAING_THMAR | 3544 | Banteay Meanchey | 103.3242 | 13.792 | 2025-04-30 | WK18(28-Apr - 04-May) | April |  | Waiting WP Approval by TRC
153 | BMC1842MKB | SRAH_PHLUOH | 1561 | Banteay Meanchey | 102.7766 | 13.4233 | 2025-05-01 | WK18(28-Apr - 04-May) | May |  | Waiting WP Approval by TRC

## ALU PROJECT_ALU&HW_SWAP(185)
No | SBTS | SSC | SiteName | LAT | LON | Existing BTS | Province | WP_Batch | MAINCluster_ID | Cluster_ID | Swap_Batch | Forecast Start | Forecast OA Date | OA Week Number End | OA Month | OA Actual | GAP OA Analysis
1 | SVR0963BVT | 963 | BANTEY_CHAKREY2 | 10.9973 | 106.1769 | ALU/ZTE | Svay Rieng | B1 | SVR1 | SVR1 | 1 | 2025-04-21 | 2025-04-25 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan (WP Received)
2 | SVR1235CTR | 1235 | CHAN_TREA | 10.8731 | 106.0795 | ALU/ZTE | Svay Rieng | B1 | SVR1 | SVR1 | 1 | 2025-04-21 | 2025-04-25 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan (WP Received)
3 | SVR0954KPR | 954 | KANDAL | 10.8974 | 106.0329 | ALU/ZTE | Svay Rieng | B1 | SVR1 | SVR1 | 1 | 2025-04-21 | 2025-04-25 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan (WP Received)
4 | SVR0368CTR | 368 | MESA_THNGORK | 10.9848 | 106.1179 | ALU/ZTE | Svay Rieng | B1 | SVR1 | SVR1 | 1 | 2025-04-21 | 2025-04-25 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan (WP Received)
5 | SVR1722CTR | 1722 | TROPEANG_RUN_VILLAGE | 10.9258 | 106.0662 | ALU/ZTE | Svay Rieng | B1 | SVR1 | SVR1 | 1 | 2025-04-21 | 2025-04-25 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan (WP Received)
6 | SVR0800CTR | 800 | TUOL_SDEY | 10.9306 | 106.1282 | ALU/ZTE | Svay Rieng | B1 | SVR1 | SVR1 | 1 | 2025-04-21 | 2025-04-25 | WK17(21-Apr - 27-Apr) | April |  | Implementation Under Plan (WP Received)
7 | SVR1709SVT | 1709 | ANGK_TA_MOUK | 10.9868 | 105.9212 | ALU/ZTE | Svay Rieng | B1 | SVR2 | SVR2_1 | 2 | 2025-04-26 | 2025-04-29 | WK18(28-Apr - 04-May) | April |  | Implementation Under Plan (WP Received)
8 | SVR1710SVC | 1710 | CHIES_RUESSEI | 11.0306 | 105.7471 | ALU/ZTE | Svay Rieng | B1 | SVR2 | SVR2_1 | 2 | 2025-04-26 | 2025-04-29 | WK18(28-Apr - 04-May) | April |  | Implementation Under Plan (WP Received)
9 | SVR1242KPR | 1242 | ORDON_ARM | 11.0088 | 105.885 | ALU/ZTE | Svay Rieng | B1 | SVR2 | SVR2_1 | 2 | 2025-04-26 | 2025-04-29 | WK18(28-Apr - 04-May) | April |  | Implementation Under Plan (WP Received)
10 | SVR1718KPR | 1718 | REACH_MON_TY | 10.9514 | 105.8968 | ALU/ZTE | Svay Rieng | B1 | SVR2 | SVR2_1 | 2 | 2025-04-26 | 2025-04-29 | WK18(28-Apr - 04-May) | April |  | Implementation Under Plan (WP Received)
11 | SVR0777KPR | 777 | SAM_YOUNG | 10.9601 | 105.8551 | ALU/ZTE | Svay Rieng | B1 | SVR2 | SVR2_1 | 2 | 2025-04-26 | 2025-04-29 | WK18(28-Apr - 04-May) | April |  | Implementation Under Plan (WP Received)
12 | SVR0993SVC | 993 | SAYAONG2 | 11.0211 | 105.8192 | ALU/ZTE | Svay Rieng | B1 | SVR2 | SVR2_1 | 2 | 2025-04-26 | 2025-04-29 | WK18(28-Apr - 04-May) | April |  | Implementation Under Plan (WP Received)
13 | SVR1583SVC | 1583 | TA_NU | 11.0353 | 105.702 | ALU/ZTE | Svay Rieng | B1 | SVR2 | SVR2_1 | 2 | 2025-04-26 | 2025-04-29 | WK18(28-Apr - 04-May) | April |  | Implementation Under Plan (WP Received)
14 | KRT1881SNO | 1881 | DOUN_MEAS | 11.9977 | 106.314 | ALU/ZTE | Kratie | B1 | KRT1 | KRT1_1 | 2 | 2025-04-30 | 2025-05-02 | WK18(28-Apr - 04-May) | May |  | Implementation Under Plan (WP Received)
15 | KRT1878SNO | 1878 | KOUN_KRAPEU | 11.9659 | 106.3766 | ALU/ZTE | Kratie | B1 | KRT1 | KRT1_1 | 2 | 2025-04-30 | 2025-05-02 | WK18(28-Apr - 04-May) | May |  | Implementation Under Plan (WP Received)
16 | KRA181 | 5541 | KRA181 | 12.0851 | 106.4234 | HW | Kratie | B2 | KRT1 | KRT1_1 | 2 | 2025-04-30 | 2025-05-02 | WK18(28-Apr - 04-May) | May |  | Implementation Under Plan (WP Under TRC Approval)
17 | SNUOL | 148 | SNUOL | 12.0674 | 106.4226 | HW | Kratie | B2 | KRT1 | KRT1_1 | 2 | 2025-04-30 | 2025-05-02 | WK18(28-Apr - 04-May) | May |  | Implementation Under Plan (WP Under TRC Approval)
18 | KRT1146SNO | 1146 | SRE_CHAR | 12.0977 | 106.3445 | ALU/ZTE | Kratie | B1 | KRT1 | KRT1_1 | 2 | 2025-04-30 | 2025-05-02 | WK18(28-Apr - 04-May) | May |  | Implementation Under Plan (WP Received)
19 | SVR1373CTR | 1373 | ANG_KHDOUCH | 11.0138 | 106.0633 | ALU/ZTE | Svay Rieng | B1 | SVR2 | SVR2_2 | 3 | 2025-05-03 | 2025-05-06 | WK19(05-May - 11-May) | May |  | Implementation Under Plan (WP Received)
20 | SVR1660KPR | 1660 | CHOB_BRING | 10.8727 | 105.9279 | ALU/ZTE | Svay Rieng | B1 | SVR2 | SVR2_2 | 3 | 2025-05-03 | 2025-05-06 | WK19(05-May - 11-May) | May |  | Implementation Under Plan (WP Received)
21 | SVR0144KPR | 144 | KG_ROU | 10.9203 | 105.9446 | ALU/ZTE | Svay Rieng | B1 | SVR2 | SVR2_2 | 3 | 2025-05-03 | 2025-05-06 | WK19(05-May - 11-May) | May |  | Implementation Under Plan (WP Received)
22 | SVR1715KPR | 1715 | PRA_CHANTREA | 10.9123 | 105.8671 | ALU/ZTE | Svay Rieng | B1 | SVR2 | SVR2_2 | 3 | 2025-05-03 | 2025-05-06 | WK19(05-May - 11-May) | May |  | Implementation Under Plan (WP Received)
23 | SVR1159KPR | 1159 | SAMLEY_KHANG_CHOEUNG | 10.9644 | 106.0212 | ALU/ZTE | Svay Rieng | B1 | SVR2 | SVR2_2 | 3 | 2025-05-03 | 2025-05-06 | WK19(05-May - 11-May) | May |  | Implementation Under Plan (WP Received)
24 | SVR1695KPR | 1695 | TRAPEANG_TRACH | 10.9887 | 105.9797 | ALU/ZTE | Svay Rieng | B1 | SVR2 | SVR2_2 | 3 | 2025-05-03 | 2025-05-06 | WK19(05-May - 11-May) | May |  | Implementation Under Plan (WP Received)
25 | KRT2015SNO | 2015 | KAT_DAI | 12.1139 | 106.4291 | ALU/ZTE | Kratie | B1 | KRT1 | KRT1_2 | 3 | 2025-05-07 | 2025-05-09 | WK19(05-May - 11-May) | May |  | Implementation Under Plan (WP Received)
26 | KRT1877SNO | 1877 | KHSUEM_KNONG | 12.2147 | 106.4405 | ALU/ZTE | Kratie | B1 | KRT1 | KRT1_2 | 3 | 2025-05-07 | 2025-05-09 | WK19(05-May - 11-May) | May |  | Implementation Under Plan (WP Received)
27 | KRT2024SNO | 2024 | RONAENG | 12.4098 | 106.473 | ALU/ZTE | Kratie | B1 | KRT1 | KRT1_2 | 3 | 2025-05-07 | 2025-05-09 | WK19(05-May - 11-May) | May |  | Implementation Under Plan (WP Received)
28 | KRT1873SNO | 1873 | SAMRANG2 | 12.261 | 106.4281 | ALU/ZTE | Kratie | B1 | KRT1 | KRT1_2 | 3 | 2025-05-07 | 2025-05-09 | WK19(05-May - 11-May) | May |  | Implementation Under Plan (WP Received)
29 | KRT0779SNO | 779 | SNUOL2 | 12.1688 | 106.4509 | ALU/ZTE | Kratie | B1 | KRT1 | KRT1_2 | 3 | 2025-05-07 | 2025-05-09 | WK19(05-May - 11-May) | May |  | Implementation Under Plan (WP Received)
30 | KRT1510SNO | 1510 | SRE_RONEAM | 12.2897 | 106.4087 | ALU/ZTE | Kratie | B1 | KRT1 | KRT1_2 | 3 | 2025-05-07 | 2025-05-09 | WK19(05-May - 11-May) | May |  | Implementation Under Plan (WP Received)
31 | SVR1724RDL | 1724 | ALONG_SPEAN | 11.1848 | 105.781 | ALU/ZTE | Svay Rieng | B1 | SVR3 | SVR3 | 4 | 2025-05-10 | 2025-05-13 | WK20(12-May - 18-May) | May |  | Implementation Under Plan (WP Received)
32 | SVR0369RDL | 369 | CHAK | 11.1588 | 105.821 | ALU/ZTE | Svay Rieng | B1 | SVR3 | SVR3 | 4 | 2025-05-10 | 2025-05-13 | WK20(12-May - 18-May) | May |  | Implementation Under Plan (WP Received)
33 | SVR0794SVT | 794 | CHAK2 | 11.1434 | 105.8939 | ALU/ZTE | Svay Rieng | B1 | SVR3 | SVR3 | 4 | 2025-05-10 | 2025-05-13 | WK20(12-May - 18-May) | May |  | Implementation Under Plan (WP Received)
34 | SVR0979SVT | 979 | KAMPOUT_MREAK | 11.1649 | 105.9481 | ALU/ZTE | Svay Rieng | B1 | SVR3 | SVR3 | 4 | 2025-05-10 | 2025-05-13 | WK20(12-May - 18-May) | May |  | Implementation Under Plan (WP Received)
35 | SVR1160SVT | 1160 | PHOUM_OTAMOUR | 11.1067 | 106.0517 | ALU/ZTE | Svay Rieng | B1 | SVR3 | SVR3 | 4 | 2025-05-10 | 2025-05-13 | WK20(12-May - 18-May) | May |  | Implementation Under Plan (WP Received)
36 | SVR1738RDL | 1738 | PREY_TA_YOAN | 11.1898 | 105.8832 | ALU/ZTE | Svay Rieng | B1 | SVR3 | SVR3 | 4 | 2025-05-10 | 2025-05-13 | WK20(12-May - 18-May) | May |  | Implementation Under Plan (WP Received)
37 | SVR1741SVT | 1741 | TA_PAONH | 11.1438 | 105.9834 | ALU/ZTE | Svay Rieng | B1 | SVR3 | SVR3 | 4 | 2025-05-10 | 2025-05-13 | WK20(12-May - 18-May) | May |  | Implementation Under Plan (WP Received)
38 | SVR1745RDL | 1745 | TREAPEANG_HAMBAK | 11.2147 | 105.7786 | ALU/ZTE | Svay Rieng | B1 | SVR3 | SVR3 | 4 | 2025-05-10 | 2025-05-13 | WK20(12-May - 18-May) | May |  | Implementation Under Plan (WP Received)
39 | KRT1668SNO | 1668 | CHEUNG_KHLE | 11.9941 | 106.5243 | ALU/ZTE | Kratie | B1 | KRT1 | KRT1_3 | 4 | 2025-05-14 | 2025-05-16 | WK20(12-May - 18-May) | May |  | Implementation Under Plan (WP Received)
40 | KRT2241SNO | 2241 | CHEUNG_KHLE1 | 12.1192 | 106.5874 | ALU/ZTE | Kratie | B1 | KRT1 | KRT1_3 | 4 | 2025-05-14 | 2025-05-16 | WK20(12-May - 18-May) | May |  | Implementation Under Plan (WP Received)
41 | KRT1875SNO | 1875 | CHHNAENG | 12.1285 | 106.7398 | ALU/ZTE | Kratie | B1 | KRT1 | KRT1_3 | 4 | 2025-05-14 | 2025-05-16 | WK20(12-May - 18-May) | May |  | Implementation Under Plan (WP Received)
42 | KRT2231SNO | 2231 | CHRAB | 12.0456 | 106.4718 | ALU/ZTE | Kratie | B1 | KRT1 | KRT1_3 | 4 | 2025-05-14 | 2025-05-16 | WK20(12-May - 18-May) | May |  | Implementation Under Plan (WP Received)
43 | KRT1945SNO | 1945 | MIL | 12.1295 | 106.6617 | ALU/ZTE | Kratie | B1 | KRT1 | KRT1_3 | 4 | 2025-05-14 | 2025-05-16 | WK20(12-May - 18-May) | May |  | Implementation Under Plan (WP Received)
44 | SVR1082RDL | 1082 | PHOUM_KRAUCH | 11.2576 | 105.8255 | ALU/ZTE | Svay Rieng | B1 | SVR4 | SVR4_1 | 5 | 2025-05-17 | 2025-05-20 | WK21(19-May - 25-May) | May |  | Implementation Under Plan (WP Received)
45 | SVR1359RDL | 1359 | PHOUM_SAMOR | 11.2456 | 105.8524 | ALU/ZTE | Svay Rieng | B1 | SVR4 | SVR4_1 | 5 | 2025-05-17 | 2025-05-20 | WK21(19-May - 25-May) | May |  | Implementation Under Plan (WP Received)
46 | SVR1157RMH | 1157 | PHOUM_TRAPEANG_BOS | 11.3582 | 105.8013 | ALU/ZTE | Svay Rieng | B1 | SVR4 | SVR4_1 | 5 | 2025-05-17 | 2025-05-20 | WK21(19-May - 25-May) | May |  | Implementation Under Plan (WP Received)
47 | SVR1743RDL | 1743 | THNONG | 11.2737 | 105.8995 | ALU/ZTE | Svay Rieng | B1 | SVR4 | SVR4_1 | 5 | 2025-05-17 | 2025-05-20 | WK21(19-May - 25-May) | May |  | Implementation Under Plan (WP Received)
48 | SVR0957RDL | 957 | TRAPEANG_KNONG | 11.2311 | 105.8816 | ALU/ZTE | Svay Rieng | B1 | SVR4 | SVR4_1 | 5 | 2025-05-17 | 2025-05-20 | WK21(19-May - 25-May) | May |  | Implementation Under Plan (WP Received)
49 | SVR0527RMH | 527 | TRAPEANG_SDAU | 11.3122 | 105.8207 | ALU/ZTE | Svay Rieng | B1 | SVR4 | SVR4_1 | 5 | 2025-05-17 | 2025-05-20 | WK21(19-May - 25-May) | May |  | Implementation Under Plan (WP Received)
50 | KRT0122CLG | 122 | CHLAUNG | 12.2393 | 105.9675 | ALU/ZTE | Kratie | B1 | KRT2 | KRT2_1 | 5 | 2025-05-21 | 2025-05-23 | WK21(19-May - 25-May) | May |  | Implementation Under Plan (WP Received)
51 | KRT0787CLG | 787 | LAA | 12.3296 | 106.0568 | ALU/ZTE | Kratie | B1 | KRT2 | KRT2_1 | 5 | 2025-05-21 | 2025-05-23 | WK21(19-May - 25-May) | May |  | Implementation Under Plan (WP Received)
52 | KRT0772CLG | 772 | PAURAK | 12.2531 | 105.9014 | ALU/ZTE | Kratie | B1 | KRT2 | KRT2_1 | 5 | 2025-05-21 | 2025-05-23 | WK21(19-May - 25-May) | May |  | Implementation Under Plan (WP Received)
53 | KRT2067CLG | 2067 | PREAEK_SAMAN | 12.2803 | 106.0254 | ALU/ZTE | Kratie | B1 | KRT2 | KRT2_1 | 5 | 2025-05-21 | 2025-05-23 | WK21(19-May - 25-May) | May |  | Implementation Under Plan (WP Received)
54 | KRT0377PPS | 377 | PREAK_PRASAB | 12.3568 | 106.0323 | ALU/ZTE | Kratie | B1 | KRT2 | KRT2_1 | 5 | 2025-05-21 | 2025-05-23 | WK21(19-May - 25-May) | May |  | Implementation Under Plan (WP Received)
55 | SVR1103RMH | 1103 | BLOCK_SALAKHUM | 11.3363 | 105.8593 | ALU/ZTE | Svay Rieng | B1 | SVR4 | SVR4_2 | 6 | 2025-05-24 | 2025-05-27 | WK22(26-May - 01-Jun) | May |  | Implementation Under Plan (WP Received)
56 | SVR1733RMH | 1733 | DAK_POR | 11.4598 | 105.7472 | ALU/ZTE | Svay Rieng | B1 | SVR4 | SVR4_2 | 6 | 2025-05-24 | 2025-05-27 | WK22(26-May - 01-Jun) | May |  | Implementation Under Plan (WP Received)
57 | SVR0767RMH | 767 | KAMCHAY_MEAR2 | 11.5343 | 105.7149 | ALU/ZTE | Svay Rieng | B1 | SVR4 | SVR4_2 | 6 | 2025-05-24 | 2025-05-27 | WK22(26-May - 01-Jun) | May |  | Implementation Under Plan (WP Received)
58 | SVR1699RMH | 1699 | KRANHUNG | 11.3871 | 105.8589 | ALU/ZTE | Svay Rieng | B1 | SVR4 | SVR4_2 | 6 | 2025-05-24 | 2025-05-27 | WK22(26-May - 01-Jun) | May |  | Implementation Under Plan (WP Received)
59 | SVR1081RMH | 1081 | PHOUM_TRORK | 11.4641 | 105.7988 | ALU/ZTE | Svay Rieng | B1 | SVR4 | SVR4_2 | 6 | 2025-05-24 | 2025-05-27 | WK22(26-May - 01-Jun) | May |  | Implementation Under Plan (WP Received)
60 | SVR0143RMH | 143 | ROMEAS_HEK | 11.4088 | 105.7944 | ALU/ZTE | Svay Rieng | B1 | SVR4 | SVR4_2 | 6 | 2025-05-24 | 2025-05-27 | WK22(26-May - 01-Jun) | May |  | Drop Site (Need replacement site by Cellard)
61 | SVR1750RMH | 1750 | VEAL_VEAENG | 11.544 | 105.7936 | ALU/ZTE | Svay Rieng | B1 | SVR4 | SVR4_2 | 6 | 2025-05-24 | 2025-05-27 | WK22(26-May - 01-Jun) | May |  | Implementation Under Plan (WP Received)
62 | KRT1611CBR | 1611 | ALUCH | 12.4052 | 106.2383 | ALU/ZTE | Kratie | B1 | KRT2 | KRT2_2 | 6 | 2025-05-28 | 2025-05-30 | WK22(26-May - 01-Jun) | May |  | Implementation Under Plan (WP Received)
63 | PNH6358SSK | 6358 | GPP43 | 11.5915 | 104.8608 | ALU/ZTE | Phnom Penh | B2 |  |  | 6 | 2025-05-28 | 2025-05-30 | WK22(26-May - 01-Jun) | May |  | Implementation Under Plan (WP Under TRC Approval)
64 | KRT0983CLG | 983 | PNOV | 12.1753 | 106.079 | ALU/ZTE | Kratie | B1 | KRT2 | KRT2_2 | 6 | 2025-05-28 | 2025-05-30 | WK22(26-May - 01-Jun) | May |  | Implementation Under Plan (WP Received)
65 | KRT1879SNO | 1879 | SRAE_NON | 12.3414 | 106.2641 | ALU/ZTE | Kratie | B1 | KRT2 | KRT2_2 | 6 | 2025-05-28 | 2025-05-30 | WK22(26-May - 01-Jun) | May |  | Implementation Under Plan (WP Received)
66 | KRT1876SNO | 1876 | SRAE_RONEAM | 12.3014 | 106.3598 | ALU/ZTE | Kratie | B1 | KRT2 | KRT2_2 | 6 | 2025-05-28 | 2025-05-30 | WK22(26-May - 01-Jun) | May |  | Implementation Under Plan (WP Received)
67 | KRT0233SNO | 233 | SVAY_CHREAH | 12.2989 | 106.3058 | ALU/ZTE | Kratie | B1 | KRT2 | KRT2_2 | 6 | 2025-05-28 | 2025-05-30 | WK22(26-May - 01-Jun) | May |  | Implementation Under Plan (WP Received)
68 | KRT0776SNO | 776 | SVAY_CHREAH2 | 12.2243 | 106.2892 | ALU/ZTE | Kratie | B1 | KRT2 | KRT2_2 | 6 | 2025-05-28 | 2025-05-30 | WK22(26-May - 01-Jun) | May |  | Implementation Under Plan (WP Received)
69 | KRT1100CLG | 1100 | VEAL_KANSENG | 12.1148 | 106.0833 | ALU/ZTE | Kratie | B1 | KRT2 | KRT2_2 | 6 | 2025-05-28 | 2025-05-30 | WK22(26-May - 01-Jun) | May |  | Implementation Under Plan (WP Received)
70 | TKM0528MEM | 528 | CHOAM_KROVEAN | 11.7673 | 106.3356 | ALU/ZTE | Tboung Khmum | B1 | TKM1 | TKM1_1 | 7 | 2025-05-31 | 2025-06-03 | WK23(02-Jun - 08-Jun) | June |  | Implementation Under Plan (WP Received)
71 | TKM0766MEM | 766 | CLONG | 11.7065 | 106.2709 | ALU/ZTE | Tboung Khmum | B1 | TKM1 | TKM1_1 | 7 | 2025-05-31 | 2025-06-03 | WK23(02-Jun - 08-Jun) | June |  | Implementation Under Plan (WP Received)
72 | TKM0303MEM | 303 | KDOL_KGCHAM | 11.8987 | 106.3378 | ALU/ZTE | Tboung Khmum | B1 | TKM1 | TKM1_1 | 7 | 2025-05-31 | 2025-06-03 | WK23(02-Jun - 08-Jun) | June |  | Implementation Under Plan (WP Received)
73 | TKM1134MEM | 1134 | PHUM_SLA | 11.8644 | 106.3002 | ALU/ZTE | Tboung Khmum | B1 | TKM1 | TKM1_1 | 7 | 2025-05-31 | 2025-06-03 | WK23(02-Jun - 08-Jun) | June |  | Implementation Under Plan (WP Received)
74 | TKM1930MEM | 1930 | STUENG_ANGKAM | 11.7585 | 106.2716 | ALU/ZTE | Tboung Khmum | B1 | TKM1 | TKM1_1 | 7 | 2025-05-31 | 2025-06-03 | WK23(02-Jun - 08-Jun) | June |  | Implementation Under Plan (WP Received)
75 | TKM2118MEM | 2118 | CHUMNUM_POL | 11.9367 | 106.2439 | ALU/ZTE | Tboung Khmum | B1 | TKM1 | TKM1_2 | 7 | 2025-06-04 | 2025-06-06 | WK23(02-Jun - 08-Jun) | June |  | Implementation Under Plan (WP Received)
76 | TKM0749MEM | 749 | KAMPOAN | 11.9795 | 106.1118 | ALU/ZTE | Tboung Khmum | B1 | TKM1 | TKM1_2 | 7 | 2025-06-04 | 2025-06-06 | WK23(02-Jun - 08-Jun) | June |  | Implementation Under Plan (WP Received)
77 | TKM0751MEM | 751 | KAMPONG_DAMREL | 12.0459 | 106.048 | ALU/ZTE | Tboung Khmum | B1 | TKM1 | TKM1_2 | 7 | 2025-06-04 | 2025-06-06 | WK23(02-Jun - 08-Jun) | June |  | Implementation Under Plan (WP Received)
78 | TKM1836DBE | 1836 | SRAE_PRANG | 12.1444 | 105.988 | ALU/ZTE | Tboung Khmum | B1 | TKM1 | TKM1_2 | 7 | 2025-06-04 | 2025-06-06 | WK23(02-Jun - 08-Jun) | June |  | Implementation Under Plan (WP Received)
79 | TKM1833MEM | 1833 | SRAE_SAOM_CHAS | 11.9426 | 106.159 | ALU/ZTE | Tboung Khmum | B1 | TKM1 | TKM1_2 | 7 | 2025-06-04 | 2025-06-06 | WK23(02-Jun - 08-Jun) | June |  | Implementation Under Plan (WP Received)
80 | KRT2214PPS | 2214 | BOENG_CHRAENG | 12.4913 | 105.9853 | ALU/ZTE | Kratie | B1 | KRT3 | KRT3_1 | 7 | 2025-06-07 | 2025-06-10 | WK24(09-Jun - 15-Jun) | June |  | Implementation Under Plan (WP Received)
81 | KRT1936CBR | 1936 | BOS_LEAV_KRAOM | 12.4127 | 106.0502 | ALU/ZTE | Kratie | B1 | KRT3 | KRT3_1 | 7 | 2025-06-07 | 2025-06-10 | WK24(09-Jun - 15-Jun) | June |  | Implementation Under Plan (WP Received)
82 | KR004 | 2639 | KR004 | 12.4523 | 106.031 | HW | Kratie | B2 | KRT3 | KRT3_1 | 7 | 2025-06-07 | 2025-06-10 | WK24(09-Jun - 15-Jun) | June |  | Implementation Under Plan (WP Under TRC Approval)
83 | KR016SE | 3340 | KR016SE | 12.4967 | 106.0229 | HW | Kratie | B2 | KRT3 | KRT3_1 | 7 | 2025-06-07 | 2025-06-10 | WK24(09-Jun - 15-Jun) | June |  | Implementation Under Plan (WP Under TRC Approval)
84 | KRATIE | 47 | KRATIE | 12.4793 | 106.0209 | HW | Kratie | B2 | KRT3 | KRT3_1 | 7 | 2025-06-07 | 2025-06-10 | WK24(09-Jun - 15-Jun) | June |  | Implementation Under Plan (WP Under TRC Approval)
85 | KRATIE_MKT | 1960 | KRATIE_MKT | 12.4867 | 106.0199 | HW | Kratie | B2 | KRT3 | KRT3_1 | 7 | 2025-06-07 | 2025-06-10 | WK24(09-Jun - 15-Jun) | June |  | Implementation Under Plan (WP Under TRC Approval)
86 | KRT1003CBR | 1003 | ANG_CHANH | 12.4859 | 106.1271 | ALU/ZTE | Kratie | B1 | KRT3 | KRT3_2 | 8 | 2025-06-11 | 2025-06-13 | WK24(09-Jun - 15-Jun) | June |  | Implementation Under Plan (WP Received)
87 | KRT1869CBR | 1869 | CHRAVA | 12.5403 | 106.0854 | ALU/ZTE | Kratie | B1 | KRT3 | KRT3_2 | 8 | 2025-06-11 | 2025-06-13 | WK24(09-Jun - 15-Jun) | June |  | Implementation Under Plan (WP Received)
88 | KRT0410CBR | 410 | KAN_TOURT | 12.4589 | 106.1703 | ALU/ZTE | Kratie | B1 | KRT3 | KRT3_2 | 8 | 2025-06-11 | 2025-06-13 | WK24(09-Jun - 15-Jun) | June |  | Implementation Under Plan (WP Received)
89 | KRT1086CBR | 1086 | KARSANG_POGODA | 12.6183 | 106.0877 | ALU/ZTE | Kratie | B1 | KRT3 | KRT3_2 | 8 | 2025-06-11 | 2025-06-13 | WK24(09-Jun - 15-Jun) | June |  | Implementation Under Plan (WP Received)
90 | KRA033 | 3011 | KRA033 | 12.508 | 106.017 | HW | Kratie | B2 | KRT3 | KRT3_2 | 8 | 2025-06-11 | 2025-06-13 | WK24(09-Jun - 15-Jun) | June |  | Implementation Under Plan (WP Under TRC Approval)
91 | KRT6461KRC | 6461 | TKR001 | 12.4917 | 106.0177 | HW | Kratie | B2 |  |  | 8 | 2025-06-11 | 2025-06-13 | WK24(09-Jun - 15-Jun) | June |  | Implementation Under Plan (WP Under TRC Approval)
92 | OU_RUSSEI | 411 | OU_RUSSEI | 12.4995 | 106.0363 | HW | Kratie | B2 | KRT3 | KRT3_2 | 8 | 2025-06-11 | 2025-06-13 | WK24(09-Jun - 15-Jun) | June |  | Implementation Under Plan (WP Under TRC Approval)
93 | KRT0160CBR | 160 | SAMBOK | 12.6178 | 106.0225 | ALU/ZTE | Kratie | B1 | KRT3 | KRT3_2 | 8 | 2025-06-11 | 2025-06-13 | WK24(09-Jun - 15-Jun) | June |  | Implementation Under Plan (WP Received)
94 | KRT1663CBR | 1663 | THMA_KREAE_LEU | 12.5517 | 106.0099 | ALU/ZTE | Kratie | B1 | KRT3 | KRT3_2 | 8 | 2025-06-11 | 2025-06-13 | WK24(09-Jun - 15-Jun) | June |  | Implementation Under Plan (WP Received)
95 | STN1167TBV | 1167 | PHUM_OU_RAI | 13.4942 | 105.903 | ALU/ZTE | Stung Treng | B1 | STN1 | STN1_1 | 8 | 2025-06-14 | 2025-06-17 | WK25(16-Jun - 22-Jun) | June |  | Implementation Under Plan (WP Received)
96 | STN1109TBV | 1109 | PHUM_ROM_DENG | 13.5147 | 105.7311 | ALU/ZTE | Stung Treng | B1 | STN1 | STN1_1 | 8 | 2025-06-14 | 2025-06-17 | WK25(16-Jun - 22-Jun) | June |  | Implementation Under Plan (WP Received)
97 | STN0980TBV | 980 | SAM_ANG | 13.712 | 105.8352 | ALU/ZTE | Stung Treng | B1 | STN1 | STN1_1 | 8 | 2025-06-14 | 2025-06-17 | WK25(16-Jun - 22-Jun) | June |  | Implementation Under Plan (WP Received)
98 | STN1184TBV | 1184 | SPUNG | 13.5362 | 105.6108 | ALU/ZTE | Stung Treng | B1 | STN1 | STN1_1 | 8 | 2025-06-14 | 2025-06-17 | WK25(16-Jun - 22-Jun) | June |  | Implementation Under Plan (WP Received)
99 | STN1263TBV | 1263 | SRALAU | 13.7669 | 105.6668 | ALU/ZTE | Stung Treng | B1 | STN1 | STN1_1 | 8 | 2025-06-14 | 2025-06-17 | WK25(16-Jun - 22-Jun) | June |  | Implementation Under Plan (WP Received)
100 | STN1179TBV | 1179 | THALA_BARIVA | 13.5567 | 105.9546 | ALU/ZTE | Stung Treng | B1 | STN1 | STN1_1 | 8 | 2025-06-14 | 2025-06-17 | WK25(16-Jun - 22-Jun) | June |  | Implementation Under Plan (WP Received)
101 | KRT2016SBU | 2016 | CHANGHAB | 12.8117 | 106.1692 | ALU/ZTE | Kratie | B1 | KRT4 | KRT4_1 | 9 | 2025-06-18 | 2025-06-20 | WK25(16-Jun - 22-Jun) | June |  | Implementation Under Plan (WP Received)
102 | KRT0998SBU | 998 | OUTA_NEANG | 12.8587 | 106.1882 | ALU/ZTE | Kratie | B1 | KRT4 | KRT4_1 | 9 | 2025-06-18 | 2025-06-20 | WK25(16-Jun - 22-Jun) | June |  | Implementation Under Plan (WP Received)
103 | KRT0161SBU | 161 | SANDAN | 12.7673 | 105.968 | ALU/ZTE | Kratie | B1 | KRT4 | KRT4_1 | 9 | 2025-06-18 | 2025-06-20 | WK25(16-Jun - 22-Jun) | June |  | Implementation Under Plan (WP Received)
104 | KRT2154CBR | 2154 | SANGKOM | 12.6716 | 106.1081 | ALU/ZTE | Kratie | B1 | KRT4 | KRT4_1 | 9 | 2025-06-18 | 2025-06-20 | WK25(16-Jun - 22-Jun) | June |  | Implementation Under Plan (WP Received)
105 | KRT2017SBU | 2017 | SRAE_SBOV | 12.8916 | 106.1966 | ALU/ZTE | Kratie | B1 | KRT4 | KRT4_1 | 9 | 2025-06-18 | 2025-06-20 | WK25(16-Jun - 22-Jun) | June |  | Implementation Under Plan (WP Received)
106 | KRT1880SBU | 1880 | SRAE_TRAENG | 12.7638 | 106.1418 | ALU/ZTE | Kratie | B1 | KRT4 | KRT4_1 | 9 | 2025-06-18 | 2025-06-20 | WK25(16-Jun - 22-Jun) | June |  | Implementation Under Plan (WP Received)
107 | KRT0401SBU | 401 | THMEI | 12.7058 | 106.048 | ALU/ZTE | Kratie | B1 | KRT4 | KRT4_1 | 9 | 2025-06-18 | 2025-06-20 | WK25(16-Jun - 22-Jun) | June |  | Implementation Under Plan (WP Received)
108 | STN0600SBK | 600 | KOAN_PREAH | 13.3553 | 105.969 | ALU/ZTE | Stung Treng | B1 | STN1 | STN1_2 | 9 | 2025-06-21 | 2025-06-24 | WK26(23-Jun - 29-Jun) | June |  | Implementation Under Plan (WP Received)
109 | STN1226SBK | 1226 | OU_MREAH | 13.2545 | 105.971 | ALU/ZTE | Stung Treng | B1 | STN1 | STN1_2 | 9 | 2025-06-21 | 2025-06-24 | WK26(23-Jun - 29-Jun) | June |  | Implementation Under Plan (WP Received)
110 | STN0407STG | 407 | O_PONG_MUAN | 13.4424 | 106.0662 | ALU/ZTE | Stung Treng | B1 | STN1 | STN1_2 | 9 | 2025-06-21 | 2025-06-24 | WK26(23-Jun - 29-Jun) | June |  | Implementation Under Plan (WP Received)
111 | STN2063SSA | 2063 | O_PONG_MUAN2 | 13.4152 | 106.2025 | ALU/ZTE | Stung Treng | B1 | STN1 | STN1_2 | 9 | 2025-06-21 | 2025-06-24 | WK26(23-Jun - 29-Jun) | June |  | Implementation Under Plan (WP Received)
112 | STN2137SSA | 2137 | PHLUK | 13.4203 | 106.2777 | ALU/ZTE | Stung Treng | B1 | STN1 | STN1_2 | 9 | 2025-06-21 | 2025-06-24 | WK26(23-Jun - 29-Jun) | June |  | Implementation Under Plan (WP Received)
113 | STN1211SBK | 1211 | SIEM_BOUK | 13.286 | 105.924 | ALU/ZTE | Stung Treng | B1 | STN1 | STN1_2 | 9 | 2025-06-21 | 2025-06-24 | WK26(23-Jun - 29-Jun) | June |  | Implementation Under Plan (WP Received)
114 | KRT0400SBU | 400 | OU_KRIENG | 13.0272 | 106.1796 | ALU/ZTE | Kratie | B1 | KRT4 | KRT4_2 | 10 | 2025-06-25 | 2025-06-27 | WK26(23-Jun - 29-Jun) | June |  | Implementation Under Plan (WP Received)
115 | KRT1020SBU | 1020 | OU_PREAH | 13.1502 | 106.153 | ALU/ZTE | Kratie | B1 | KRT4 | KRT4_2 | 10 | 2025-06-25 | 2025-06-27 | WK26(23-Jun - 29-Jun) | June |  | Implementation Under Plan (WP Received)
116 | KRT2167SBU | 2167 | OU_PREAH1 | 13.2889 | 106.1038 | ALU/ZTE | Kratie | B1 | KRT4 | KRT4_2 | 10 | 2025-06-25 | 2025-06-27 | WK26(23-Jun - 29-Jun) | June |  | Implementation Under Plan (WP Received)
117 | KRT1872SBU | 1872 | OU_PREAH2 | 13.1963 | 106.1332 | ALU/ZTE | Kratie | B1 | KRT4 | KRT4_2 | 10 | 2025-06-25 | 2025-06-27 | WK26(23-Jun - 29-Jun) | June |  | Implementation Under Plan (WP Received)
118 | KRT2013SBU | 2013 | OU_PREAH3 | 13.2479 | 106.1218 | ALU/ZTE | Kratie | B1 | KRT4 | KRT4_2 | 10 | 2025-06-25 | 2025-06-27 | WK26(23-Jun - 29-Jun) | June |  | Implementation Under Plan (WP Received)
119 | KRT1656SBU | 1656 | OU_RUESSEI_KANDAL | 13.3527 | 106.0936 | ALU/ZTE | Kratie | B1 | KRT4 | KRT4_2 | 10 | 2025-06-25 | 2025-06-27 | WK26(23-Jun - 29-Jun) | June |  | Implementation Under Plan (WP Received)
120 | STN2062SSA | 2062 | BAN_MAI | 13.5481 | 106.0857 | ALU/ZTE | Stung Treng | B1 | STN1 | STN1_3 | 10 | 2025-06-28 | 2025-07-01 | WK27(30-Jun - 06-Jul) | July |  | Implementation Under Plan (WP Received)
121 | STN2222STG | 2222 | HANG_KHOU_BAN | 13.538 | 106.0083 | ALU/ZTE | Stung Treng | B1 | STN1 | STN1_3 | 10 | 2025-06-28 | 2025-07-01 | WK27(30-Jun - 06-Jul) | July |  | Implementation Under Plan (WP Received)
122 | STN0602STG | 602 | SAMEAKI | 13.5813 | 106.0386 | ALU/ZTE | Stung Treng | B1 | STN1 | STN1_3 | 10 | 2025-06-28 | 2025-07-01 | WK27(30-Jun - 06-Jul) | July |  | Implementation Under Plan (WP Received)
123 | ST026 | 2672 | ST026 | 13.5207 | 105.972 | HW | Stung Treng | B2 | STN1 | STN1_3 | 10 | 2025-06-28 | 2025-07-01 | WK27(30-Jun - 06-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
124 | STUNG_TRENG | 413 | STUNG_TRENG | 13.5285 | 105.9683 | HW | Stung Treng | B2 | STN1 | STN1_3 | 10 | 2025-06-28 | 2025-07-01 | WK27(30-Jun - 06-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
125 | STUNG_TRENG_HILL | 371 | STUNG_TRENG_HILL | 13.5179 | 105.9665 | HW | Stung Treng | B2 | STN1 | STN1_3 | 10 | 2025-06-28 | 2025-07-01 | WK27(30-Jun - 06-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
126 | STN2133STG | 2133 | KAOH_KEI | 13.7632 | 106.1027 | ALU/ZTE | Stung Treng | B1 | STN2 | STN2_1 | 11 | 2025-07-02 | 2025-07-04 | WK27(30-Jun - 06-Jul) | July |  | Implementation Under Plan (WP Received)
127 | STN2223STG | 2223 | KAOH_PNOV | 13.9058 | 106.1085 | ALU/ZTE | Stung Treng | B1 | STN2 | STN2_1 | 11 | 2025-07-02 | 2025-07-04 | WK27(30-Jun - 06-Jul) | July |  | Implementation Under Plan (WP Received)
128 | STN2134STG | 2134 | KAOH_SNAENG | 13.6973 | 106.0832 | ALU/ZTE | Stung Treng | B1 | STN2 | STN2_1 | 11 | 2025-07-02 | 2025-07-04 | WK27(30-Jun - 06-Jul) | July |  | Implementation Under Plan (WP Received)
129 | STN1658SPG | 1658 | KET_MOEANG | 14.0098 | 106.3272 | ALU/ZTE | Stung Treng | B1 | STN2 | STN2_1 | 11 | 2025-07-02 | 2025-07-04 | WK27(30-Jun - 06-Jul) | July |  | Implementation Under Plan (WP Received)
130 | STN2132SPG | 2132 | NA_OUNG | 13.9958 | 106.1907 | ALU/ZTE | Stung Treng | B1 | STN2 | STN2_1 | 11 | 2025-07-02 | 2025-07-04 | WK27(30-Jun - 06-Jul) | July |  | Implementation Under Plan (WP Received)
131 | STN2232STG | 2232 | OU_RUN | 13.8325 | 106.0931 | ALU/ZTE | Stung Treng | B1 | STN2 | STN2_1 | 11 | 2025-07-02 | 2025-07-04 | WK27(30-Jun - 06-Jul) | July |  | Implementation Under Plan (WP Received)
132 | STN0406SPG | 406 | SEKONG | 14.1065 | 106.3856 | ALU/ZTE | Stung Treng | B1 | STN2 | STN2_1 | 11 | 2025-07-02 | 2025-07-04 | WK27(30-Jun - 06-Jul) | July |  | Implementation Under Plan (WP Received)
133 | DAOH_KRAMOM | 2221 | DAOH_KRAMOM | 12.4622 | 107.1848 | HW | Mondul Kiri | B2 | MKR1 | MKR1_1 | 11 | 2025-07-05 | 2025-07-08 | WK28(07-Jul - 13-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
134 | MKR0469KSM | 469 | KEO_SEYMA | 12.1067 | 106.8835 | ALU/ZTE | Mondul Kiri | B1 | MKR1 | MKR1_1 | 11 | 2025-07-05 | 2025-07-08 | WK28(07-Jul - 13-Jul) | July |  | Implementation Under Plan (WP Received)
135 | MKR2180SMR | 2180 | LAUKA | 12.5003 | 107.1689 | ALU/ZTE | Mondul Kiri | B1 | MKR1 | MKR1_1 | 11 | 2025-07-05 | 2025-07-08 | WK28(07-Jul - 13-Jul) | July |  | Implementation Under Plan (WP Received)
136 | MONDULKIRI | 78 | MONDULKIRI | 12.4466 | 107.1983 | HW | Mondul Kiri | B2 | MKR1 | MKR1_1 | 11 | 2025-07-05 | 2025-07-08 | WK28(07-Jul - 13-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
137 | MKR1309ORG | 1309 | SEN_MONOROM | 12.3316 | 107.1485 | ALU/ZTE | Mondul Kiri | B1 | MKR1 | MKR1_1 | 11 | 2025-07-05 | 2025-07-08 | WK28(07-Jul - 13-Jul) | July |  | Implementation Under Plan (WP Received)
138 | MKR0811KSM | 811 | SRAE_PREAH | 12.1888 | 106.8786 | ALU/ZTE | Mondul Kiri | B1 | MKR1 | MKR1_1 | 11 | 2025-07-05 | 2025-07-08 | WK28(07-Jul - 13-Jul) | July |  | Implementation Under Plan (WP Received)
139 | MKR1613KSM | 1613 | SRE_KTHOM | 12.114 | 106.7912 | ALU/ZTE | Mondul Kiri | B1 | MKR1 | MKR1_1 | 11 | 2025-07-05 | 2025-07-08 | WK28(07-Jul - 13-Jul) | July |  | Implementation Under Plan (WP Received)
140 | STN0159TBV | 159 | ANLONG_SVAY | 13.9214 | 106.0061 | ALU/ZTE | Stung Treng | B1 | STN2 | STN2_2 | 12 | 2025-07-09 | 2025-07-11 | WK28(07-Jul - 13-Jul) | July |  | Implementation Under Plan (WP Received)
141 | PVH1906CAB | 1906 | KAMPONG_CHREY | 13.9871 | 105.83 | ALU/ZTE | Preah Vihear | B1 | STN2 | STN2_2 | 12 | 2025-07-09 | 2025-07-11 | WK28(07-Jul - 13-Jul) | July |  | Implementation Under Plan (WP Received)
142 | PVH1342CAB | 1342 | KG_SRA_LAU | 14.0867 | 105.77 | ALU/ZTE | Preah Vihear | B1 | STN2 | STN2_2 | 12 | 2025-07-09 | 2025-07-11 | WK28(07-Jul - 13-Jul) | July |  | Implementation Under Plan (WP Received)
143 | MKR0472PCD | 472 | BUSRA | 12.5505 | 107.4262 | ALU/ZTE | Mondul Kiri | B1 | MKR1 | MKR1_2 | 12 | 2025-07-12 | 2025-07-15 | WK29(14-Jul - 20-Jul) | July |  | Implementation Under Plan (WP Received)
144 | MKR1437PCD | 1437 | CHONG_PHANG | 12.7735 | 107.1525 | ALU/ZTE | Mondul Kiri | B1 | MKR1 | MKR1_2 | 12 | 2025-07-12 | 2025-07-15 | WK29(14-Jul - 20-Jul) | July |  | Implementation Under Plan (WP Received)
145 | MKR2131PCD | 2131 | PU_CHREY_CHONG_PHANG | 12.6729 | 107.233 | ALU/ZTE | Mondul Kiri | B1 | MKR1 | MKR1_2 | 12 | 2025-07-12 | 2025-07-15 | WK29(14-Jul - 20-Jul) | July |  | Implementation Under Plan (WP Received)
146 | MKR2136PCD | 2136 | PU_KROUCH | 12.5384 | 107.3126 | ALU/ZTE | Mondul Kiri | B1 | MKR1 | MKR1_2 | 12 | 2025-07-12 | 2025-07-15 | WK29(14-Jul - 20-Jul) | July |  | Implementation Under Plan (WP Received)
147 | MKR1805ORG | 1805 | PU_LUNG | 12.4814 | 107.2415 | ALU/ZTE | Mondul Kiri | B1 | MKR1 | MKR1_2 | 12 | 2025-07-12 | 2025-07-15 | WK29(14-Jul - 20-Jul) | July |  | Implementation Under Plan (WP Received)
148 | MKR1095KNK | 1095 | TI_PRAM | 12.9991 | 107.0202 | ALU/ZTE | Mondul Kiri | B1 | MKR1 | MKR1_2 | 12 | 2025-07-12 | 2025-07-15 | WK29(14-Jul - 20-Jul) | July |  | Implementation Under Plan (WP Received)
149 | MKR1098SMR | 1098 | TOUL_PRING | 12.6428 | 107.2107 | ALU/ZTE | Mondul Kiri | B1 | MKR1 | MKR1_2 | 12 | 2025-07-12 | 2025-07-15 | WK29(14-Jul - 20-Jul) | July |  | Implementation Under Plan (WP Received)
150 | RTK2103OCM | 2103 | KALAI_BEI | 13.8561 | 106.9333 | ALU/ZTE | Ratanak Kiri | B2 | RTK1 | RTK1_1 | 13 | 2025-07-16 | 2025-07-18 | WK29(14-Jul - 20-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
151 | RTK2130OCM | 2130 | LEUN_CHONG | 13.7943 | 107.0415 | ALU/ZTE | Ratanak Kiri | B2 | RTK1 | RTK1_1 | 13 | 2025-07-16 | 2025-07-18 | WK29(14-Jul - 20-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
152 | RTK0607VNS | 607 | TA_YAOK | 13.971 | 106.8165 | ALU/ZTE | Ratanak Kiri | B2 | RTK1 | RTK1_1 | 13 | 2025-07-16 | 2025-07-18 | WK29(14-Jul - 20-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
153 | RTK2042VNS | 2042 | VANG | 13.9065 | 106.8858 | ALU/ZTE | Ratanak Kiri | B2 | RTK1 | RTK1_1 | 13 | 2025-07-16 | 2025-07-18 | WK29(14-Jul - 20-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
154 | RTK0747OCM | 747 | VEUN_SAI | 13.8048 | 106.9946 | ALU/ZTE | Ratanak Kiri | B2 | RTK1 | RTK1_1 | 13 | 2025-07-16 | 2025-07-18 | WK29(14-Jul - 20-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
155 | RTK1245OCM | 1245 | BAR_NHOK | 13.8029 | 107.1004 | ALU/ZTE | Ratanak Kiri | B2 | RTK1 | RTK1_2 | 13 | 2025-07-19 | 2025-07-22 | WK30(21-Jul - 27-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
156 | RTK1186OCM | 1186 | KAMENG | 13.9248 | 107.0075 | ALU/ZTE | Ratanak Kiri | B2 | RTK1 | RTK1_2 | 13 | 2025-07-19 | 2025-07-22 | WK30(21-Jul - 27-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
157 | RTK2104OCM | 2104 | KRALA | 13.8807 | 107.0123 | ALU/ZTE | Ratanak Kiri | B2 | RTK1 | RTK1_2 | 13 | 2025-07-19 | 2025-07-22 | WK30(21-Jul - 27-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
158 | RTK1306OCM | 1306 | PHUM_PIR | 13.8427 | 107.0569 | ALU/ZTE | Ratanak Kiri | B2 | RTK1 | RTK1_2 | 13 | 2025-07-19 | 2025-07-22 | WK30(21-Jul - 27-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
159 | RTK2043OCM | 2043 | TA_NGEACH | 13.91 | 107.0523 | ALU/ZTE | Ratanak Kiri | B2 | RTK1 | RTK1_2 | 13 | 2025-07-19 | 2025-07-22 | WK30(21-Jul - 27-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
160 | RTK0981TVG | 981 | TUMPUONG_REUNG_TOUCH | 14.0372 | 107.1057 | ALU/ZTE | Ratanak Kiri | B2 | RTK1 | RTK1_2 | 13 | 2025-07-19 | 2025-07-22 | WK30(21-Jul - 27-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
161 | BANLUNG_MKT | 1971 | BANLUNG_MKT | 13.7357 | 106.9883 | HW | Ratanak Kiri | B2 | RTK2 | RTK2_1 | 14 | 2025-07-23 | 2025-07-25 | WK30(21-Jul - 27-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
162 | LABANSIEK | 372 | LABANSIEK | 13.7382 | 106.9884 | HW | Ratanak Kiri | B2 | RTK2 | RTK2_1 | 14 | 2025-07-23 | 2025-07-25 | WK30(21-Jul - 27-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
163 | RTK1908OCM | 1908 | PA_CHON_THUM | 13.7487 | 107.0587 | ALU/ZTE | Ratanak Kiri | B2 | RTK2 | RTK2_1 | 14 | 2025-07-23 | 2025-07-25 | WK30(21-Jul - 27-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
164 | RTK1355OCM | 1355 | PHUM_PAROR | 13.7493 | 107.0962 | ALU/ZTE | Ratanak Kiri | B2 | RTK2 | RTK2_1 | 14 | 2025-07-23 | 2025-07-25 | WK30(21-Jul - 27-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
165 | PHUM_PRAMMUOY | 2026 | PHUM_PRAMMUOY | 13.752 | 106.987 | HW | Ratanak Kiri | B2 | RTK2 | RTK2_1 | 14 | 2025-07-23 | 2025-07-25 | WK30(21-Jul - 27-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
166 | SEL | 2197 | SEL | 13.7431 | 107.014 | HW | Ratanak Kiri | B2 | RTK2 | RTK2_1 | 14 | 2025-07-23 | 2025-07-25 | WK30(21-Jul - 27-Jul) | July |  | Implementation Under Plan (WP Under TRC Approval)
167 | RTK1527BNL | 1527 | KACHANH_TATUENG | 13.6971 | 106.987 | ALU/ZTE | Ratanak Kiri | B2 | RTK2 | RTK2_2 | 14 | 2025-07-26 | 2025-07-29 | WK31(28-Jul - 03-Aug) | July |  | Implementation Under Plan (WP Under TRC Approval)
168 | RTK0475LPT | 475 | LOMPHAT_TOWN | 13.4919 | 106.9817 | ALU/ZTE | Ratanak Kiri | B2 | RTK2 | RTK2_2 | 14 | 2025-07-26 | 2025-07-29 | WK31(28-Jul - 03-Aug) | July |  | Implementation Under Plan (WP Under TRC Approval)
169 | RTK6468BNL | 6468 | TRR001 | 13.7345 | 106.9805 | HW | Ratanak Kiri | B2 |  |  | 14 | 2025-07-26 | 2025-07-29 | WK31(28-Jul - 03-Aug) | July |  | Implementation Under Plan (WP Under TRC Approval)
170 | RTK1116KMM | 1116 | PHUM_LAR_INN | 13.6166 | 106.8753 | ALU/ZTE | Ratanak Kiri | B2 | RTK2 | RTK2_2 | 14 | 2025-07-26 | 2025-07-29 | WK31(28-Jul - 03-Aug) | July |  | Implementation Under Plan (WP Under TRC Approval)
171 | RATANAKIRI | 2355 | RATANAKIRI | 13.7345 | 106.9673 | HW | Ratanak Kiri | B2 | RTK2 | RTK2_2 | 14 | 2025-07-26 | 2025-07-29 | WK31(28-Jul - 03-Aug) | July |  | Implementation Under Plan (WP Under TRC Approval)
172 | RTK2044KMM | 2044 | TA_ANG_KA_TE | 13.6839 | 106.9381 | ALU/ZTE | Ratanak Kiri | B2 | RTK2 | RTK2_2 | 14 | 2025-07-26 | 2025-07-29 | WK31(28-Jul - 03-Aug) | July |  | Implementation Under Plan (WP Under TRC Approval)
173 | RTK0402KMM | 402 | TRAPEANG_CHRES | 13.5776 | 106.761 | ALU/ZTE | Ratanak Kiri | B2 | RTK2 | RTK2_2 | 14 | 2025-07-26 | 2025-07-29 | WK31(28-Jul - 03-Aug) | July |  | Implementation Under Plan (WP Under TRC Approval)
174 | RTK1123KMM | 1123 | TRAPEANG_KRAHAM | 13.5454 | 106.6871 | ALU/ZTE | Ratanak Kiri | B2 | RTK2 | RTK2_2 | 14 | 2025-07-26 | 2025-07-29 | WK31(28-Jul - 03-Aug) | July |  | Implementation Under Plan (WP Under TRC Approval)
175 | RTK0982BNL | 982 | CHUM_RUMBEISROK | 13.6217 | 107.0759 | ALU/ZTE | Ratanak Kiri | B2 | RTK3 | RTK3_1 | 15 | 2025-07-30 | 2025-08-01 | WK31(28-Jul - 03-Aug) | August |  | Implementation Under Plan (WP Under TRC Approval)
176 | RTK0984ADM | 984 | KACHUT | 13.8646 | 107.2979 | ALU/ZTE | Ratanak Kiri | B2 | RTK3 | RTK3_1 | 15 | 2025-07-30 | 2025-08-01 | WK31(28-Jul - 03-Aug) | August |  | Implementation Under Plan (WP Under TRC Approval)
177 | RTK1265BKV | 1265 | LUE_KHOUN | 13.7503 | 107.2496 | ALU/ZTE | Ratanak Kiri | B2 | RTK3 | RTK3_1 | 15 | 2025-07-30 | 2025-08-01 | WK31(28-Jul - 03-Aug) | August |  | Implementation Under Plan (WP Under TRC Approval)
178 | RTK1125BKV | 1125 | PHUM_CHAK | 13.7099 | 107.1184 | ALU/ZTE | Ratanak Kiri | B2 | RTK3 | RTK3_1 | 15 | 2025-07-30 | 2025-08-01 | WK31(28-Jul - 03-Aug) | August |  | Implementation Under Plan (WP Under TRC Approval)
179 | RTK1308BKV | 1308 | PHUM_KAK | 13.7069 | 107.2358 | ALU/ZTE | Ratanak Kiri | B2 | RTK3 | RTK3_1 | 15 | 2025-07-30 | 2025-08-01 | WK31(28-Jul - 03-Aug) | August |  | Implementation Under Plan (WP Under TRC Approval)
180 | RTK1110BKV | 1110 | PHUM_LUNG_KHUNG | 13.6605 | 107.1472 | ALU/ZTE | Ratanak Kiri | B2 | RTK3 | RTK3_1 | 15 | 2025-07-30 | 2025-08-01 | WK31(28-Jul - 03-Aug) | August |  | Implementation Under Plan (WP Under TRC Approval)
181 | RTK0403BKV | 403 | LAMINH | 13.6824 | 107.2018 | ALU/ZTE | Ratanak Kiri | B2 | RTK3 | RTK3_2 | 15 | 2025-08-02 | 2025-08-05 | WK32(04-Aug - 10-Aug) | August |  | Implementation Under Plan (WP Under TRC Approval)
182 | RTK0257OYD | 257 | OR_YADAV | 13.6708 | 107.3486 | ALU/ZTE | Ratanak Kiri | B2 | RTK3 | RTK3_2 | 15 | 2025-08-02 | 2025-08-05 | WK32(04-Aug - 10-Aug) | August |  | Implementation Under Plan (WP Under TRC Approval)
183 | RTK1176OYD | 1176 | PHUM_PRILL | 13.6308 | 107.299 | ALU/ZTE | Ratanak Kiri | B2 | RTK3 | RTK3_2 | 15 | 2025-08-02 | 2025-08-05 | WK32(04-Aug - 10-Aug) | August |  | Implementation Under Plan (WP Under TRC Approval)
184 | RTK1150OYD | 1150 | POK_THOM | 13.7518 | 107.4274 | ALU/ZTE | Ratanak Kiri | B2 | RTK3 | RTK3_2 | 15 | 2025-08-02 | 2025-08-05 | WK32(04-Aug - 10-Aug) | August |  | Implementation Under Plan (WP Under TRC Approval)
185 | RTK0384OYD | 384 | SE_SAN | 13.765 | 107.4859 | ALU/ZTE | Ratanak Kiri | B2 | RTK3 | RTK3_2 | 15 | 2025-08-02 | 2025-08-05 | WK32(04-Aug - 10-Aug) | August |  | Implementation Under Plan (WP Under TRC Approval)

## ALU PROJECT_HUAWEI_REDEPLOY(20)
No. | SiteName | Province | LON | LAT | SoW | OA Forecast End | Forecast OA Date | OA Week Number End | OA Month | OA Actual | GAP OA Analysis
1 | PP1239 | Phnom Penh | 104.8666 | 11.5245 | 20 HW Redeploy | 2025-05-16 | 2025-05-18 | WK20(12-May - 18-May) | May |  | Implementation Under Plan
2 | PP243 | Phnom Penh | 104.826 | 11.5273 | 20 HW Redeploy | 2025-05-16 | 2025-05-18 | WK20(12-May - 18-May) | May |  | Implementation Under Plan
3 | TPP069 | Phnom Penh | 104.8873 | 11.4978 | 20 HW Redeploy | 2025-05-16 | 2025-05-18 | WK20(12-May - 18-May) | May |  | Implementation Under Plan
4 | New_PPF125-cootel | Phnom Penh | 104.82 | 11.5366 | 20 HW Redeploy | 2025-05-19 | 2025-05-21 | WK21(19-May - 25-May) | May |  | Implementation Under Plan
5 | PP366 | Phnom Penh | 104.809 | 11.531 | 20 HW Redeploy | 2025-05-19 | 2025-05-21 | WK21(19-May - 25-May) | May |  | Implementation Under Plan
6 | VIP Vital Complaint | Phnom Penh | 104.8065 | 11.598 | 20 HW Redeploy | 2025-05-19 | 2025-05-21 | WK21(19-May - 25-May) | May |  | Implementation Under Plan
7 | PP289a | Phnom Penh | 104.826 | 11.5224 | 20 HW Redeploy | 2025-05-22 | 2025-05-24 | WK21(19-May - 25-May) | May |  | Implementation Under Plan
8 | PP344SE | Kandal | 104.749 | 11.5217 | 20 HW Redeploy | 2025-05-22 | 2025-05-24 | WK21(19-May - 25-May) | May |  | Implementation Under Plan
9 | TPP064 | Phnom Penh | 104.8456 | 11.5825 | 20 HW Redeploy | 2025-05-22 | 2025-05-24 | WK21(19-May - 25-May) | May |  | Implementation Under Plan
10 | KandalSteung_CC_03 | Kandal | 104.8273 | 11.4381 | 20 HW Redeploy | 2025-05-25 | 2025-05-27 | WK22(26-May - 01-Jun) | May |  | Implementation Under Plan
11 | PP444 | Phnom Penh | 104.924 | 11.6018 | 20 HW Redeploy | 2025-05-25 | 2025-05-27 | WK22(26-May - 01-Jun) | May |  | Implementation Under Plan
12 | Phum Mongkul | Phnom Penh | 104.8326 | 11.6091 | 20 HW Redeploy | 2025-05-25 | 2025-05-27 | WK22(26-May - 01-Jun) | May |  | Implementation Under Plan
13 | 3rd_RingRoad_CC_11 | Phnom Penh | 104.837 | 11.4393 | 20 HW Redeploy | 2025-05-28 | 2025-05-30 | WK22(26-May - 01-Jun) | May |  | Implementation Under Plan
14 | GPP34 | Phnom Penh | 104.912 | 11.6724 | 20 HW Redeploy | 2025-05-28 | 2025-05-30 | WK22(26-May - 01-Jun) | May |  | Implementation Under Plan
15 | KD185 | Kandal | 104.741 | 11.5098 | 20 HW Redeploy | 2025-05-28 | 2025-05-30 | WK22(26-May - 01-Jun) | May |  | Implementation Under Plan
16 | PPB028 | Phnom Penh | 104.906 | 11.6683 | 20 HW Redeploy | 2025-05-31 | 2025-06-02 | WK23(02-Jun - 08-Jun) | June |  | Implementation Under Plan
17 | PPB120 | Phnom Penh | 104.907 | 11.6458 | 20 HW Redeploy | 2025-05-31 | 2025-06-02 | WK23(02-Jun - 08-Jun) | June |  | Implementation Under Plan
18 | PraekPnov_5 | Phnom Penh | 104.754 | 11.5927 | 20 HW Redeploy | 2025-05-31 | 2025-06-02 | WK23(02-Jun - 08-Jun) | June |  | Implementation Under Plan
19 | PPB040 | Phnom Penh | 104.897 | 11.6471 | 20 HW Redeploy | 2025-06-03 | 2025-06-05 | WK23(02-Jun - 08-Jun) | June |  | Implementation Under Plan
20 | SV231 | Preah Sihanouk | 103.6184 | 10.7254 | 20 HW Redeploy | 2025-06-03 | 2025-06-05 | WK23(02-Jun - 08-Jun) | June |  | Implementation Under Plan

## BTB PROJECT_NOKIA_SWAP(349)
No. | SBTS | SiteName | Solution | SSC | LON | LAT | Existing BTS | Cluster_ID | Swap_Batch | Province | Forecast OA Date | Swap Forecast Week | OA Month | OA Actual | GAP OA Analysis
1 | BTB0021BTB | BATTAMBANG1 | 3*4T4R | 21 | 103.1978 | 13.0937 | Nokia | BTB03 | 1 | Battambang | 2025-04-05 | WK14(31-Mar - 06-Apr) | April | 2025-04-05
2 | BTB0378BTB | ROM_CHEK | 3*2T2R | 378 | 103.2047 | 13.096 | Nokia | BTB03 | 1 | Battambang | 2025-04-05 | WK14(31-Mar - 06-Apr) | April | 2025-04-05
3 | BTB0690BTB | BATTAMBANG14 | 3*2T2R | 690 | 103.2039 | 13.0925 | Nokia | BTB03 | 1 | Battambang | 2025-04-05 | WK14(31-Mar - 06-Apr) | April | 2025-04-05
4 | BTB0691BTB | BATTAMBANG15 | 3*2T2R | 691 | 103.1952 | 13.0949 | Nokia | BTB03 | 1 | Battambang | 2025-04-05 | WK14(31-Mar - 06-Apr) | April | 2025-04-05
5 | BTB1602BTB | NUM_KRIEB | 3*2T2R | 1602 | 103.2025 | 13.0959 | Nokia | BTB03 | 1 | Battambang | 2025-04-05 | WK14(31-Mar - 06-Apr) | April | 2025-04-05
6 | BTB5682BTB | BB143 | 3*2T2R | 5682 | 103.203 | 13.0984 | Nokia | BTB03 | 1 | Battambang | 2025-04-05 | WK14(31-Mar - 06-Apr) | April | 2025-04-05
7 | BTB5686BTB | BB020 | 3*4T4R | 5686 | 103.1951 | 13.0918 | Nokia | BTB03 | 1 | Battambang | 2025-04-05 | WK14(31-Mar - 06-Apr) | April | 2025-04-07
8 | BTB0173BTB | PSAR_THMEY | 2*4T4R+1*4T6S | 173 | 103.2123 | 13.0855 | Nokia | BTB04 | 2 | Battambang | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-07
9 | BTB0286BTB | ANDONG_PRING | 3*4T4R | 286 | 103.1916 | 13.0829 | Nokia | BTB04 | 2 | Battambang | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-07
10 | BTB0505BTB | BATTAMBANG6 | 3*2T2R | 505 | 103.1994 | 13.0864 | Nokia | BTB04 | 2 | Battambang | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-07
11 | BTB0581BTB | BATTAMBANG7 | 3*4T4R | 581 | 103.213 | 13.0894 | Nokia | BTB04 | 2 | Battambang | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-07
12 | BTB0952BTB | KOM_KOR | 3*2T2R | 952 | 103.2009 | 13.0819 | Nokia | BTB04 | 2 | Battambang | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-07
13 | BTB1463BTB | BAEK_CHAN_THMEI | 3*4T4R | 1463 | 103.209 | 13.0884 | Nokia | BTB04 | 2 | Battambang | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-07
14 | BTB1472BTB | OU_TA_KAM_PIR | 3*2T2R | 1472 | 103.1955 | 13.0884 | Nokia | BTB04 | 2 | Battambang | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-07
15 | BTB6211SKE | BB278 | 3*4T4R | 6211 | 103.2034 | 13.078 | Nokia | BTB04 | 2 | Battambang | 2025-04-07 | WK15(07-Apr - 13-Apr) | April | 2025-04-07
16 | BTB0059BTB | BATTAMBANG2 | 3*2T2R | 59 | 103.1955 | 13.1073 | Nokia | BTB02 | 3 | Battambang | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
17 | BTB0396BTB | PHSAR_NAT | 3*2T2R | 396 | 103.1973 | 13.1012 | Nokia | BTB02 | 3 | Battambang | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
18 | BTB0582BTB | BATTAMBANG8 | 2*4T4R+1*4T6S | 582 | 103.1931 | 13.1049 | Nokia | BTB02 | 3 | Battambang | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-10
19 | BTB0652BTB | BATTAMBANG9 | 3*4T4R | 652 | 103.1939 | 13.1092 | Nokia | BTB02 | 3 | Battambang | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
20 | BTB0653BTB | CK_SAMRAONG3 | 3*4T4R | 653 | 103.2076 | 13.1171 | Nokia | BTB02 | 3 | Battambang | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
21 | BTB0654BTB | CK_SAMRAONG4 | 2*4T4R+1*4T6S | 654 | 103.214 | 13.1139 | Nokia | BTB02 | 3 | Battambang | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
22 | BTB0922BTB | CHROY | 3*4T4R | 922 | 103.1821 | 13.0941 | Nokia | BTB02 | 3 | Battambang | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
23 | BTB1455BTB | TUOL_TA_AEK | 3*4T4R | 1455 | 103.1882 | 13.1015 | Nokia | BTB02 | 3 | Battambang | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
24 | BTB1456BTB | PHKA_SLA | 2*4T4R+1*4T6S | 1456 | 103.197 | 13.1169 | Nokia | BTB02 | 3 | Battambang | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
25 | BTB1471BTB | KAMPONG_KRABEI | 3*2T2R | 1471 | 103.2013 | 13.1011 | Nokia | BTB02 | 3 | Battambang | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
26 | BTB2056BTB | STAR_HTL | 3*4T6S | 2056 | 103.2 | 13.1057 | Nokia | BTB02 | 3 | Battambang | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
27 | BTB2599BTB | BB078 | 3*4T4R | 2599 | 103.1852 | 13.1088 | Nokia | BTB02 | 3 | Battambang | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-10
28 | BTB5683BTB | BB007SE | 3*2T2R | 5683 | 103.1969 | 13.0968 | Nokia | BTB02 | 3 | Battambang | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
29 | BTB6260BTB | TBB001 | 2*4T4R+1*4T6S | 6260 | 103.192 | 13.0974 | Nokia | BTB02 | 3 | Battambang | 2025-04-09 | WK15(07-Apr - 13-Apr) | April | 2025-04-09
30 | BTB0284BTB | CK_SAMRAONG | 2*4T4R+1*4T6S | 284 | 103.2064 | 13.1099 | Nokia | BTB01 | 4 | Battambang | 2025-04-11 | WK15(07-Apr - 13-Apr) | April | 2025-04-11
31 | BTB0580BTB | CK_SAMRAONG2 | 3*4T4R | 580 | 103.2038 | 13.1088 | Nokia | BTB01 | 4 | Battambang | 2025-04-11 | WK15(07-Apr - 13-Apr) | April | 2025-04-11
32 | BTB0889BTB | ROM_CHEK2 | 2*4T4R+1*4T6S | 889 | 103.2066 | 13.1029 | Nokia | BTB01 | 4 | Battambang | 2025-04-11 | WK15(07-Apr - 13-Apr) | April | 2025-04-11
33 | BTB1349BTB | PREAEK_MOHA_TEP | 3*2T2R | 1349 | 103.2028 | 13.1055 | Nokia | BTB01 | 4 | Battambang | 2025-04-11 | WK15(07-Apr - 13-Apr) | April | 2025-04-11
34 | BTB2598BTB | BB142 | 3*2T2R | 2598 | 103.2135 | 13.105 | Nokia | BTB01 | 4 | Battambang | 2025-04-11 | WK15(07-Apr - 13-Apr) | April | 2025-04-11
35 | BTB6757BTB | BB0187 | 3*4T4R | 6757 | 103.208 | 13.106 | Nokia | BTB01 | 4 | Battambang | 2025-04-11 | WK15(07-Apr - 13-Apr) | April | 2025-04-11
36 | BTB0454BNN | CHHEU_TEAL | 3*4T4R | 454 | 103.175 | 13.027 | Nokia | BTB05 | 5 | Battambang | 2025-04-30 | WK18(28-Apr - 04-May) | April |  | WP Under TRC Approval
37 | BTB0523BTB | OU_MAL | 3*4T4R | 523 | 103.1573 | 13.0653 | Nokia | BTB05 | 5 | Battambang | 2025-04-30 | WK18(28-Apr - 04-May) | April |  | WP Under TRC Approval
38 | BTB1495BTB | CHAENG_KDAR | 2*4T4R+1*4T6S | 1495 | 103.134 | 13.0476 | Nokia | BTB05 | 5 | Battambang | 2025-04-30 | WK18(28-Apr - 04-May) | April |  | WP Under TRC Approval
39 | BTB1895SKE | OU_KHCHEAY | 3*4T4R | 1895 | 103.2038 | 13.0428 | Nokia | BTB05 | 5 | Battambang | 2025-04-30 | WK18(28-Apr - 04-May) | April |  | WP Under TRC Approval
40 | BTB2527SKE | BB151 | 3*2T2R | 2527 | 103.202 | 13.035 | Nokia | BTB05 | 5 | Battambang | 2025-04-30 | WK18(28-Apr - 04-May) | April |  | WP Under TRC Approval
41 | BTB2544BTB | BB093 | 3*4T4R | 2544 | 103.146 | 13.0641 | Nokia | BTB05 | 5 | Battambang | 2025-04-30 | WK18(28-Apr - 04-May) | April |  | WP Under TRC Approval
42 | BTB2546BTB | BB148 | 3*2T2R | 2546 | 103.166 | 13.07 | Nokia | BTB05 | 5 | Battambang | 2025-04-30 | WK18(28-Apr - 04-May) | April |  | WP Under TRC Approval
43 | BTB2618BTB | BB167 | 3*4T4R | 2618 | 103.1579 | 13.0847 | Nokia | BTB05 | 5 | Battambang | 2025-04-30 | WK18(28-Apr - 04-May) | April |  | WP Under TRC Approval
44 | BTB0098SKE | BATTAMBANG3 | 3*4T4R | 98 | 103.2504 | 13.0659 | Nokia | BTB06 | 6 | Battambang | 2025-05-05 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
45 | BTB0119SKE | BATTAMBANG4 | 3*4T4R | 119 | 103.3582 | 12.9308 | Nokia | BTB06 | 6 | Battambang | 2025-05-05 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
46 | BTB0859SKE | BATTAMBANG12 | 3*2T2R | 859 | 103.3135 | 13.0138 | Nokia | BTB06 | 6 | Battambang | 2025-05-05 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
47 | BTB0953SKE | PSAR_THMEY2 | 3*2T2R | 953 | 103.2389 | 13.0799 | Nokia | BTB06 | 6 | Battambang | 2025-05-05 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
48 | BTB1233SKE | VOAT_TA_MUEM | 3*4T4R | 1233 | 103.215 | 13.0684 | Nokia | BTB06 | 6 | Battambang | 2025-05-05 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
49 | BTB1377SKE | CHRAB_VEAL | 3*4T4R | 1377 | 103.233 | 13.0846 | Nokia | BTB06 | 6 | Battambang | 2025-05-05 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
50 | BTB2051SKE | PREY_CHAEK | 3*4T4R | 2051 | 103.2825 | 13.0452 | Nokia | BTB06 | 6 | Battambang | 2025-05-05 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
51 | BTB2543SKE | BB092 | 3*2T2R | 2543 | 103.233 | 13.0727 | Nokia | BTB06 | 6 | Battambang | 2025-05-05 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
52 | BTB2547SKE | BB150 | 3*2T2R | 2547 | 103.198 | 13.06 | Nokia | BTB06 | 6 | Battambang | 2025-05-05 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
53 | BTB3301BTB | BB117 | 3*2T2R | 3301 | 103.2062 | 13.07 | Nokia | BTB06 | 6 | Battambang | 2025-05-05 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
54 | BTB5687SKE | BB038SE | 3*2T2R | 5687 | 103.2158 | 13.078 | Nokia | BTB06 | 6 | Battambang | 2025-05-05 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
55 | BTB0168BTB | KDOL | 3*4T4R | 168 | 103.2081 | 13.1279 | Nokia | BTB07 | 7 | Battambang | 2025-05-08 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
56 | BTB0186APM | BAK_PREA | 3*2T2R | 186 | 103.4048 | 13.3095 | Nokia | BTB07 | 7 | Battambang | 2025-05-08 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
57 | BTB0473APM | EK_PHNOM | 3*2T2R | 473 | 103.2256 | 13.1583 | Nokia | BTB07 | 7 | Battambang | 2025-05-08 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
58 | BTB0965BTB | WAT_POTEVONG | 2*4T4R+1*4T6S | 965 | 103.1894 | 13.1235 | Nokia | BTB07 | 7 | Battambang | 2025-05-08 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
59 | BTB0969SKE | BOENG_TUEM | 3*2T2R | 969 | 103.3059 | 13.1188 | Nokia | BTB07 | 7 | Battambang | 2025-05-08 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
60 | BTB1232SKE | ROKA | 3*2T2R | 1232 | 103.2901 | 13.0947 | Nokia | BTB07 | 7 | Battambang | 2025-05-08 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
61 | BTB1509APM | PREK_CHHDOR | 3*2T2R | 1509 | 103.207 | 13.1709 | Nokia | BTB07 | 7 | Battambang | 2025-05-08 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
62 | BTB1559SKE | SAMRAONG_TA_KOK | 3*2T2R | 1559 | 103.2181 | 13.12 | Nokia | BTB07 | 7 | Battambang | 2025-05-08 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
63 | BTB1560APM | PREAK_TA_CHRAENG | 3*2T2R | 1560 | 103.219 | 13.1435 | Nokia | BTB07 | 7 | Battambang | 2025-05-08 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
64 | BTB1980SKE | TA_PON | 3*2T2R | 1980 | 103.3833 | 13.1589 | Nokia | BTB07 | 7 | Battambang | 2025-05-08 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
65 | BTB2011APM | PREAEK_NORINT | 3*2T2R | 2011 | 103.2956 | 13.2136 | Nokia | BTB07 | 7 | Battambang | 2025-05-08 | WK19(05-May - 11-May) | May |  | WP Under TRC Approval
66 | BTB0094TKL | THMORKOL | 3*4T6S | 94 | 103.091 | 13.2753 | Nokia | BTB08 | 8 | Battambang | 2025-05-12 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
67 | BTB0187BVL | KHNACH_ROMEAS | 3*2T2R | 187 | 102.9525 | 13.2612 | Nokia | BTB08 | 8 | Battambang | 2025-05-12 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
68 | BTB0188TKL | OR_TAKI | 3*4T4R | 188 | 103.117 | 13.1503 | Nokia | BTB08 | 8 | Battambang | 2025-05-12 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
69 | BTB0453TKL | KO_KOUR | 3*2T2R | 453 | 103.1342 | 13.1266 | Nokia | BTB08 | 8 | Battambang | 2025-05-12 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
70 | BTB0598TKL | THMORKOL2 | 3*2T2R | 598 | 103.1097 | 13.1981 | Nokia | BTB08 | 8 | Battambang | 2025-05-12 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
71 | BTB0689BTB | BATTAMBANG11 | 2*4T4R+1*4T6S | 689 | 103.1694 | 13.1062 | Nokia | BTB08 | 8 | Battambang | 2025-05-12 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
72 | BTB0774TKL | ANDOUNG | 3*2T2R | 774 | 103.0333 | 13.2647 | Nokia | BTB08 | 8 | Battambang | 2025-05-12 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
73 | BTB1012TKL | WAT_POYSAMRONG | 3*2T2R | 1012 | 103.1016 | 13.2294 | Nokia | BTB08 | 8 | Battambang | 2025-05-12 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
74 | BTB1014TKL | TOUL_TAKOY | 3*2T2R | 1014 | 103.0056 | 13.2645 | Nokia | BTB08 | 8 | Battambang | 2025-05-12 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
75 | BTB1059TKL | PREY_DACH | 3*2T2R | 1059 | 103.1641 | 13.1657 | Nokia | BTB08 | 8 | Battambang | 2025-05-12 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
76 | BTB1376TKL | TAPUNG | 3*4T4R | 1376 | 103.0884 | 13.2664 | Nokia | BTB08 | 8 | Battambang | 2025-05-12 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
77 | BTB1974TKL | TUMPUNG_TBOUNG | 2*4T4R+1*4T6S | 1974 | 103.1401 | 13.269 | Nokia | BTB08 | 8 | Battambang | 2025-05-12 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
78 | BTB0163BNN | PHNOM_SAMPOV | 3*2T2R | 163 | 103.0983 | 13.031 | Nokia | BTB09 | 9 | Battambang | 2025-05-16 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
79 | BTB0189RMD | SDAOV | 3*2T2R | 189 | 102.9694 | 12.888 | Nokia | BTB09 | 9 | Battambang | 2025-05-16 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
80 | BTB0190BNN | SNOEUNG | 3*2T2R | 190 | 103.0457 | 12.9605 | Nokia | BTB09 | 9 | Battambang | 2025-05-16 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
81 | BTB0283BNN | TAKREAM | 3*2T2R | 283 | 103.0235 | 13.0924 | Nokia | BTB09 | 9 | Battambang | 2025-05-16 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
82 | BTB1204BNN | BOENG_PREY | 2*4T4R+1*4T6S | 1204 | 102.9838 | 12.9538 | Nokia | BTB09 | 9 | Battambang | 2025-05-16 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
83 | BTB1209BNN | ANLUNG_RUN | 2*4T4R+1*4T6S | 1209 | 103.0315 | 13.1299 | Nokia | BTB09 | 9 | Battambang | 2025-05-16 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
84 | BTB1340BNN | BOEUNG_KRASAL | 3*2T2R | 1340 | 102.9822 | 13.0104 | Nokia | BTB09 | 9 | Battambang | 2025-05-16 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
85 | BTB1344RMD | ANDAEUK_HAEB | 3*2T2R | 1344 | 102.9777 | 12.8688 | Nokia | BTB09 | 9 | Battambang | 2025-05-16 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
86 | BTB1436RMD | REAKSMEY_SANGHA | 3*2T2R | 1436 | 102.9117 | 12.9388 | Nokia | BTB09 | 9 | Battambang | 2025-05-16 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
87 | BTB1649BNN | KDAONG | 3*2T2R | 1649 | 103.1014 | 13.0125 | Nokia | BTB09 | 9 | Battambang | 2025-05-16 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
88 | BTB1976BNN | PHNUM_SAMPOV | 3*2T2R | 1976 | 103.0536 | 13.0468 | Nokia | BTB09 | 9 | Battambang | 2025-05-16 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
89 | BTB2193RMD | BOENG_AMPIL | 3*4T4R | 2193 | 102.9988 | 12.918 | Nokia | BTB09 | 9 | Battambang | 2025-05-16 | WK20(12-May - 18-May) | May |  | WP Under TRC Approval
90 | BTB0282BNN | KANTEU_PIR | 3*2T2R | 282 | 103.1443 | 12.9461 | Nokia | BTB10 | 10 | Battambang | 2025-05-19 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
91 | BTB0793SKE | BAMNAK | 3*2T2R | 793 | 103.2582 | 12.9676 | Nokia | BTB10 | 10 | Battambang | 2025-05-19 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
92 | BTB0807BNN | KBAL_THNAL2 | 3*2T2R | 807 | 103.0975 | 12.8744 | Nokia | BTB10 | 10 | Battambang | 2025-05-19 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
93 | BTB0966SKE | REANG_KESAL | 3*2T2R | 966 | 103.2425 | 13.0148 | Nokia | BTB10 | 10 | Battambang | 2025-05-19 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
94 | BTB1011KKL | THIPADOL | 3*2T2R | 1011 | 103.2707 | 12.8657 | Nokia | BTB10 | 10 | Battambang | 2025-05-19 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
95 | BTB1240BNN | PAI_LAM | 3*2T2R | 1240 | 103.0603 | 12.8108 | Nokia | BTB10 | 10 | Battambang | 2025-05-19 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
96 | BTB1258BNN | THMEY | 3*2T2R | 1258 | 103.1485 | 12.8743 | Nokia | BTB10 | 10 | Battambang | 2025-05-19 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
97 | BTB1896SKE | VOAT_KANDAL | 3*2T2R | 1896 | 103.2901 | 12.926 | Nokia | BTB10 | 10 | Battambang | 2025-05-19 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
98 | BTB2187BNN | BAY_DAMRAM | 3*4T4R | 2187 | 103.1647 | 12.9907 | Nokia | BTB10 | 10 | Battambang | 2025-05-19 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
99 | BTB0118MRS | MOUNG_RUSSEY | 3*4T4R | 118 | 103.4471 | 12.7797 | Nokia | BTB11 | 11 | Battambang | 2025-05-22 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
100 | BTB0287KKL | KUAS_KROLOR | 3*2T2R | 287 | 103.2619 | 12.7611 | Nokia | BTB11 | 11 | Battambang | 2025-05-22 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
101 | BTB0862MRS | OU_SAOUN | 3*2T2R | 862 | 103.397 | 12.8448 | Nokia | BTB11 | 11 | Battambang | 2025-05-22 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
102 | BTB0863MRS | KAKAOH | 3*2T2R | 863 | 103.4665 | 12.8247 | Nokia | BTB11 | 11 | Battambang | 2025-05-22 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
103 | BTB0985MRS | DOUN_TRI | 3*2T2R | 985 | 103.5343 | 12.8532 | Nokia | BTB11 | 11 | Battambang | 2025-05-22 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
104 | BTB1372MRS | KON_KHAEK | 3*4T4R | 1372 | 103.4448 | 12.7455 | Nokia | BTB11 | 11 | Battambang | 2025-05-22 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
105 | BTB1454MRS | RUESSEI_MUOY | 3*2T2R | 1454 | 103.4422 | 12.7707 | Nokia | BTB11 | 11 | Battambang | 2025-05-22 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
106 | BTB1478KKL | CHHNALMOAN | 3*2T2R | 1478 | 103.2138 | 12.7175 | Nokia | BTB11 | 11 | Battambang | 2025-05-22 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
107 | BTB1534MRS | CHREY_PIR | 3*2T2R | 1534 | 103.4775 | 12.7788 | Nokia | BTB11 | 11 | Battambang | 2025-05-22 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
108 | BTB1979MRS | KAOH_CHAR | 3*2T2R | 1979 | 103.3672 | 12.8001 | Nokia | BTB11 | 11 | Battambang | 2025-05-22 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
109 | BTB1982KKL | KHTUM_PRARHAONG | 3*2T2R | 1982 | 103.3276 | 12.7415 | Nokia | BTB11 | 11 | Battambang | 2025-05-22 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
110 | BTB1986MRS | OU_KRABAU | 3*2T2R | 1986 | 103.3849 | 12.7473 | Nokia | BTB11 | 11 | Battambang | 2025-05-22 | WK21(19-May - 25-May) | May |  | WP Under TRC Approval
111 | BTB0457MRS | PREY_SVAY | 3*2T2R | 457 | 103.5038 | 12.7248 | Nokia | BTB12 | 12 | Battambang | 2025-05-26 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
112 | BTB0458RKR | PREY_TROLACH | 3*2T2R | 458 | 103.5332 | 12.5396 | Nokia | BTB12 | 12 | Battambang | 2025-05-26 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
113 | BTB0778RKR | KOUK_KANDAL | 3*2T2R | 778 | 103.3906 | 12.64 | Nokia | BTB12 | 12 | Battambang | 2025-05-26 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
114 | BTB1135MRS | CHREY_RUN | 3*2T2R | 1135 | 103.5718 | 12.68 | Nokia | BTB12 | 12 | Battambang | 2025-05-26 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
115 | BTB1180MRS | ANLONG_TAMOK | 3*2T2R | 1180 | 103.3844 | 12.6936 | Nokia | BTB12 | 12 | Battambang | 2025-05-26 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
116 | BTB1420RKR | TOUL_TAKI | 3*2T2R | 1420 | 103.4979 | 12.602 | Nokia | BTB12 | 12 | Battambang | 2025-05-26 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
117 | BTB1506MRS | KEAR_TA_NAK | 3*2T2R | 1506 | 103.4618 | 12.707 | Nokia | BTB12 | 12 | Battambang | 2025-05-26 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
118 | BTB1897MRS | NIKOM_KRAOM | 3*2T2R | 1897 | 103.5837 | 12.7266 | Nokia | BTB12 | 12 | Battambang | 2025-05-26 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
119 | BTB1984RKR | PAEN | 3*2T2R | 1984 | 103.4399 | 12.5706 | Nokia | BTB12 | 12 | Battambang | 2025-05-26 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
120 | BTB1985RKR | ROUNG | 3*4T4R | 1985 | 103.3458 | 12.5745 | Nokia | BTB12 | 12 | Battambang | 2025-05-26 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
121 | BTB2196KKL | KRAPEU_PI_KRAOM | 3*2T2R | 2196 | 103.1071 | 12.5317 | Nokia | BTB12 | 12 | Battambang | 2025-05-26 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
122 | BTB0320RMD | PCHEAV | 3*2T2R | 320 | 102.899 | 12.8278 | Nokia | BTB13 | 13 | Battambang | 2025-05-29 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
123 | BTB0855RMD | SRE_NOY2 | 3*4T4R | 855 | 102.8787 | 12.7143 | Nokia | BTB13 | 13 | Battambang | 2025-05-29 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
124 | BTB0865RMD | PCHEAV2 | 3*2T2R | 865 | 102.7764 | 12.8455 | Nokia | BTB13 | 13 | Battambang | 2025-05-29 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
125 | BTB1441RMD | OU_LMOUN | 3*4T4R | 1441 | 102.8383 | 12.7632 | Nokia | BTB13 | 13 | Battambang | 2025-05-29 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
126 | BTB1444SLT | BOENG_RUN | 3*2T2R | 1444 | 102.7728 | 12.6446 | Nokia | BTB13 | 13 | Battambang | 2025-05-29 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
127 | BTB1625RMD | SEK_SAK | 3*2T2R | 1625 | 102.8871 | 12.7872 | Nokia | BTB13 | 13 | Battambang | 2025-05-29 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
128 | BTB2023SLT | TA_NON | 3*2T2R | 2023 | 102.8132 | 12.7192 | Nokia | BTB13 | 13 | Battambang | 2025-05-29 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
129 | BTB2027SLT | SAMLOUT | 3*2T2R | 2027 | 102.7401 | 12.67 | Nokia | BTB13 | 13 | Battambang | 2025-05-29 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
130 | BTB2083SLT | KAMPONG_TUK | 3*2T2R | 2083 | 102.7467 | 12.7067 | Nokia | BTB13 | 13 | Battambang | 2025-05-29 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
131 | BTB2125SLT | KAMCHAT | 3*4T4R | 2125 | 102.817 | 12.6837 | Nokia | BTB13 | 13 | Battambang | 2025-05-29 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
132 | BTB2235RMD | SVAY_SAR | 3*2T2R | 2235 | 102.8226 | 12.849 | Nokia | BTB13 | 13 | Battambang | 2025-05-29 | WK22(26-May - 01-Jun) | May |  | WP Under TRC Approval
133 | BTB0137SLT | SAMLOT | 3*2T2R | 137 | 102.7518 | 12.5746 | Nokia | BTB14 | 14 | Battambang | 2025-06-02 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
134 | BTB0479SLT | SAMLOT_TOWN | 3*2T2R | 479 | 102.8532 | 12.6214 | Nokia | BTB14 | 14 | Battambang | 2025-06-02 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
135 | BTB1212SLT | VEAL_ROLOEM | 3*2T2R | 1212 | 102.829 | 12.4682 | Nokia | BTB14 | 14 | Battambang | 2025-06-02 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
136 | BTB1213SLT | TASANH | 3*2T2R | 1213 | 102.8522 | 12.596 | Nokia | BTB14 | 14 | Battambang | 2025-06-02 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
137 | BTB1259SLT | OU_TATEAK | 3*2T2R | 1259 | 102.8273 | 12.513 | Nokia | BTB14 | 14 | Battambang | 2025-06-02 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
138 | BTB1413SLT | PHUMOUKROUCH | 3*2T2R | 1413 | 102.8454 | 12.5145 | Nokia | BTB14 | 14 | Battambang | 2025-06-02 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
139 | BTB1645SLT | PHNUM_RAI | 3*2T2R | 1645 | 102.7982 | 12.5118 | Nokia | BTB14 | 14 | Battambang | 2025-06-02 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
140 | BTB1662SLT | KANHCHANG | 3*2T2R | 1662 | 102.8089 | 12.5769 | Nokia | BTB14 | 14 | Battambang | 2025-06-02 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
141 | BTB2028SLT | PREY_RUMCHEK | 3*2T2R | 2028 | 102.885 | 12.669 | Nokia | BTB14 | 14 | Battambang | 2025-06-02 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
142 | BTB2029RMD | CHAMLANG_ROMEANG_LEU | 3*2T2R | 2029 | 102.9547 | 12.7102 | Nokia | BTB14 | 14 | Battambang | 2025-06-02 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
143 | BTB2238SLT | OU_CHOAM_KRAOM | 3*2T2R | 2238 | 102.9185 | 12.5649 | Nokia | BTB14 | 14 | Battambang | 2025-06-02 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
144 | PLN0071PLN | PAYLIN | 3*2T2R | 71 | 102.6241 | 12.8439 | Nokia | PL01 | 15 | Pailin | 2025-06-05 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
145 | PLN0114SLK | PSAR_PRUM | 3*4T4R | 114 | 102.5016 | 12.931 | Nokia | PL01 | 15 | Pailin | 2025-06-05 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
146 | PLN0529SLK | PAILIN2 | 3*2T2R | 529 | 102.5968 | 12.9438 | Nokia | PL01 | 15 | Pailin | 2025-06-05 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
147 | PLN0540PLN | PAILIN3 | 3*2T2R | 540 | 102.6054 | 12.8597 | Nokia | PL01 | 15 | Pailin | 2025-06-05 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
148 | PLN0613PLN | OU_ANDONG | 3*2T2R | 613 | 102.5857 | 12.8868 | Nokia | PL01 | 15 | Pailin | 2025-06-05 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
149 | PLN1181SLK | SRE_ANTEAK | 3*2T2R | 1181 | 102.6383 | 13.0753 | Nokia | PL01 | 15 | Pailin | 2025-06-05 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
150 | PLN1207PLN | KRACHAB | 3*2T2R | 1207 | 102.7493 | 12.7502 | Nokia | PL01 | 15 | Pailin | 2025-06-05 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
151 | PLN1415PLN | PANG_ROLOEUM | 3*2T2R | 1415 | 102.7153 | 12.8113 | Nokia | PL01 | 15 | Pailin | 2025-06-05 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
152 | PLN1442PLN | BOR_TAINGSOU | 3*2T2R | 1442 | 102.5627 | 12.8745 | Nokia | PL01 | 15 | Pailin | 2025-06-05 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
153 | PLN1601SLK | STEUNG_KACH | 3*4T4R | 1601 | 102.5426 | 12.9399 | Nokia | PL01 | 15 | Pailin | 2025-06-05 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
154 | PLN2022SLK | PHNUM_KOY | 3*2T2R | 2022 | 102.596 | 12.9976 | Nokia | PL01 | 15 | Pailin | 2025-06-05 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
155 | PLN2066SLK | PHTEAH_SBOV | 3*2T2R | 2066 | 102.6692 | 13.0258 | Nokia | PL01 | 15 | Pailin | 2025-06-05 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
156 | PLN2124SLK | KOUN_DAMREI | 3*2T2R | 2124 | 102.7428 | 13.0053 | Nokia | PL01 | 15 | Pailin | 2025-06-05 | WK23(02-Jun - 08-Jun) | June |  | WP Under TRC Approval
157 | BTB0136KRG | KAM_RIENG | 3*4T4R | 136 | 102.4589 | 13.084 | Nokia | BTB16 | 16 | Battambang | 2025-06-09 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
158 | BTB0723KRG | TA_HAO | 3*2T2R | 723 | 102.4278 | 13.1183 | Nokia | BTB16 | 16 | Battambang | 2025-06-09 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
159 | BTB0973KRG | KAMRIENG_TOWN | 3*4T4R | 973 | 102.4494 | 13.0876 | Nokia | BTB16 | 16 | Battambang | 2025-06-09 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
160 | BTB1393KRG | SRALAO_TONG | 3*2T2R | 1393 | 102.5506 | 13.0276 | Nokia | BTB16 | 16 | Battambang | 2025-06-09 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
161 | BTB1474KRG | SVAY_VENG | 3*2T2R | 1474 | 102.4985 | 13.0461 | Nokia | BTB16 | 16 | Battambang | 2025-06-09 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
162 | BTB1475KRG | BOENG_OUCHEANG | 3*2T2R | 1475 | 102.5376 | 12.9969 | Nokia | BTB16 | 16 | Battambang | 2025-06-09 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
163 | BTB1959KRG | PHNUM_MUOY_ROY | 3*2T2R | 1959 | 102.5037 | 13.1524 | Nokia | BTB16 | 16 | Battambang | 2025-06-09 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
164 | BTB1972KRG | VEAL_LUMPHAT | 3*2T2R | 1972 | 102.5279 | 13.108 | Nokia | BTB16 | 16 | Battambang | 2025-06-09 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
165 | BTB1973KRG | TANG_YU | 3*2T2R | 1973 | 102.5685 | 13.1284 | Nokia | BTB16 | 16 | Battambang | 2025-06-09 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
166 | BTB1977KRG | PHUM_SAMSEB | 3*2T2R | 1977 | 102.6118 | 13.1531 | Nokia | BTB16 | 16 | Battambang | 2025-06-09 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
167 | BTB2585KRG | BB055 | 3*4T4R | 2585 | 102.4408 | 13.096 | Nokia | BTB16 | 16 | Battambang | 2025-06-09 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
168 | BMC0135MLI | MALAY | 3*4T6S | 135 | 102.3694 | 13.5656 | Nokia | BTB18 | 17 | Banteay Meanchey | 2025-06-12 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
169 | BMC0861MLI | ANG_BAN | 3*2T2R | 861 | 102.3655 | 13.4959 | Nokia | BTB18 | 17 | Banteay Meanchey | 2025-06-12 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
170 | BMC0975MLI | MALAY_TOWN | 3*4T4R | 975 | 102.365 | 13.5667 | Nokia | BTB18 | 17 | Banteay Meanchey | 2025-06-12 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
171 | BMC1414MLI | BOENG_BENG | 3*2T2R | 1414 | 102.3524 | 13.533 | Nokia | BTB18 | 17 | Banteay Meanchey | 2025-06-12 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
172 | BTB0139PPK | PHNOM_PREUK | 3*2T2R | 139 | 102.392 | 13.2201 | Nokia | BTB18 | 17 | Battambang | 2025-06-12 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
173 | BTB0164SPL | SAMPOVLOUN | 3*2T2R | 164 | 102.3768 | 13.426 | Nokia | BTB18 | 17 | Battambang | 2025-06-12 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
174 | BTB0489SPL | SAMPOVLOUN2 | 3*2T2R | 489 | 102.3782 | 13.4343 | Nokia | BTB18 | 17 | Battambang | 2025-06-12 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
175 | BTB0829PPK | SRE_MAM | 3*2T2R | 829 | 102.3542 | 13.3319 | Nokia | BTB18 | 17 | Battambang | 2025-06-12 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
176 | BTB1443PPK | PHUM_THNAL_BAT | 3*2T2R | 1443 | 102.3752 | 13.2727 | Nokia | BTB18 | 17 | Battambang | 2025-06-12 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
177 | BTB1483SPL | SRALAU_CHRUM | 3*2T2R | 1483 | 102.3617 | 13.4332 | Nokia | BTB18 | 17 | Battambang | 2025-06-12 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
178 | BTB1894PPK | BENG_SAT | 3*2T2R | 1894 | 102.3673 | 13.3014 | Nokia | BTB18 | 17 | Battambang | 2025-06-12 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
179 | BTB1905PPK | CHAKREI | 3*2T2R | 1905 | 102.3593 | 13.3795 | Nokia | BTB18 | 17 | Battambang | 2025-06-12 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
180 | BTB1981SPL | VEAL_VONG | 3*2T2R | 1981 | 102.4381 | 13.4116 | Nokia | BTB18 | 17 | Battambang | 2025-06-12 | WK24(09-Jun - 15-Jun) | June |  | WP Under TRC Approval
181 | BTB0140BVL | BAVEL | 3*2T2R | 140 | 102.8653 | 13.2506 | Nokia | BTB17 | 18 | Battambang | 2025-06-16 | WK25(16-Jun - 22-Jun) | June |  | WP Under TRC Approval
182 | BTB0555PPK | BOUR | 3*2T2R | 555 | 102.6168 | 13.2865 | Nokia | BTB17 | 18 | Battambang | 2025-06-16 | WK25(16-Jun - 22-Jun) | June |  | WP Under TRC Approval
183 | BTB1252BVL | KHDOL_TAHEN2 | 3*2T2R | 1252 | 102.8462 | 13.2044 | Nokia | BTB17 | 18 | Battambang | 2025-06-16 | WK25(16-Jun - 22-Jun) | June |  | WP Under TRC Approval
184 | BTB1480SPL | TRAV_CHOU | 3*2T2R | 1480 | 102.5459 | 13.4017 | Nokia | BTB17 | 18 | Battambang | 2025-06-16 | WK25(16-Jun - 22-Jun) | June |  | WP Under TRC Approval
185 | BTB1481SPL | TRAPAING_PRALIT | 3*2T2R | 1481 | 102.5146 | 13.3799 | Nokia | BTB17 | 18 | Battambang | 2025-06-16 | WK25(16-Jun - 22-Jun) | June |  | WP Under TRC Approval
186 | BTB1508BVL | AMPIL_PRAM_DAEUM | 3*2T2R | 1508 | 102.7694 | 13.2593 | Nokia | BTB17 | 18 | Battambang | 2025-06-16 | WK25(16-Jun - 22-Jun) | June |  | WP Under TRC Approval
187 | BTB1607PPK | DAMNAK_KSAN | 3*2T2R | 1607 | 102.5625 | 13.342 | Nokia | BTB17 | 18 | Battambang | 2025-06-16 | WK25(16-Jun - 22-Jun) | June |  | WP Under TRC Approval
188 | BTB1978BVL | TA_KHIEV | 3*4T4R | 1978 | 102.6977 | 13.2726 | Nokia | BTB17 | 18 | Battambang | 2025-06-16 | WK25(16-Jun - 22-Jun) | June |  | WP Under TRC Approval
189 | BTB5958BVL | BB050 | 3*2T2R | 5958 | 102.8759 | 13.2567 | Nokia | BTB17 | 18 | Battambang | 2025-06-16 | WK25(16-Jun - 22-Jun) | June |  | WP Under TRC Approval
190 | BTB0729KRG | DONTRY | 3*2T2R | 729 | 102.6538 | 13.1267 | Nokia | BTB15 | 19 | Battambang | 2025-06-19 | WK25(16-Jun - 22-Jun) | June |  | WP Under TRC Approval
191 | BTB0789BVL | TOUK_KHAONG | 3*2T2R | 789 | 102.8263 | 13.1511 | Nokia | BTB15 | 19 | Battambang | 2025-06-19 | WK25(16-Jun - 22-Jun) | June |  | WP Under TRC Approval
192 | BTB0860BNN | THIPADEL | 3*2T2R | 860 | 102.9386 | 13.0973 | Nokia | BTB15 | 19 | Battambang | 2025-06-19 | WK25(16-Jun - 22-Jun) | June |  | WP Under TRC Approval
193 | BTB1006BNN | SDAOV1 | 3*2T2R | 1006 | 102.8577 | 12.9808 | Nokia | BTB15 | 19 | Battambang | 2025-06-19 | WK25(16-Jun - 22-Jun) | June |  | WP Under TRC Approval
194 | BTB1338RMD | KHDOL_TAHEN | 3*2T2R | 1338 | 102.8 | 13.0362 | Nokia | BTB15 | 19 | Battambang | 2025-06-19 | WK25(16-Jun - 22-Jun) | June |  | WP Under TRC Approval
195 | BTB1339BVL | TUMNOB_TRAKUON | 3*2T2R | 1339 | 102.8667 | 13.0823 | Nokia | BTB15 | 19 | Battambang | 2025-06-19 | WK25(16-Jun - 22-Jun) | June |  | WP Under TRC Approval
196 | BTB1438RMD | KHUM_STUNG_TRANG | 3*2T2R | 1438 | 102.7274 | 13.0703 | Nokia | BTB15 | 19 | Battambang | 2025-06-19 | WK25(16-Jun - 22-Jun) | June |  | WP Under TRC Approval
197 | BTB1975BVL | BUOR_SANGKREACH | 3*4T4R | 1975 | 102.7702 | 13.1107 | Nokia | BTB15 | 19 | Battambang | 2025-06-19 | WK25(16-Jun - 22-Jun) | June |  | WP Under TRC Approval
198 | BTB1983KRG | TUOL_TILL | 3*2T2R | 1983 | 102.6885 | 13.1146 | Nokia | BTB15 | 19 | Battambang | 2025-06-19 | WK25(16-Jun - 22-Jun) | June |  | WP Under TRC Approval
199 | PNH0105MCY | CHAK_ANGRE | 3*2T2R | 105 | 104.939 | 11.5062 | Nokia | PP01 | 20 | Phnom Penh | 2025-06-23 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
200 | PNH0578MCY | TAKHMAO2 | 3*4T4R | 578 | 104.9426 | 11.4956 | Nokia | PP01 | 20 | Phnom Penh | 2025-06-23 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
201 | PNH0619CAP | CHAK_ANGRE4 | 3*2T2R | 619 | 104.9426 | 11.512 | Nokia | PP01 | 20 | Phnom Penh | 2025-06-23 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
202 | PNH0900MCY | CHAK_ANGRE6 | 2*4T4R+1*4T6S | 900 | 104.9371 | 11.5022 | Nokia | PP01 | 20 | Phnom Penh | 2025-06-23 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
203 | PNH0907MCY | CHAK_ANGRE7 | 3*2T2R | 907 | 104.9343 | 11.5086 | Nokia | PP01 | 20 | Phnom Penh | 2025-06-23 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
204 | PNH1388MCY | TUOL_ROKA | 3*4T4R | 1388 | 104.9359 | 11.5115 | Nokia | PP01 | 20 | Phnom Penh | 2025-06-23 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
205 | PNH2413MCY | PP329 | 3*2T2R | 2413 | 104.941 | 11.5 | Nokia | PP01 | 20 | Phnom Penh | 2025-06-23 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
206 | PNH2415CAP | PP334 | 3*2T2R | 2415 | 104.95 | 11.511 | Nokia | PP01 | 20 | Phnom Penh | 2025-06-23 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
207 | PNH2627CAP | PPF033 | 3*2T2R | 2627 | 104.9548 | 11.5122 | Nokia | PP01 | 20 | Phnom Penh | 2025-06-23 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
208 | PNH5671CAP | PP274 | 3*2T2R | 5671 | 104.9455 | 11.5095 | Nokia | PP01 | 20 | Phnom Penh | 2025-06-23 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
209 | PNH6622CAP | PP0080 | 3*4T4R | 6622 | 104.9486 | 11.5029 | Nokia | PP01 | 20 | Phnom Penh | 2025-06-23 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
210 | KDL0011TKM | TAKHMAO | 2*4T4R+1*4T6S | 11 | 104.946 | 11.4856 | Nokia | KD01 | 21 | Kandal | 2025-06-26 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
211 | KDL0362TKM | YUNG_WAH | 3*2T2R | 362 | 104.9495 | 11.4719 | Nokia | KD01 | 21 | Kandal | 2025-06-26 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
212 | KDL0363TKM | PREAK_RUSSEI | 3*4T4R | 363 | 104.941 | 11.4759 | Nokia | KD01 | 21 | Kandal | 2025-06-26 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
213 | KDL0640TKM | TAKHMAO5 | 3*2T2R | 640 | 104.9409 | 11.4902 | Nokia | KD01 | 21 | Kandal | 2025-06-26 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
214 | KDL0683TKM | PREAK_RUSSEI2 | 3*4T4R | 683 | 104.9351 | 11.4669 | Nokia | KD01 | 21 | Kandal | 2025-06-26 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
215 | KDL0710TKM | TAKHMAO4 | 3*2T2R | 710 | 104.9499 | 11.4786 | Nokia | KD01 | 21 | Kandal | 2025-06-26 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
216 | KDL0782TKM | TAKHMAO3 | 3*4T4R | 782 | 104.941 | 11.4812 | Nokia | KD01 | 21 | Kandal | 2025-06-26 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
217 | KDL0941TKM | KHPOB_VEAENG | 3*4T4R | 941 | 104.9539 | 11.4637 | Nokia | KD01 | 21 | Kandal | 2025-06-26 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
218 | KDL2081TKM | KRAPEU_HA | 3*2T2R | 2081 | 104.9461 | 11.481 | Nokia | KD01 | 21 | Kandal | 2025-06-26 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
219 | KDL2382TKM | KD008 | 3*2T2R | 2382 | 104.95 | 11.4739 | Nokia | KD01 | 21 | Kandal | 2025-06-26 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
220 | KDL2387TKM | KD073 | 3*2T2R | 2387 | 104.942 | 11.46 | Nokia | KD01 | 21 | Kandal | 2025-06-26 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
221 | KDL2388TKM | KD075 | 3*2T2R | 2388 | 104.944 | 11.468 | Nokia | KD01 | 21 | Kandal | 2025-06-26 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
222 | KDL2392TKM | KD131 | 3*4T4R | 2392 | 104.944 | 11.4828 | Nokia | KD01 | 21 | Kandal | 2025-06-26 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
223 | KDL2394TKM | KD136 | 3*2T2R | 2394 | 104.944 | 11.4883 | Nokia | KD01 | 21 | Kandal | 2025-06-26 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
224 | KDL2446TKM | KD117 | 3*2T2R | 2446 | 104.952 | 11.4715 | Nokia | KD01 | 21 | Kandal | 2025-06-26 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
225 | KDL3125TKM | TAKMAOV2 | 3*2T2R | 3125 | 104.9554 | 11.4685 | Nokia | KD01 | 21 | Kandal | 2025-06-26 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
226 | KDL6331TKM | KD006 | 3*4T4R | 6331 | 104.9395 | 11.4845 | Nokia | KD01 | 21 | Kandal | 2025-06-26 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
227 | KDL6384TKM | PP218SE | 3*2T2R | 6384 | 104.9423 | 11.4654 | Nokia | KD01 | 21 | Kandal | 2025-06-26 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
228 | KDL6405TKM | KDB005 | 3*2T2R | 6405 | 104.9478 | 11.4649 | Nokia | KD01 | 21 | Kandal | 2025-06-26 | WK26(23-Jun - 29-Jun) | June |  | WP Under TRC Approval
229 | PNH0412CAP | CHAMPOU_KAAEK | 3*2T2R | 412 | 104.988 | 11.5013 | Nokia | PP02 | 22 | Phnom Penh | 2025-06-30 | WK27(30-Jun - 06-Jul) | June |  | WP Under TRC Approval
230 | PNH0915CAP | OU_ANDOUNG | 3*2T2R | 915 | 104.9532 | 11.4852 | Nokia | PP02 | 22 | Phnom Penh | 2025-06-30 | WK27(30-Jun - 06-Jul) | June |  | WP Under TRC Approval
231 | PNH2438CAP | PP698 | 3*2T2R | 2438 | 104.967 | 11.484 | Nokia | PP02 | 22 | Phnom Penh | 2025-06-30 | WK27(30-Jun - 06-Jul) | June |  | WP Under TRC Approval
232 | PNH2476CAP | PP561 | 3*2T2R | 2476 | 104.989 | 11.466 | Nokia | PP02 | 22 | Phnom Penh | 2025-06-30 | WK27(30-Jun - 06-Jul) | June |  | WP Under TRC Approval
233 | PNH2487CAP | PP692 | 3*2T2R | 2487 | 104.96 | 11.474 | Nokia | PP02 | 22 | Phnom Penh | 2025-06-30 | WK27(30-Jun - 06-Jul) | June |  | WP Under TRC Approval
234 | PNH5481CAP | VATTANAC_GOLF_01 | 3*2T2R | 5481 | 105.0248 | 11.4788 | Nokia | PP02 | 22 | Phnom Penh | 2025-06-30 | WK27(30-Jun - 06-Jul) | June |  | WP Under TRC Approval
235 | PNH5482CAP | VATTANAC_GOLF_02 | 3*2T2R | 5482 | 105.0315 | 11.4884 | Nokia | PP02 | 22 | Phnom Penh | 2025-06-30 | WK27(30-Jun - 06-Jul) | June |  | WP Under TRC Approval
236 | PNH5751CAP | PP612 | 3*2T2R | 5751 | 104.9936 | 11.5026 | Nokia | PP02 | 22 | Phnom Penh | 2025-06-30 | WK27(30-Jun - 06-Jul) | June |  | WP Under TRC Approval
237 | PNH6194CAP | KAN437 | 3*2T2R | 6194 | 104.9653 | 11.4684 | Nokia | PP02 | 22 | Phnom Penh | 2025-06-30 | WK27(30-Jun - 06-Jul) | June |  | WP Under TRC Approval
238 | PNH6549CAP | GPP107 | 3*2T2R | 6549 | 104.9808 | 11.4933 | Nokia | PP02 | 22 | Phnom Penh | 2025-06-30 | WK27(30-Jun - 06-Jul) | June |  | WP Under TRC Approval
239 | PNH1778CAP | PREK_ENG_PAGODA | 3*2T2R | 1778 | 104.9904 | 11.532 | Nokia | PP03 | 23 | Phnom Penh | 2025-07-03 | WK27(30-Jun - 06-Jul) | July |  | WP Under TRC Approval
240 | PNH1941CAP | KEIN_SVAY | 3*4T4R | 1941 | 105.0244 | 11.5213 | Nokia | PP03 | 23 | Phnom Penh | 2025-07-03 | WK27(30-Jun - 06-Jul) | July |  | WP Under TRC Approval
241 | PNH2418CAP | PP355 | 3*2T2R | 2418 | 104.99 | 11.511 | Nokia | PP03 | 23 | Phnom Penh | 2025-07-03 | WK27(30-Jun - 06-Jul) | July |  | WP Under TRC Approval
242 | PNH2467CAP | PP353 | 3*2T2R | 2467 | 104.983 | 11.533 | Nokia | PP03 | 23 | Phnom Penh | 2025-07-03 | WK27(30-Jun - 06-Jul) | July |  | WP Under TRC Approval
243 | PNH2468CAP | PP354 | 3*2T2R | 2468 | 105.017 | 11.525 | Nokia | PP03 | 23 | Phnom Penh | 2025-07-03 | WK27(30-Jun - 06-Jul) | July |  | WP Under TRC Approval
244 | PNH2514CAP | PP717 | 3*2T2R | 2514 | 104.992 | 11.5203 | Nokia | PP03 | 23 | Phnom Penh | 2025-07-03 | WK27(30-Jun - 06-Jul) | July |  | WP Under TRC Approval
245 | PNH3122CAP | PSAR_PREK_ENG | 3*2T2R | 3122 | 104.9755 | 11.5358 | Nokia | PP03 | 23 | Phnom Penh | 2025-07-03 | WK27(30-Jun - 06-Jul) | July |  | WP Under TRC Approval
246 | PNH3296CAP | ROAD1 | 3*4T4R | 3296 | 105.006 | 11.5327 | Nokia | PP03 | 23 | Phnom Penh | 2025-07-03 | WK27(30-Jun - 06-Jul) | July |  | WP Under TRC Approval
247 | PNH4420CAP | SVAY_TA_OK | 3*2T2R | 4420 | 104.9752 | 11.5296 | Nokia | PP03 | 23 | Phnom Penh | 2025-07-03 | WK27(30-Jun - 06-Jul) | July |  | WP Under TRC Approval
248 | PNH6106CAP | PP394 | 3*2T2R | 6106 | 104.983 | 11.5143 | Nokia | PP03 | 23 | Phnom Penh | 2025-07-03 | WK27(30-Jun - 06-Jul) | July |  | WP Under TRC Approval
249 | PNH6547CAP | GPP101 | 3*2T2R | 6547 | 104.983 | 11.5248 | Nokia | PP03 | 23 | Phnom Penh | 2025-07-03 | WK27(30-Jun - 06-Jul) | July |  | WP Under TRC Approval
250 | PNH6548CAP | GPP114 | 3*2T2R | 6548 | 105.0192 | 11.5093 | Nokia | PP03 | 23 | Phnom Penh | 2025-07-03 | WK27(30-Jun - 06-Jul) | July |  | WP Under TRC Approval
251 | PNH6614CAP | PPB093 | 3*2T2R | 6614 | 104.9936 | 11.5349 | Nokia | PP03 | 23 | Phnom Penh | 2025-07-03 | WK27(30-Jun - 06-Jul) | July |  | WP Under TRC Approval
252 | KDL0084KSY | KOKI | 3*4T4R | 84 | 105.096 | 11.4915 | Nokia | KD03 | 24 | Kandal | 2025-07-07 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
253 | KDL0225KSY | BANTEAY_DEK | 3*2T2R | 225 | 105.2017 | 11.4245 | Nokia | KD03 | 24 | Kandal | 2025-07-07 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
254 | KDL0226KSY | PSA_KOKI | 3*4T4R | 226 | 105.0464 | 11.5094 | Nokia | KD03 | 24 | Kandal | 2025-07-07 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
255 | KDL1163KSY | KANDAOL_LEU | 3*4T4R | 1163 | 105.1465 | 11.4645 | Nokia | KD03 | 24 | Kandal | 2025-07-07 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
256 | KDL2008KSY | SRAE_AMPIL | 3*2T2R | 2008 | 105.0966 | 11.4644 | Nokia | KD03 | 24 | Kandal | 2025-07-07 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
257 | KDL2034KSY | SAMRAONG_KAER | 3*4T4R | 2034 | 105.244 | 11.371 | Nokia | KD03 | 24 | Kandal | 2025-07-07 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
258 | KDL2383KSY | KD015 | 3*2T2R | 2383 | 105.186 | 11.4416 | Nokia | KD03 | 24 | Kandal | 2025-07-07 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
259 | KDL2397KSY | KD155 | 3*4T4R | 2397 | 105.076 | 11.5 | Nokia | KD03 | 24 | Kandal | 2025-07-07 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
260 | KDL2529KSY | KD110 | 3*4T4R | 2529 | 105.051 | 11.5102 | Nokia | KD03 | 24 | Kandal | 2025-07-07 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
261 | KDL2587KSY | KD016 | 3*2T2R | 2587 | 105.237 | 11.3945 | Nokia | KD03 | 24 | Kandal | 2025-07-07 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
262 | KDL5519KSY | PRINCE_MANOR_RESORT | 3*2T2R | 5519 | 105.0905 | 11.507 | Nokia | KD03 | 24 | Kandal | 2025-07-07 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
263 | KDL5761KSY | KD038 | 3*2T2R | 5761 | 105.0426 | 11.5148 | Nokia | KD03 | 24 | Kandal | 2025-07-07 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
264 | KDL5973KSY | KD096 | 3*2T2R | 5973 | 105.1369 | 11.4753 | Nokia | KD03 | 24 | Kandal | 2025-07-07 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
265 | KDL5976KSY | KD144 | 3*2T2R | 5976 | 105.1144 | 11.488 | Nokia | KD03 | 24 | Kandal | 2025-07-07 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
266 | KDL6111KSY | KD039 | 3*2T2R | 6111 | 105.2416 | 11.3312 | Nokia | KD03 | 24 | Kandal | 2025-07-07 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
267 | KDL6113KSY | #N/A | 3*4T4R | 6113 | 105.026 | 11.5071 | Nokia | KD03 | 24 | Kandal | 2025-07-07 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
268 | KDL6640KSY | TCE_KD002 | 2*4T4R+1*4T6S | 6640 | 105.108 | 11.4869 | Nokia | KD03 | 24 | Kandal | 2025-07-07 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
269 | KDL0229SAN | SATHABOR | 3*2T2R | 229 | 105.0461 | 11.4268 | Nokia | KD02 | 25 | Kandal | 2025-07-10 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
270 | KDL0297SAN | SVAY_ROLOM | 3*4T6S | 297 | 104.9944 | 11.4537 | Nokia | KD02 | 25 | Kandal | 2025-07-10 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
271 | KDL0695SAN | SVAY_ROLOM3 | 3*2T2R | 695 | 104.973 | 11.4618 | Nokia | KD02 | 25 | Kandal | 2025-07-10 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
272 | KDL0835SAN | SATHABOR3 | 3*4T4R | 835 | 105.0392 | 11.4425 | Nokia | KD02 | 25 | Kandal | 2025-07-10 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
273 | KDL0914SAN | PREAK_SAMRAONG | 3*4T4R | 914 | 104.977 | 11.4587 | Nokia | KD02 | 25 | Kandal | 2025-07-10 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
274 | KDL1391SAN | PHUM5 | 3*4T4R | 1391 | 105.0183 | 11.4566 | Nokia | KD02 | 25 | Kandal | 2025-07-10 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
275 | KDL1399KSY | KAMPONG_SVAY | 3*4T4R | 1399 | 105.0585 | 11.4283 | Nokia | KD02 | 25 | Kandal | 2025-07-10 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
276 | KDL1791KDS | CHREY_RO_YOUNG | 3*4T4R | 1791 | 104.9014 | 11.3974 | Nokia | KD02 | 25 | Kandal | 2025-07-10 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
277 | KDL2385SAN | KD030 | 3*4T4R | 2385 | 104.969 | 11.4418 | Nokia | KD02 | 25 | Kandal | 2025-07-10 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
278 | KDL2395SAN | KD137 | 3*4T4R | 2395 | 104.984 | 11.42 | Nokia | KD02 | 25 | Kandal | 2025-07-10 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
279 | KDL2489KTM | KD076 | 2*4T4R+1*4T6S | 2489 | 105.027 | 11.4685 | Nokia | KD02 | 25 | Kandal | 2025-07-10 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
280 | KDL2620SAN | KD071 | 3*4T4R | 2620 | 104.9663 | 11.4515 | Nokia | KD02 | 25 | Kandal | 2025-07-10 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
281 | KDL5969TKM | KD056 | 3*2T2R | 5969 | 104.9373 | 11.4518 | Nokia | KD02 | 25 | Kandal | 2025-07-10 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
282 | KDL6094KSY | KD189 | 3*4T4R | 6094 | 105.0601 | 11.4393 | Nokia | KD02 | 25 | Kandal | 2025-07-10 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
283 | KDL6244TKM | KD249 | 3*2T2R | 6244 | 104.9578 | 11.4529 | Nokia | KD02 | 25 | Kandal | 2025-07-10 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
284 | KDL6259TKM | TKD005 | 3*2T2R | 6259 | 104.9436 | 11.4536 | Nokia | KD02 | 25 | Kandal | 2025-07-10 | WK28(07-Jul - 13-Jul) | July |  | WP Under TRC Approval
285 | KDL0296SAN | TEUK_VIL | 3*4T4R | 296 | 105.0294 | 11.3191 | Nokia | KD04 | 26 | Kandal | 2025-07-14 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
286 | KDL0533SAN | KHPOP_KOH_KHEL | 3*2T2R | 533 | 105.0379 | 11.2646 | Nokia | KD04 | 26 | Kandal | 2025-07-14 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
287 | KDL0825SAN | ROKA_KHPOS | 3*4T4R | 825 | 105.0032 | 11.401 | Nokia | KD04 | 26 | Kandal | 2025-07-14 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
288 | KDL0836SAN | TA_LOK | 3*2T2R | 836 | 105.048 | 11.2895 | Nokia | KD04 | 26 | Kandal | 2025-07-14 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
289 | KDL0994SAN | PREAEK_THEI | 3*4T4R | 994 | 105.0193 | 11.3865 | Nokia | KD04 | 26 | Kandal | 2025-07-14 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
290 | KDL1790SAN | VEAL_TRAENG | 3*2T2R | 1790 | 105.0813 | 11.3129 | Nokia | KD04 | 26 | Kandal | 2025-07-14 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
291 | KDL1792SAN | SAANG_MARKET | 3*4T4R | 1792 | 105.0019 | 11.3659 | Nokia | KD04 | 26 | Kandal | 2025-07-14 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
292 | KDL1940SAN | TUOL_SALA | 3*4T4R | 1940 | 104.9643 | 11.34 | Nokia | KD04 | 26 | Kandal | 2025-07-14 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
293 | KDL2009SAN | LEKH_BEI | 3*2T2R | 2009 | 105.1405 | 11.2842 | Nokia | KD04 | 26 | Kandal | 2025-07-14 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
294 | KDL2010SAN | LEKH_PRAM | 3*4T4R | 2010 | 105.1611 | 11.3177 | Nokia | KD04 | 26 | Kandal | 2025-07-14 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
295 | KDL2448SAN | KD123 | 3*4T4R | 2448 | 105.027 | 11.4113 | Nokia | KD04 | 26 | Kandal | 2025-07-14 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
296 | KDL2450SAN | KD134 | 2*4T4R+1*4T6S | 2450 | 105.06 | 11.326 | Nokia | KD04 | 26 | Kandal | 2025-07-14 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
297 | KDL5963SAN | KD013 | 3*2T2R | 5963 | 105.0183 | 11.3466 | Nokia | KD04 | 26 | Kandal | 2025-07-14 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
298 | KDL5972SAN | KD090 | 3*4T4R | 5972 | 105.004 | 11.3946 | Nokia | KD04 | 26 | Kandal | 2025-07-14 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
299 | KDL5974SAN | KD127 | 3*4T4R | 5974 | 105.0035 | 11.3594 | Nokia | KD04 | 26 | Kandal | 2025-07-14 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
300 | KDL5984SAN | KD196 | 3*2T2R | 5984 | 104.9836 | 11.3562 | Nokia | KD04 | 26 | Kandal | 2025-07-14 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
301 | KDL6377KDS | KAN420 | 3*4T6S | 6377 | 104.9409 | 11.354 | Nokia | KD04 | 26 | Kandal | 2025-07-14 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
302 | KDL0408KKD | KOH_OKNHATEI | 3*4T4R | 408 | 104.941 | 11.6325 | Nokia | KD06 | 27 | Kandal | 2025-07-17 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
303 | KDL1395KKD | PREAK_TAMEAK | 3*4T4R | 1395 | 105.017 | 11.7447 | Nokia | KD06 | 27 | Kandal | 2025-07-17 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
304 | KDL1513KKD | PUK_RUESSEI_KRAOM | 3*4T4R | 1513 | 104.973 | 11.6989 | Nokia | KD06 | 27 | Kandal | 2025-07-17 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
305 | KDL2069KKD | PREAK_KRABAU_TI_MUOY | 3*4T4R | 2069 | 104.967 | 11.6638 | Nokia | KD06 | 27 | Kandal | 2025-07-17 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
306 | KDL2234KKD | PREAK_LVEA | 3*4T4R | 2234 | 104.954 | 11.6061 | Nokia | KD06 | 27 | Kandal | 2025-07-17 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
307 | KDL2386KKD | KD048 | 3*4T4R | 2386 | 104.954 | 11.6347 | Nokia | KD06 | 27 | Kandal | 2025-07-17 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
308 | KDL2389KKD | KD093 | 3*4T4R | 2389 | 104.954 | 11.6224 | Nokia | KD06 | 27 | Kandal | 2025-07-17 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
309 | KDL2399KKD | KD173 | 3*4T4R | 2399 | 104.978 | 11.7118 | Nokia | KD06 | 27 | Kandal | 2025-07-17 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
310 | KDL6015KKD | KD040 | 3*4T4R | 6015 | 104.955 | 11.5857 | Nokia | KD06 | 27 | Kandal | 2025-07-17 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
311 | KDL6019LAM | KD024 | 3*4T4R | 6019 | 104.951 | 11.5753 | Nokia | KD06 | 27 | Kandal | 2025-07-17 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
312 | KDL6100KKD | KDX005 | 3*4T4R | 6100 | 104.975 | 11.597 | Nokia | KD06 | 27 | Kandal | 2025-07-17 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
313 | KDL6101KKD | KDX006 | 3*4T4R | 6101 | 104.962 | 11.59 | Nokia | KD06 | 27 | Kandal | 2025-07-17 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
314 | KDL6214LAM | KD046 | 3*4T4R | 6214 | 104.959 | 11.5725 | Nokia | KD06 | 27 | Kandal | 2025-07-17 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
315 | KDL6250KKD | KD005 | 3*4T4R | 6250 | 104.971 | 11.5848 | Nokia | KD06 | 27 | Kandal | 2025-07-17 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
316 | PNH6654CCV | #N/A | 3*4T4R | 6654 | 104.942 | 11.6573 | Nokia | KD06 | 27 | Kandal | 2025-07-17 | WK29(14-Jul - 20-Jul) | July |  | WP Under TRC Approval
317 | KDL1871LAM | TUOL_TREA | 3*4T4R | 1871 | 105.086 | 11.5562 | Nokia | KD05 | 28 | Kandal | 2025-07-21 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
318 | KDL1918LAM | PREAK_CHREY | 3*4T4R | 1918 | 105.232 | 11.4686 | Nokia | KD05 | 28 | Kandal | 2025-07-21 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
319 | KDL2025LAM | CHROUY_CHREAE | 3*4T4R | 2025 | 105.254 | 11.4144 | Nokia | KD05 | 28 | Kandal | 2025-07-21 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
320 | KDL2068LAM | KHNOR_KAR | 3*4T4R | 2068 | 105.061 | 11.6133 | Nokia | KD05 | 28 | Kandal | 2025-07-21 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
321 | KDL2102LAM | THMA_KOR | 3*4T4R | 2102 | 105.096 | 11.5167 | Nokia | KD05 | 28 | Kandal | 2025-07-21 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
322 | KDL2123LAM | TUOL_MEAS | 3*4T4R | 2123 | 104.968 | 11.5595 | Nokia | KD05 | 28 | Kandal | 2025-07-21 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
323 | KDL2391LAM | KD120 | 3*4T4R | 2391 | 105.068 | 11.5373 | Nokia | KD05 | 28 | Kandal | 2025-07-21 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
324 | KDL2396LAM | KD150 | 3*4T4R | 2396 | 105.115 | 11.5592 | Nokia | KD05 | 28 | Kandal | 2025-07-21 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
325 | KDL3121LAM | PEAM_OKNHA_ONG | 3*4T4R | 3121 | 105.026 | 11.5504 | Nokia | KD05 | 28 | Kandal | 2025-07-21 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
326 | KDL3288LAM | PHUM_TA_CHOU | 3*4T4R | 3288 | 104.99 | 11.5669 | Nokia | KD05 | 28 | Kandal | 2025-07-21 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
327 | KDL5965LAM | KD021 | 3*4T4R | 5965 | 104.979 | 11.557 | Nokia | KD05 | 28 | Kandal | 2025-07-21 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
328 | KDL6121LAM | KD045 | 3*4T4R | 6121 | 105.041 | 11.5455 | Nokia | KD05 | 28 | Kandal | 2025-07-21 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
329 | KDL6390KKD | KD277 | 3*4T4R | 6390 | 105.023 | 11.6476 | Nokia | KD05 | 28 | Kandal | 2025-07-21 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
330 | PNH1926CCV | PREAEK_CHHMUOH | 3*4T4R | 1926 | 105.137 | 11.5332 | Nokia | KD05 | 28 | Kandal | 2025-07-21 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
331 | PVG1522PRG | BAK_DAV_KRAOM | 3*4T4R | 1522 | 105.114 | 11.5945 | Nokia | KD05 | 28 | Kandal | 2025-07-21 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
332 | BB135 | #N/A | 3*4T4R |  | 103.215 | 13.14 | Swap/NewSite | Unassigned | 30 | Battambang | 2025-07-24 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
333 | BB166 | #N/A | 3*4T4R |  | 102.992 | 13.079 | Swap/NewSite | Unassigned | 29 | Battambang | 2025-07-24 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
334 | BTB6563TKL | BB246 | 3*4T4R | 6563 | 103.054 | 13.2728 | Swap/NewSite | Unassigned | 29 | Battambang | 2025-07-24 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
335 | BTB6566TKL | BB146 | 3*4T4R | 6566 | 103.14 | 13.1107 | Swap/NewSite | Unassigned | 29 | Battambang | 2025-07-24 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
336 | BTB_NEW01 | #N/A | 3*4T4R | 6564 | 103.05 | 13.0726 | Swap/NewSite | Unassigned | 29 | Battambang | 2025-07-24 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
337 | Battambang_CC_05 | #N/A | 3*4T4R |  | 103.22 | 13.1286 | Swap/NewSite | Unassigned | 30 | Battambang | 2025-07-24 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
338 | Battambang_CC_06 | #N/A | 3*4T4R |  | 103.235 | 13.1394 | Swap/NewSite | Unassigned | 30 | Battambang | 2025-07-24 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
339 | Battambang_CC_11 | #N/A | 3*4T4R |  | 103.224 | 13.0657 | Swap/NewSite | Unassigned | 29 | Battambang | 2025-07-24 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
340 | Battambang_CC_16 | #N/A | 3*4T4R | 6825 | 103.225 | 13.0887 | Swap/NewSite | Unassigned | 29 | Battambang | 2025-07-24 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
341 | Battambang_CC_20 | #N/A | 3*4T4R | 6826 | 103.212 | 13.123 | Swap/NewSite | Unassigned | 30 | Battambang | 2025-07-24 | WK30(21-Jul - 27-Jul) | July |  | WP Under TRC Approval
342 | BAT029 | #N/A | 3*4T4R |  | 103.341 | 12.9552 | Swap/NewSite | Unassigned | 31 | Battambang | 2025-07-28 | WK31(28-Jul - 03-Aug) | July |  | WP Under TRC Approval
343 | BAT228 | #N/A | 3*4T4R |  | 103.199 | 13.1432 | Swap/NewSite | Unassigned | 30 | Battambang | 2025-07-28 | WK31(28-Jul - 03-Aug) | July |  | WP Under TRC Approval
344 | BAT270 | #N/A | 3*4T4R | 6433 | 103.197 | 13.1032 | Swap/NewSite | Unassigned | 31 | Battambang | 2025-07-28 | WK31(28-Jul - 03-Aug) | July |  | WP Under TRC Approval
345 | BAT_New04 | #N/A | 3*4T4R |  | 103.225 | 13.1537 | Swap/NewSite | Unassigned | 30 | Battambang | 2025-07-28 | WK31(28-Jul - 03-Aug) | July |  | WP Under TRC Approval
346 | KD057 | #N/A | 3*4T4R | 6381 | 104.946 | 11.4756 | Swap/NewSite | Unassigned | 31 | Kandal | 2025-07-28 | WK31(28-Jul - 03-Aug) | July |  | WP Under TRC Approval
347 | KD151 | #N/A | 3*4T4R | 6840 | 105.01 | 11.5539 | Swap/NewSite | Unassigned | 31 | Kandal | 2025-07-28 | WK31(28-Jul - 03-Aug) | July |  | WP Under TRC Approval
348 | PAILIN01 | #N/A | 3*4T4R |  | 102.496 | 12.9271 | Swap/NewSite | Unassigned | 31 | Pailin | 2025-07-28 | WK31(28-Jul - 03-Aug) | July |  | WP Under TRC Approval
349 | RBAT019 | #N/A | 3*4T4R |  | 103.452 | 12.7704 | Swap/NewSite | Unassigned | 31 | Battambang | 2025-07-28 | WK31(28-Jul - 03-Aug) | July |  | WP Under TRC Approval

## BTB PROJECT-NEWSITE(130)
No. | SiteName | Province | SOW | Candidate Name | GAP | Rollout Province | RO SOW | RING NAME (CASE IPRAN) | LAT | LON | Target Solution | RO Milestone | TRC Project Name | 50 site Batch1 | TRM Requirement | TRM Remark | TX. Comments | Cluster | Forecast Start | Forecast OA Date | Swap Forecast Week | OA Month | OA Actual | GAP OA Analysis
1 | KDT116 | Kandal | New site ZTE | KDT116 | Do-Able | Kandal | ZTE Wireless+Eltek Power cabinet*2Battery+ZTE New MW |  | 11.3457 | 105.0353 | 3*4T4R | 5-RFI-Stage | Kandal | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 500Mbps | Batch1 OK-Greenlight | 0 | 2025-04-25 | 2025-04-28 | WK18(28-Apr - 04-May) | April |  | Do-Able
2 | KDT117 | Kandal | New site ZTE | KDT117 | Do-Able | Kandal | ZTE Wireless+Eltek Power cabinet*2Battery+ZTE New MW |  | 11.2941 | 105.0344 | 3*4T4R | 5-RFI-Stage | Kandal | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 500Mbps | Batch1 OK-Greenlight | 0 | 2025-04-25 | 2025-04-28 | WK18(28-Apr - 04-May) | April |  | Do-Able
3 | TCE_KD022 | Phnom Penh | New site ZTE | TCE_KD022 | Do-Able | Kandal | ZTE Wireless+Eltek Power cabinet*2Battery+ZTE New MW |  | 11.4563 | 105.0517 | 3*4T4R | 4-CME-Stage | 3rd Ring Road | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 500Mbps | Batch1 OK-Greenlight | 0 | 2025-04-25 | 2025-04-28 | WK18(28-Apr - 04-May) | April |  | Do-Able
4 | TCE_KD038 | Kandal | New site ZTE | TCE_KD038 | Do-Able | Kandal | ZTE Wireless+Eltek Power cabinet*2Battery+ZTE New MW |  | 11.3711 | 105.0084 | 3*4T4R | 4-CME-Stage | Kandal | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 500Mbps | Batch1 OK-Greenlight | 0 | 2025-04-25 | 2025-04-28 | WK18(28-Apr - 04-May) | April |  | Do-Able
5 | TCE_KD039 | Kandal | New site ZTE | TCE_KD039 | Do-Able | Kandal | ZTE Wireless+Eltek Power cabinet*2Battery+ZTE New MW |  | 11.3601 | 105.0167 | 3*4T4R | 4-CME-Stage | Kandal | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 500Mbps | Batch1 OK-Greenlight | 0 | 2025-04-25 | 2025-04-28 | WK18(28-Apr - 04-May) | April |  | Do-Able
6 | KD072 | Kandal | New site ZTE | KD072 | Do-Able | Kandal | ZTE Wireless+Eltek Power cabinet*2Battery+ZTE New MW |  | 11.413 | 105.0435 | 3*4T4R | 5-RFI-Stage | Kandal | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 500Mbps | Batch1 OK-Greenlight | 0 | 2025-04-29 | 2025-05-02 | WK18(28-Apr - 04-May) | May |  | Do-Able
7 | TCE_KD024 | Kandal | Nokia re-deployment | TCE_KD024 | Do-Able | Kandal | Nokia Wireless+Elteck Power cabinet *2Battery+ ZTE New MW |  | 11.0539 | 105.0637 | Dismantled Nokia BTS | 4-CME-Stage | Kandal | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 600Mbps | Batch1 OK-Greenlight | 1 | 2025-04-29 | 2025-05-02 | WK18(28-Apr - 04-May) | May |  | Do-Able
8 | TCE_KD027 | Kandal | Nokia re-deployment | TCE_KD027 | Do-Able | Kandal | Nokia Wireless+Elteck Power cabinet *2Battery+ ZTE New MW |  | 11.1393 | 105.2247 | Dismantled Nokia BTS | 4-CME-Stage | Kandal | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 600Mbps | Batch1 OK-Greenlight | 1 | 2025-04-29 | 2025-05-02 | WK18(28-Apr - 04-May) | May |  | Do-Able
9 | TCE_KD029 | Kandal | Nokia re-deployment | TCE_KD029 | Do-Able | Kandal | Nokia Wireless+Elteck Power cabinet *2Battery+ ZTE New MW |  | 11.4692 | 105.1713 | Dismantled Nokia BTS | 4-CME-Stage | Kandal | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS(REQUIRE KANDAOL_LEU_AGG_RING1) | NEW MW 600Mbps(KANDAOL_LEU_AGG_RING1) | Batch1 OK-Greenlight | 0 | 2025-04-29 | 2025-05-02 | WK18(28-Apr - 04-May) | May |  | Do-Able
10 | TKD041 | Kandal | Nokia re-deployment | TKD041 | Do-Able | Kandal | Nokia Wireless+Elteck Power cabinet *2Battery+ ZTE New MW |  | 11.6777 | 104.7946 | Dismantled Nokia BTS | 4-CME-Stage | Kandal | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 600Mbps | Batch1 OK-Greenlight | 4 | 2025-04-29 | 2025-05-02 | WK18(28-Apr - 04-May) | May |  | Do-Able
11 | KD108SE | Kandal | Nokia re-deployment | KD108SE | Do-Able | Kandal | Nokia Wireless+Elteck Power cabinet *2Battery+ ZTE New MW |  | 11.1787 | 105.0766 | Dismantled Nokia BTS | 5-RFI-Stage | Kandal | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS(SAMPONG_LEU_ACC_RING1) | NEW MW 600Mbps(SAMPONG_LEU_ACC_RING1) | Batch1 OK-Greenlight | 1 | 2025-05-03 | 2025-05-06 | WK19(05-May - 11-May) | May |  | Do-Able
12 | TCE_KD013 | Kandal | Nokia re-deployment | TCE_KD013 | Do-Able | Kandal | Nokia Wireless+Elteck Power cabinet *2Battery+ ZTE New MW |  | 11.6601 | 105.0675 | Dismantled Nokia BTS | 4-CME-Stage | Kandal | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 600Mbps | Batch1 OK-Greenlight | 0 | 2025-05-03 | 2025-05-06 | WK19(05-May - 11-May) | May |  | Do-Able
13 | TCE_KD023 | Kandal | Nokia re-deployment | TCE_KD023 | Do-Able | Kandal | Nokia Wireless+Elteck Power cabinet *2Battery+ ZTE New MW |  | 11.2332 | 105.0418 | Dismantled Nokia BTS | 4-CME-Stage | Kandal | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 600Mbps | Batch1 OK-Greenlight | 1 | 2025-05-03 | 2025-05-06 | WK19(05-May - 11-May) | May |  | Do-Able
14 | TCE_KD032 | Kandal | Nokia re-deployment | TCE_KD032 | Do-Able | Kandal | Nokia Wireless+Elteck Power cabinet *2Battery+ ZTE New MW |  | 11.4522 | 105.2579 | Dismantled Nokia BTS | 4-CME-Stage | Kandal | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS(REQUIRE KANDAOL_LEU_AGG_RING1) | NEW MW 600Mbps(KANDAOL_LEU_AGG_RING1)-allocated from 29MW Links | Batch1 OK-Greenlight | 0 | 2025-05-03 | 2025-05-06 | WK19(05-May - 11-May) | May |  | Do-Able
15 | TKT083 | Takeo | Nokia re-deployment | TKT083 | Do-Able | Takeo | Nokia Wireless+Elteck Power cabinet *2Battery+ ZTE New MW |  | 11.1211 | 104.9405 | Dismantled Nokia BTS | 5-RFI-Stage | Takeo | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 600Mbps | Batch1 OK-Greenlight | 1 | 2025-05-03 | 2025-05-06 | WK19(05-May - 11-May) | May |  | Do-Able
16 | KCT086 | Kandal | Nokia re-deployment | KCT086 | Do-Able | Kandal | Nokia Wireless+Elteck Power cabinet *2Battery+ ZTE New MW |  | 11.8637 | 105.016 | Dismantled Nokia BTS | 5-RFI-Stage | Kandal | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 600Mbps | Batch1 OK-Greenlight | 0 | 2025-05-07 | 2025-05-10 | WK19(05-May - 11-May) | May |  | Do-Able
17 | KD044SE | Kandal | Nokia re-deployment | KD044SE | Do-Able | Kandal | Nokia Wireless+Elteck Power cabinet *2Battery+ ZTE New MW |  | 11.3031 | 104.9684 | Dismantled Nokia BTS | 5-RFI-Stage | Kandal | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 600Mbps | Batch1 OK-Greenlight | 0 | 2025-05-07 | 2025-05-10 | WK19(05-May - 11-May) | May |  | Do-Able
18 | KD268 | Kandal | Nokia re-deployment | KD268 | Do-Able | Kandal | Nokia Wireless+Elteck Power cabinet *2Battery+ ZTE New MW |  | 11.0908 | 105.1893 | Dismantled Nokia BTS | 5-RFI-Stage | Kandal | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 600Mbps | Batch1 OK-Greenlight | 1 | 2025-05-07 | 2025-05-10 | WK19(05-May - 11-May) | May |  | Do-Able
19 | KDT014 | Kandal | Nokia re-deployment | KDT014 | Do-Able | Kandal | Nokia Wireless+Elteck Power cabinet *2Battery+ ZTE New MW |  | 11.429 | 104.6745 | Dismantled Nokia BTS | 5-RFI-Stage | Kandal | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 600Mbps | Batch1 OK-Greenlight | 4 | 2025-05-07 | 2025-05-10 | WK19(05-May - 11-May) | May |  | Do-Able
20 | TKT059 | Takeo | Nokia re-deployment | TKT059 | Do-Able | Takeo | Nokia Wireless+Elteck Power cabinet *2Battery+ ZTE New MW |  | 11.0621 | 104.882 | Dismantled Nokia BTS | 5-RFI-Stage | Takeo | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 600Mbps | Batch1 OK-Greenlight | 1 | 2025-05-07 | 2025-05-10 | WK19(05-May - 11-May) | May |  | Do-Able
21 | AROMA Success (new built) | Kampong Speu | Nokia re-deployment | TKS003 | Do-Able | Kampong Speu | Nokia Wireless+Elteck Power cabinet *2Battery+ ZTE New MW |  | 11.5663 | 104.362 | Dismantled Nokia BTS | 5-RFI-Stage | - | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 600Mbps | Batch1 OK-Greenlight | 4 | 2025-05-12 | 2025-05-16 | WK20(12-May - 18-May) | May |  | Do-Able
22 | GTK20 | Takeo | Nokia re-deployment | GTK20 | Do-Able | Takeo | ZTE Wireless+Eltek Power cabinet*2Battery+MW Redeploy |  | 10.8548 | 104.8213 | Dismantled Nokia BTS | 5-RFI-Stage | Takeo | 50 site List | MW REDEPLOY | MW REDEPLOY FROM KIENSVAY_ACC_RING1 | Batch1 Swap+New Remaining | 1 | 2025-05-12 | 2025-05-16 | WK20(12-May - 18-May) | May |  | Do-Able
23 | KDT017 | Kandal | New site ZTE | KDT017 | Do-Able | Kandal | ZTE Wireless+Eltek Power cabinet*2Battery+MW Redeploy |  | 11.3719 | 104.8833 | 3*4T4R | 5-RFI-Stage | Kandal | 50 site List | MW REDEPLOY | MW REDEPLOY FROM SAMPONG_LEU_ACC_RING1 | Batch1 Swap+New Remaining | 0 | 2025-05-12 | 2025-05-16 | WK20(12-May - 18-May) | May |  | Do-Able
24 | TCE_PP117 | Phnom Penh | Nokia re-deployment | TCE_PP117 | FO Readiness Dependency | Phnom Penh | ZTE Wireless+Eltek Power cabinet*2Battery+MW Redeploy | TUOL_LIEB_ACC_RING1 | 11.5927 | 104.754 | Dismantled Nokia BTS | 4-CME-Stage | 14-Khan | 50 site List | MW REDEPLOY | MW REDEPLOY FROM SAMPONG_LEU_ACC_RING1 | Batch1 Swap+New Remaining | 4 | 2025-05-12 | 2025-05-16 | WK20(12-May - 18-May) | May |  | FO Readiness Dependency
25 | TTK003 | Tboung khmum | Nokia re-deployment | TTK003 | FO Readiness Dependency | Tboung khmum | Nokia Wireless+Elteck Power cabinet *2Battery+IPRAN(ZTE) | SOUNG_AGG_MF1 | 11.9224 | 105.6497 | Dismantled Nokia BTS | 5-RFI-Stage | Tboung khmum | - | - | - | - | 3 | 2025-05-12 | 2025-05-16 | WK20(12-May - 18-May) | May |  | FO Readiness Dependency
26 | KDT115 | Kandal | New site ZTE | KDT115 | FO Readiness Dependency | Kandal | ZTE Wireless+Eltek Power cabinet*2Battery+IPRAN(ZTE) | SVAY_ROLOM_ACC_RING1 | 11.4542 | 105.0301 | 3*4T4R | 5-RFI-Stage | Kandal | 50 site List | SVAY_ROLOM_ACC_RING1 | NEW RING | Batch1 OK-Greenlight | 0 | 2025-05-17 | 2025-05-20 | WK21(19-May - 25-May) | May |  | FO Readiness Dependency
27 | KDX002 | Kandal | New site ZTE | KD246 | FO Readiness Dependency | Kandal | ZTE Wireless+Eltek Power cabinet*2Battery+IPRAN(Huawei) | PPMAR46 | 11.4626 | 104.9601 | 3*4T4R | 5-RFI-Stage | Kandal | 50 site List | Insertion to PPMAR46 | Insertion to PPMAR46 | Batch1 OK-Greenlight | 0 | 2025-05-17 | 2025-05-20 | WK21(19-May - 25-May) | May |  | FO Readiness Dependency
28 | TCE_BB025 | Battambang | New site ZTE | TCE_BB025 | FO Readiness Dependency | Battambang | ZTE Wireless+Eltek Power cabinet*2Battery+IPRAN(ZTE) | BTB_AGG_MF3 | 13.0901 | 103.1884 | 3*4T4R | 4-CME-Stage | Battam Bang | 50 site List | BTB_AGG_MF3 | NEW RING | Batch1 Swap+New Remaining | 2 | 2025-05-17 | 2025-05-20 | WK21(19-May - 25-May) | May |  | FO Readiness Dependency
29 | TCE_KD018 | Kandal | New site ZTE | TCE_KD018 | FO Readiness Dependency | Kandal | ZTE Wireless+Eltek Power cabinet*2Battery+IPRAN(ZTE) | KIENSVAY_ACC_RING1 | 11.5167 | 105.0695 | 3*4T4R | 4-CME-Stage | Kandal | 50 site List | KIENSVAY_ACC_RING1 | NEW RING | Batch1 OK-Greenlight | 0 | 2025-05-17 | 2025-05-20 | WK21(19-May - 25-May) | May |  | FO Readiness Dependency
30 | TCE_KD019 | Kandal | New site ZTE | TCE_KD019 | FO Readiness Dependency | Kandal | ZTE Wireless+Eltek Power cabinet*2Battery+IPRAN(ZTE) | KIENSVAY_ACC_RING1 | 11.4969 | 105.0463 | 3*4T4R | 4-CME-Stage | Kandal | 50 site List | KIENSVAY_ACC_RING1 | NEW RING | Batch1 OK-Greenlight | 0 | 2025-05-17 | 2025-05-20 | WK21(19-May - 25-May) | May |  | FO Readiness Dependency
31 | 3rd_RingRoad_CC_10 | Phnom Penh | Nokia re-deployment | TCE_PP164 | FO Readiness Dependency | Phnom Penh | Nokia Wireless+Elteck Power cabinet *2Battery+IPRAN(ZTE) | PPMAR115 | 11.5884 | 104.8044 | Dismantled Nokia BTS | 4-CME-Stage | 3rd Ring Road | 50 site List | PPMAR171-Insertion(Huawei-26Redeploy) | PPMAR171-Insertion(Huawei-26Redeploy) | Batch1 Swap+New Remaining | 4 | 2025-05-21 | 2025-05-24 | WK21(19-May - 25-May) | May |  | FO Readiness Dependency
32 | PPB134 | Kandal | Nokia re-deployment | PPB134 | FO Readiness Dependency | Kandal | Nokia Wireless+Elteck Power cabinet *2Battery+IPRAN(Huawei) | PPMAR116 | 11.5358 | 104.7584 | Dismantled Nokia BTS | 5-RFI-Stage | Kandal | 50 site List | PPMAR116-Insertion | NEW RING | Batch1 OK-Greenlight | 4 | 2025-05-21 | 2025-05-24 | WK21(19-May - 25-May) | May |  | FO Readiness Dependency
33 | TBT001 | Tboung khmum | Nokia re-deployment | TBT001 | FO Readiness Dependency | Tboung khmum | Nokia Wireless+Elteck Power cabinet *2Battery+IPRAN(ZTE) | SOUNG_AGG_MF1 | 11.9125 | 105.6222 | Dismantled Nokia BTS | 4-CME-Stage | Tboung khmum | 50 site List | SOUNG_AGG_MF1 | SOUNG_AGG_MF1 | Batch1 OK-Greenlight | 3 | 2025-05-21 | 2025-05-24 | WK21(19-May - 25-May) | May |  | FO Readiness Dependency
34 | TCE_KD025 | Kandal | Nokia re-deployment | TCE_KD025 | FO Readiness Dependency | Kandal | Nokia Wireless+Elteck Power cabinet *2Battery+IPRAN(ZTE) | SAMPONG_LEU_ACC_RING1 | 11.1082 | 105.064 | Dismantled Nokia BTS | 4-CME-Stage | Kandal | 50 site List | SAMPONG_LEU_ACC_RING1 | NEW RING | Batch1 OK-Greenlight | 1 | 2025-05-21 | 2025-05-24 | WK21(19-May - 25-May) | May |  | FO Readiness Dependency
35 | TCE_KD026 | Kandal | Nokia re-deployment | TCE_KD026 | FO Readiness Dependency | Kandal | Nokia Wireless+Elteck Power cabinet *2Battery+IPRAN(ZTE) | SAMPONG_LEU_ACC_RING1 | 11.1594 | 105.0616 | Dismantled Nokia BTS | 4-CME-Stage | Kandal | 50 site List | SAMPONG_LEU_ACC_RING1 | NEW RING | Batch1 OK-Greenlight | 1 | 2025-05-21 | 2025-05-24 | WK21(19-May - 25-May) | May |  | FO Readiness Dependency
36 | AngSnoul_CC_09 | Phnom Penh | Nokia re-deployment | PP827 | FO Readiness Dependency | Kandal | Nokia Wireless+Elteck Power cabinet *2Battery+IPRAN(Huawei) | PPSEZ Ring | 11.4972 | 104.7658 | Dismantled Nokia BTS | 5-RFI-Stage | Kandal | 50 site List | PPSEZ-Insertion | NEW RING | Batch1 OK-Greenlight | 4 | 2025-05-25 | 2025-05-28 | WK22(26-May - 01-Jun) | May |  | FO Readiness Dependency
37 | AngSnoul_CC_10 | Kandal | Nokia re-deployment | PP400 | FO Readiness Dependency | Kandal | Nokia Wireless+Elteck Power cabinet *2Battery+IPRAN(Huawei) | PPSEZ Ring | 11.5099 | 104.7641 | Dismantled Nokia BTS | 5-RFI-Stage | Kandal | 50 site List | PPSEZ-Insertion | NEW RING | Batch1 OK-Greenlight | 4 | 2025-05-25 | 2025-05-28 | WK22(26-May - 01-Jun) | May |  | FO Readiness Dependency
38 | TKT086 | Takeo | Nokia re-deployment | TKT086 | FO Readiness Dependency | Takeo | Nokia Wireless+Elteck Power cabinet *2Battery+IPRAN(ZTE) | THNAL_BAT_AGG_RING1 | 11.1076 | 104.7245 | Dismantled Nokia BTS | 5-RFI-Stage | Takeo | 50 site List | THNAL_BAT_AGG_RING1 | NEW RING | Batch1 Swap+New Remaining | 1 | 2025-05-25 | 2025-05-28 | WK22(26-May - 01-Jun) | May |  | FO Readiness Dependency
39 | TKT087 | Takeo | Nokia re-deployment | TKT087 | FO Readiness Dependency | Takeo | Nokia Wireless+Elteck Power cabinet *2Battery+IPRAN(ZTE) | THNAL_BAT_AGG_RING1 | 11.101 | 104.6847 | Dismantled Nokia BTS | 5-RFI-Stage | Takeo | 50 site List | THNAL_BAT_AGG_RING1 | NEW RING | Batch1 Swap+New Remaining | 1 | 2025-05-25 | 2025-05-28 | WK22(26-May - 01-Jun) | May |  | FO Readiness Dependency
40 | TTK002 | Tboung khmum | Nokia re-deployment | TTK002 | FO Readiness Dependency | Tboung khmum | Nokia Wireless+Elteck Power cabinet *2Battery+IPRAN(ZTE) | SOUNG_AGG_MF1 | 11.9021 | 105.6576 | Dismantled Nokia BTS | 5-RFI-Stage | Tboung khmum | 50 site List | SOUNG_AGG_MF1 | SOUNG_AGG_MF1 | Batch1 OK-Greenlight | 3 | 2025-05-25 | 2025-05-28 | WK22(26-May - 01-Jun) | May |  | FO Readiness Dependency
41 | KhsachKandal_CC_01 | Kandal | New site ZTE | KDX007 |  |  |  |  | 11.6396 | 104.9865 | 3*4T4R | 3-SO-Stage | Kandal | - | - | - | - | 0 | 2025-05-29 | 2025-06-01 | WK22(26-May - 01-Jun) | June
42 | KhsachKandal_CC_02 | Kandal | New site ZTE | KDT035 |  |  |  |  | 11.7302 | 104.9911 | 3*4T4R | 3-SO-Stage | Kandal | - | - | - | - | 0 | 2025-05-29 | 2025-06-01 | WK22(26-May - 01-Jun) | June
43 | KhsachKandal_CC_03 | Kandal | New site ZTE | KD254 |  |  |  |  | 11.7378 | 105.0128 | 3*4T4R | 3-SO-Stage | Kandal | - | - | - | - | 0 | 2025-05-29 | 2025-06-01 | WK22(26-May - 01-Jun) | June
44 | KhsachKandal_CC_12 | Kandal | New site ZTE | TCE_KD014 |  |  |  |  | 11.6186 | 105.1027 | 3*4T4R | 3-SO-Stage | Kandal | - | - | - | - | 0 | 2025-05-29 | 2025-06-01 | WK22(26-May - 01-Jun) | June
45 | LveaAem_CC_14 | Kandal | New site ZTE | PV087 |  |  |  |  | 11.5326 | 105.1606 | 3*4T4R | 3-SO-Stage | Kandal | - | - | - | - | 0 | 2025-05-29 | 2025-06-01 | WK22(26-May - 01-Jun) | June
46 | KD174 | Kandal | New site ZTE | KDX009 |  |  |  |  | 11.4566 | 104.9829 | 3*4T4R | 3-SO-Stage | Kandal | - | - | - | - | 0 | 2025-06-02 | 2025-06-05 | WK23(02-Jun - 08-Jun) | June
47 | LveaAem_CC_07 | Kandal | New site ZTE | TKD056 |  |  |  |  | 11.4479 | 105.2061 | 3*4T4R | 3-SO-Stage | Kandal | - | - | - | - | 0 | 2025-06-02 | 2025-06-05 | WK23(02-Jun - 08-Jun) | June
48 | Saáng_CC_13 | Kandal | New site ZTE | TKD060 |  |  |  |  | 11.2538 | 105.0273 | 3*4T4R | 3-SO-Stage | Kandal | - | - | - | - | 1 | 2025-06-02 | 2025-06-05 | WK23(02-Jun - 08-Jun) | June
49 | TCE_KD046 | Kandal | New site ZTE | TKD063 |  |  |  |  | 11.4446 | 104.9357 | 3*4T4R | 3-SO-Stage | Kandal | - | - | - | - | 0 | 2025-06-02 | 2025-06-05 | WK23(02-Jun - 08-Jun) | June
50 | TKD066 | Kandal | New site ZTE | TKD066 |  |  |  |  | 11.4321 | 104.9901 | 3*4T4R | 3-SO-Stage | 3rd Ring Road | - | - | - | - | 0 | 2025-06-02 | 2025-06-05 | WK23(02-Jun - 08-Jun) | June
51 | NOREA_CITY01 | Phnom Penh | New site ZTE | TPP076 |  |  |  |  | 11.5489 | 104.9482 | 3*4T4R | 6-WP-Stage |  | 50 site List | KOH_NOREA_ACC_RING | New Ring Proposal | Batch1 OK-Greenlight | 0 | 2025-06-06 | 2025-06-09 | WK24(09-Jun - 15-Jun) | June
52 | NOREA_CITY02 | Phnom Penh | New site ZTE | TPP077 |  |  |  |  | 11.5432 | 104.9589 | 3*4T4R | 6-WP-Stage |  | 50 site List | KOH_NOREA_ACC_RING | New Ring Proposal | Batch1 OK-Greenlight | 0 | 2025-06-06 | 2025-06-09 | WK24(09-Jun - 15-Jun) | June
53 | NOREA_CITY03 | Phnom Penh | New site ZTE | TPP078 |  |  |  |  | 11.5366 | 104.9809 | 3*4T4R | 6-WP-Stage |  | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 600Mbps | Batch1 OK-Greenlight | 0 | 2025-06-06 | 2025-06-09 | WK24(09-Jun - 15-Jun) | June
54 | TCE_KD037 | Kandal | New site ZTE | TCE_KD037 |  |  |  |  | 11.4207 | 104.994 | 3*4T4R | 4-CME-Stage | Kandal | - | - | - | - | 0 | 2025-06-06 | 2025-06-09 | WK24(09-Jun - 15-Jun) | June
55 | TKD053 | Kandal | New site ZTE | TKD053 |  |  |  |  | 11.4736 | 104.9446 | 3*4T4R | 7-TE Stage | Kandal | - | - | - | - | 0 | 2025-06-06 | 2025-06-09 | WK24(09-Jun - 15-Jun) | June
56 | KhsachKandal_CC_04 | Kandal | New site ZTE | KDT037 |  |  |  |  | 11.7692 | 105.024 | 3*4T4R | 7-TE Stage | Kandal | - | - | - | - | 0 | 2025-06-10 | 2025-06-13 | WK24(09-Jun - 15-Jun) | June
57 | KienSvay_CC_06 | Kandal | New site ZTE | KD105 |  |  |  |  | 11.4161 | 105.219 | 3*4T4R | 7-TE Stage | Kandal | - | - | - | - | 0 | 2025-06-10 | 2025-06-13 | WK24(09-Jun - 15-Jun) | June
58 | TBB005 | Battambang | New site ZTE | TBB005 |  |  |  |  | 13.0951 | 103.2135 | 3*4T4R | 8-On Air | Battam Bang | - | - | - | - | 2 | 2025-06-10 | 2025-06-13 | WK24(09-Jun - 15-Jun) | June
59 | TKD016 | Kandal | New site ZTE | TKD016 |  |  |  |  | 11.4711 | 104.9387 | 3*4T4R | 7-TE Stage | Kandal | - | - | - | - | 0 | 2025-06-10 | 2025-06-13 | WK24(09-Jun - 15-Jun) | June
60 | TKM001 | Takeo | Nokia re-deployment | TKM001 |  |  |  |  | 11.1938 | 104.8084 | Dismantled Nokia BTS | 9-Blockage | Takeo | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 350Mbps | Batch1 OK-Greenlight | 1 | 2025-06-10 | 2025-06-13 | WK24(09-Jun - 15-Jun) | June
61 | KD109SE | Kandal | Nokia re-deployment | KD109SE |  |  |  |  | 11.2136 | 105.2597 | Dismantled Nokia BTS | 5-RFI-Stage | Kandal | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 600Mbps | Batch1 OK-Greenlight | 0 | 2025-06-14 | 2025-06-17 | WK25(16-Jun - 22-Jun) | June
62 | KD203 | Kandal | Nokia re-deployment | KD203 |  |  |  |  | 11.1878 | 105.0187 | Dismantled Nokia BTS | 5-RFI-Stage | Kandal | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 600Mbps | Batch1 OK-Greenlight | 1 | 2025-06-14 | 2025-06-17 | WK25(16-Jun - 22-Jun) | June
63 | KD214 | Kandal | Nokia re-deployment | KD214 |  |  |  |  | 11.5007 | 105.1307 | Dismantled Nokia BTS | 5-RFI-Stage | Kandal | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS(REQUIRE KANDAOL_LEU_AGG_RING1) | NEW MW 600Mbps(KANDAOL_LEU_AGG_RING1) | Batch1 OK-Greenlight | 0 | 2025-06-14 | 2025-06-17 | WK25(16-Jun - 22-Jun) | June
64 | TKT093 | Takeo | Nokia re-deployment | TKT093 |  |  |  |  | 10.8124 | 104.7633 | Dismantled Nokia BTS | 5-RFI-Stage | Takeo | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 600Mbps | Batch1 OK-Greenlight | 1 | 2025-06-14 | 2025-06-17 | WK25(16-Jun - 22-Jun) | June
65 | TTA016 | Takeo | Nokia re-deployment | TTA016 |  |  |  |  | 11.1581 | 104.7101 | Dismantled Nokia BTS | 5-RFI-Stage | Takeo | 50 site List | MW REDEPLOY | MW REDEPLOY FROM KOH_NOREA_ACC_RING | Batch1 Swap+New Remaining | 1 | 2025-06-14 | 2025-06-17 | WK25(16-Jun - 22-Jun) | June
66 | Commune Hall, Residents, Factories | Kampong Speu | Nokia re-deployment | - |  |  |  |  | 11.4053 | 104.516 | Dismantled Nokia BTS | 1-SAQ-Stage | - | - | - | - | - | 4 | 2025-06-19 | 2025-06-22 | WK25(16-Jun - 22-Jun) | June
67 | GTK24 | Takeo | Nokia re-deployment | GTK24 |  |  |  |  | 10.8838 | 104.8407 | Dismantled Nokia BTS | 5-RFI-Stage | Takeo | 50 site List | NEW MW & RE-ALLOCATED FROM 29LINKS | NEW MW 600Mbps | Batch1 Swap+New Remaining | 1 | 2025-06-19 | 2025-06-22 | WK25(16-Jun - 22-Jun) | June
68 | KDT037 | Kandal | Nokia re-deployment | KDT037 |  |  |  |  | 11.7692 | 105.024 | Dismantled Nokia BTS | 7-TE Stage | Kandal | 50 site List | MW REDEPLOY | MW REDEPLOY FROM SOUNG_AGG_MF1 | Batch1 Swap+New Remaining | 0 | 2025-06-19 | 2025-06-22 | WK25(16-Jun - 22-Jun) | June
69 | KS067 | Kampong Speu | Nokia re-deployment | - |  |  |  |  | 11.4373 | 104.52 | Dismantled Nokia BTS | 1-SAQ-Stage | - | - | - | - | - | 4 | 2025-06-19 | 2025-06-22 | WK25(16-Jun - 22-Jun) | June
70 | Pneay Factories and Commune Hall | Kampong Speu | Nokia re-deployment | - |  |  |  |  | 11.5414 | 104.523 | Dismantled Nokia BTS | 1-SAQ-Stage | - | - | - | - | - | 4 | 2025-06-19 | 2025-06-22 | WK25(16-Jun - 22-Jun) | June
71 | KS0246 | Kampong Speu | Nokia re-deployment | - |  |  |  |  | 11.5197 | 104.642 | Dismantled Nokia BTS | 1-SAQ-Stage | - | - | - | - | - | 4 | 2025-06-23 | 2025-06-26 | WK26(23-Jun - 29-Jun) | June
72 | KS0267 | Kampong Speu | Nokia re-deployment | - |  |  |  |  | 11.5733 | 104.638 | Dismantled Nokia BTS | 1-SAQ-Stage | - | - | - | - | - | 4 | 2025-06-23 | 2025-06-26 | WK26(23-Jun - 29-Jun) | June
73 | KS134 | Kampong Speu | Nokia re-deployment | - |  |  |  |  | 11.4143 | 104.616 | Dismantled Nokia BTS | 1-SAQ-Stage | - | - | - | - | - | 4 | 2025-06-23 | 2025-06-26 | WK26(23-Jun - 29-Jun) | June
74 | KS136 | Kampong Speu | Nokia re-deployment | - |  |  |  |  | 11.5094 | 104.597 | Dismantled Nokia BTS | 1-SAQ-Stage | - | - | - | - | - | 4 | 2025-06-23 | 2025-06-26 | WK26(23-Jun - 29-Jun) | June
75 | SPE194 | Kampong Speu | Nokia re-deployment | - |  |  |  |  | 11.3782 | 104.624 | Dismantled Nokia BTS | 1-SAQ-Stage | - | - | - | - | - | 4 | 2025-06-23 | 2025-06-26 | WK26(23-Jun - 29-Jun) | June
76 | K.Cham_CC_02 | Kampong Cham | Nokia re-deployment | GKC07 |  |  |  |  | 11.995 | 105.4575 | Dismantled Nokia BTS | 3-SO-Stage | Kompong Cham | - | - | - | - | 3 | 2025-06-27 | 2025-06-30 | WK27(30-Jun - 06-Jul) | June
77 | K.Cham_CC_05 | Kampong Cham | Nokia re-deployment | GKC09 |  |  |  |  | 11.9769 | 105.4574 | Dismantled Nokia BTS | 3-SO-Stage | Kompong Cham | - | - | - | - | 3 | 2025-06-27 | 2025-06-30 | WK27(30-Jun - 06-Jul) | June
78 | KC006 | Kampong Cham | Nokia re-deployment | KCT016 |  |  |  |  | 11.9947 | 105.454 | Dismantled Nokia BTS | 1-SAQ-Stage | Kompong Cham | - | - | - | - | 3 | 2025-06-27 | 2025-06-30 | WK27(30-Jun - 06-Jul) | June
79 | SPE185 | Kampong Speu | Nokia re-deployment | - |  |  |  |  | 11.4609 | 104.523 | Dismantled Nokia BTS | 1-SAQ-Stage | - | - | - | - | - | 4 | 2025-06-27 | 2025-06-30 | WK27(30-Jun - 06-Jul) | June
80 | Tramkak_CamGSM_01 | Takeo | Nokia re-deployment | TTA031 |  |  |  |  | 10.993 | 104.6766 | Dismantled Nokia BTS | 1-SAQ-Stage | Takeo | - | - | - | - | 1 | 2025-06-27 | 2025-06-30 | WK27(30-Jun - 06-Jul) | June
81 | AngSnoul_CC_03 | Kandal | Nokia re-deployment | KDT005 |  |  |  |  | 11.5008 | 104.6862 | Dismantled Nokia BTS | 3-SO-Stage | Kandal | - | - | - | - | 4 | 2025-07-01 | 2025-07-04 | WK27(30-Jun - 06-Jul) | July
82 | KhsachKandal_CC_09 | Kandal | Nokia re-deployment | KD068 |  |  |  |  | 11.6822 | 105.0703 | Dismantled Nokia BTS | 3-SO-Stage | Kandal | - | - | - | - | 0 | 2025-07-01 | 2025-07-04 | WK27(30-Jun - 06-Jul) | July
83 | LeukDaek_CC_08 | Kandal | Nokia re-deployment | KD0333 |  |  |  |  | 10.9884 | 105.1785 | Dismantled Nokia BTS | 3-SO-Stage | Kandal | - | - | - | - | 1 | 2025-07-01 | 2025-07-04 | WK27(30-Jun - 06-Jul) | July
84 | Prey Kabas_CamGSM_02 | Takeo | Nokia re-deployment | TKT082 |  |  |  |  | 11.1294 | 104.8651 | Dismantled Nokia BTS | 3-SO-Stage | Takeo | - | - | - | - | 1 | 2025-07-01 | 2025-07-04 | WK27(30-Jun - 06-Jul) | July
85 | Tramkak_CamGSM_13 | Takeo | Nokia re-deployment | TCE_TK036 |  |  |  |  | 11.0698 | 104.5895 | Dismantled Nokia BTS | 3-SO-Stage | Takeo | - | - | - | - | 1 | 2025-07-01 | 2025-07-04 | WK27(30-Jun - 06-Jul) | July
86 | Daun Keo_CamGSM_08 | Takeo | Nokia re-deployment | TCE_TK017 |  |  |  |  | 10.9351 | 104.7872 | Dismantled Nokia BTS | 3-SO-Stage | Takeo | - | - | - | - | 1 | 2025-07-05 | 2025-07-08 | WK28(07-Jul - 13-Jul) | July
87 | PonheaLeu_CC_09 | Kandal | Nokia re-deployment | KDT103 |  |  |  |  | 11.7854 | 104.7763 | Dismantled Nokia BTS | 3-SO-Stage | Kandal | - | - | - | - | 4 | 2025-07-05 | 2025-07-08 | WK28(07-Jul - 13-Jul) | July
88 | Samroang_CamGSM_23 | Takeo | Nokia re-deployment | TKT088 |  |  |  |  | 11.0381 | 104.7626 | Dismantled Nokia BTS | 3-SO-Stage | Takeo | - | - | - | - | 1 | 2025-07-05 | 2025-07-08 | WK28(07-Jul - 13-Jul) | July
89 | TCE_PP118 | Phnom Penh | Nokia re-deployment | TPP123 |  |  |  |  | 11.6186 | 104.7511 | Dismantled Nokia BTS | 3-SO-Stage | 14-Khan | - | - | - | - | 4 | 2025-07-05 | 2025-07-08 | WK28(07-Jul - 13-Jul) | July
90 | Tramkak_CamGSM_05 | Takeo | Nokia re-deployment | TKT090 |  |  |  |  | 11.0221 | 104.6309 | Dismantled Nokia BTS | 3-SO-Stage | Takeo | - | - | - | - | 1 | 2025-07-05 | 2025-07-08 | WK28(07-Jul - 13-Jul) | July
91 | Angkor Borei_CamGSM_01 | Takeo | Nokia re-deployment | TK0199 |  |  |  |  | 11.0791 | 104.9158 | Dismantled Nokia BTS | 3-SO-Stage | Takeo | - | - | - | - | 1 | 2025-07-09 | 2025-07-12 | WK28(07-Jul - 13-Jul) | July
92 | KhsachKandal_CC_11 | Kandal | Nokia re-deployment | TCE_KD016 |  |  |  |  | 11.6606 | 105.1093 | Dismantled Nokia BTS | 3-SO-Stage | Kandal | - | - | - | - | 0 | 2025-07-09 | 2025-07-12 | WK28(07-Jul - 13-Jul) | July
93 | Mukh Kampul_CC_08 | Kandal | Nokia re-deployment | TCE_KD001 |  |  |  |  | 11.7919 | 104.9822 | Dismantled Nokia BTS | 3-SO-Stage | Kandal | - | - | - | - | 0 | 2025-07-09 | 2025-07-12 | WK28(07-Jul - 13-Jul) | July
94 | Tramkak_CamGSM_15 | Takeo | Nokia re-deployment | TCE_TK033 |  |  |  |  | 11.0998 | 104.5392 | Dismantled Nokia BTS | 3-SO-Stage | Takeo | - | - | - | - | 1 | 2025-07-09 | 2025-07-12 | WK28(07-Jul - 13-Jul) | July
95 | Trang_CamGSM_11 | Takeo | Nokia re-deployment | GTK17 |  |  |  |  | 10.9147 | 104.8208 | Dismantled Nokia BTS | 3-SO-Stage | Takeo | - | - | - | - | 1 | 2025-07-09 | 2025-07-12 | WK28(07-Jul - 13-Jul) | July
96 | Mukh Kampul_CC_02 | Kandal | Nokia re-deployment | KD206 |  |  |  |  | 11.795 | 104.937 | Dismantled Nokia BTS | 3-SO-Stage | Kandal | - | - | - | - | 0 | 2025-07-13 | 2025-07-16 | WK29(14-Jul - 20-Jul) | July
97 | PonheaLeu_CC_15 | Kandal | Nokia re-deployment | TKD058 |  |  |  |  | 11.7696 | 104.8332 | Dismantled Nokia BTS | 3-SO-Stage | Kandal | - | - | - | - | 4 | 2025-07-13 | 2025-07-16 | WK29(14-Jul - 20-Jul) | July
98 | TKD050 | Kandal | Nokia re-deployment | TKD050 |  |  |  |  | 11.7253 | 104.8433 | Dismantled Nokia BTS | 4-CME-Stage | Kandal | - | - | - | - | 4 | 2025-07-13 | 2025-07-16 | WK29(14-Jul - 20-Jul) | July
99 | TKD051 | Kandal | Nokia re-deployment | TKD051 |  |  |  |  | 11.7284 | 104.7476 | Dismantled Nokia BTS | 5-RFI-Stage | Kandal | - | - | - | - | 4 | 2025-07-13 | 2025-07-16 | WK29(14-Jul - 20-Jul) | July
100 | Tramkak_CamGSM_26 | Takeo | Nokia re-deployment | TKT091 |  |  |  |  | 10.9496 | 104.6108 | Dismantled Nokia BTS | 3-SO-Stage | Takeo | - | - | - | - | 1 | 2025-07-13 | 2025-07-16 | WK29(14-Jul - 20-Jul) | July
101 | Saáng_CC_11 | Kandal | Nokia re-deployment | TKD059 |  |  |  |  | 11.2744 | 105.0772 | Dismantled Nokia BTS | 4-CME-Stage | Kandal | - | - | - | - | 0 | 2025-07-17 | 2025-07-20 | WK29(14-Jul - 20-Jul) | July
102 | TKD044 | Kandal | Nokia re-deployment | TKD044 |  |  |  |  | 11.7039 | 104.781 | Dismantled Nokia BTS | 4-CME-Stage | Kandal | - | - | - | - | 4 | 2025-07-17 | 2025-07-20 | WK29(14-Jul - 20-Jul) | July
103 | TTA023 | Takeo | Nokia re-deployment | TTA023 |  |  |  |  | 11.1189 | 104.7967 | Dismantled Nokia BTS | 5-RFI-Stage | Takeo | - | - | - | - | 1 | 2025-07-17 | 2025-07-20 | WK29(14-Jul - 20-Jul) | July
104 | TTK001 | Tboung khmum | Nokia re-deployment | TTK001 |  |  |  |  | 11.9119 | 105.6677 | Dismantled Nokia BTS | 4-CME-Stage | Tboung khmum | - | - | - | - | 3 | 2025-07-17 | 2025-07-20 | WK29(14-Jul - 20-Jul) | July
105 | TTK005 | Tboung khmum | Nokia re-deployment | TTK005 |  |  |  |  | 11.8904 | 105.6386 | Dismantled Nokia BTS | 4-CME-Stage | Tboung khmum | - | - | - | - | 3 | 2025-07-17 | 2025-07-20 | WK29(14-Jul - 20-Jul) | July
106 | TKD043 | Kandal | Nokia re-deployment | TKD043 |  |  |  |  | 11.748 | 104.7614 | Dismantled Nokia BTS | 5-RFI-Stage | Kandal | - | - | - | - | 4 | 2025-07-21 | 2025-07-24 | WK30(21-Jul - 27-Jul) | July
107 | TTA018 | Takeo | Nokia re-deployment | TTA018 |  |  |  |  | 11.1524 | 104.7596 | Dismantled Nokia BTS | 5-RFI-Stage | Takeo | - | - | - | - | 1 | 2025-07-21 | 2025-07-24 | WK30(21-Jul - 27-Jul) | July
108 | TTA020 | Takeo | Nokia re-deployment | TTA020 |  |  |  |  | 11.1441 | 104.8289 | Dismantled Nokia BTS | 5-RFI-Stage | Takeo | - | - | - | - | 1 | 2025-07-21 | 2025-07-24 | WK30(21-Jul - 27-Jul) | July
109 | TTA021 | Takeo | Nokia re-deployment | TTA021 |  |  |  |  | 11.0953 | 104.7676 | Dismantled Nokia BTS | 5-RFI-Stage | Takeo | - | - | - | - | 1 | 2025-07-21 | 2025-07-24 | WK30(21-Jul - 27-Jul) | July
110 | TTA026 | Takeo | Nokia re-deployment | TTA026 |  |  |  |  | 11.1862 | 104.7546 | Dismantled Nokia BTS | 5-RFI-Stage | Takeo | - | - | - | - | 1 | 2025-07-21 | 2025-07-24 | WK30(21-Jul - 27-Jul) | July
111 | PP797 | Phnom Penh | Nokia re-deployment | PP797 |  |  |  |  | 11.5808 | 104.7889 | Dismantled Nokia BTS | 6-WP-Stage | 14-Khan | - | - | - | - | 4 | 2025-07-25 | 2025-07-28 | WK31(28-Jul - 03-Aug) | July
112 | TKD042 | Kandal | Nokia re-deployment | TKD042 |  |  |  |  | 11.6837 | 104.7818 | Dismantled Nokia BTS | 5-RFI-Stage | Kandal | - | - | - | - | 4 | 2025-07-25 | 2025-07-28 | WK31(28-Jul - 03-Aug) | July
113 | TKD046 | Kandal | Nokia re-deployment | TKD046 |  |  |  |  | 11.8476 | 104.798 | Dismantled Nokia BTS | 5-RFI-Stage | Kandal | - | - | - | - | 4 | 2025-07-25 | 2025-07-28 | WK31(28-Jul - 03-Aug) | July
114 | TTK007 | Tboung khmum | Nokia re-deployment | TTK007 |  |  |  |  | 11.8742 | 105.7636 | Dismantled Nokia BTS | 5-RFI-Stage | Tboung khmum | - | - | - | - | 3 | 2025-07-25 | 2025-07-28 | WK31(28-Jul - 03-Aug) | July
115 | TTK009 | Tboung khmum | Nokia re-deployment | TTK009 |  |  |  |  | 11.934 | 105.5553 | Dismantled Nokia BTS | 5-RFI-Stage | Tboung khmum | - | - | - | - | 3 | 2025-07-25 | 2025-07-28 | WK31(28-Jul - 03-Aug) | July
116 | KC098 | Kampong Cham | Nokia re-deployment | KC098 |  |  |  |  | 11.9843 | 105.459 | Dismantled Nokia BTS | 7-TE Stage | Kompong Cham | - | - | - | - | 3 | 2025-07-29 | 2025-08-01 | WK31(28-Jul - 03-Aug) | August
117 | KDT006 | Kandal | Nokia re-deployment | KDT006 |  |  |  |  | 11.5011 | 104.7046 | Dismantled Nokia BTS | 7-TE Stage | Kandal | - | - | - | - | 4 | 2025-07-29 | 2025-08-01 | WK31(28-Jul - 03-Aug) | August
118 | TCE_PP119 | Phnom Penh | Nokia re-deployment | TCE_PP119 |  |  |  |  | 11.6565 | 104.759 | Dismantled Nokia BTS | 7-TE Stage | 14-Khan | - | - | - | - | 4 | 2025-07-29 | 2025-08-01 | WK31(28-Jul - 03-Aug) | August
119 | TCE_PP134 | Phnom Penh | Nokia re-deployment | TCE_PP134 |  |  |  |  | 11.5489 | 104.7527 | Dismantled Nokia BTS | 6-WP-Stage | 14-Khan | - | - | - | - | 4 | 2025-07-29 | 2025-08-01 | WK31(28-Jul - 03-Aug) | August
120 | TKS009 | Kandal | Nokia re-deployment | TKS009 |  |  |  |  | 11.8069 | 104.7512 | Dismantled Nokia BTS | 7-TE Stage | Kandal | - | - | - | - | 4 | 2025-07-29 | 2025-08-01 | WK31(28-Jul - 03-Aug) | August
121 | KS085 | Kampong Speu | Nokia re-deployment | KS085 |  |  |  |  | 11.3936 | 104.6962 | Dismantled Nokia BTS | 8-On Air | Kandal | - | - | - | - | 4 | 2025-08-02 | 2025-08-05 | WK32(04-Aug - 10-Aug) | August
122 | TCE_PP075 | Phnom Penh | Nokia re-deployment | TCE_PP075 |  |  |  |  | 11.6573 | 104.9421 | Dismantled Nokia BTS | 8-On Air | 14-Khan | - | - | - | - | 0 | 2025-08-02 | 2025-08-05 | WK32(04-Aug - 10-Aug) | August
123 | TCE_TK001 | Takeo | Nokia re-deployment | TCE_TK001 |  |  |  |  | 11.2244 | 104.7755 | Dismantled Nokia BTS | 8-On Air | Takeo | - | - | - | - | 1 | 2025-08-02 | 2025-08-05 | WK32(04-Aug - 10-Aug) | August
124 | TCE_TK005 | Takeo | Nokia re-deployment | TCE_TK005 |  |  |  |  | 11.2149 | 104.874 | Dismantled Nokia BTS | 8-On Air | Takeo | - | - | - | - | 1 | 2025-08-02 | 2025-08-05 | WK32(04-Aug - 10-Aug) | August
125 | TCE_TK009 | Takeo | Nokia re-deployment | TCE_TK009 |  |  |  |  | 11.2189 | 104.9037 | Dismantled Nokia BTS | 8-On Air | Takeo | - | - | - | - | 1 | 2025-08-02 | 2025-08-05 | WK32(04-Aug - 10-Aug) | August
126 | KC005SE | Kampong Cham | Nokia re-deployment | KC005SE |  |  |  |  | 11.9917 | 105.4647 | Dismantled Nokia BTS | 9-Blockage | Kompong Cham | - | - | - | - | 3 | 2025-08-06 | 2025-08-09 | WK32(04-Aug - 10-Aug) | August
127 | KDT001 | Kandal | Nokia re-deployment | KDT001 |  |  |  |  | 11.4788 | 104.6823 | Dismantled Nokia BTS | 9-Blockage | Kandal | - | - | - | - | 4 | 2025-08-06 | 2025-08-09 | WK32(04-Aug - 10-Aug) | August
128 | KDT022 | Kandal | Nokia re-deployment | KDT022 |  |  |  |  | 11.3589 | 104.8435 | Dismantled Nokia BTS | 9-Blockage | Kandal | - | - | - | - | 0 | 2025-08-06 | 2025-08-09 | WK32(04-Aug - 10-Aug) | August
129 | PP808 | Phnom Penh | Nokia re-deployment | PP808 |  |  |  |  | 11.4782 | 104.8708 | Dismantled Nokia BTS | 8-On Air | 14-Khan | - | - | - | - | 0 | 2025-08-06 | 2025-08-09 | WK32(04-Aug - 10-Aug) | August
130 | TCE_PP115 | Phnom Penh | Nokia re-deployment | TCE_PP115 |  |  |  |  | 11.6668 | 104.8597 | Dismantled Nokia BTS | 9-Blockage | 14-Khan | - | - | - | - | 4 | 2025-08-06 | 2025-08-09 | WK32(04-Aug - 10-Aug) | August

## Sitelogs
No. | Old SBTS Site Name | Old Site Name Name | Project SoW | New Site Name | New SBTS Site Name | Province | Latitude | Longitude | Reason | Date Replacement | Cellcard PIC
1 | PNH01777MR | CANADIA_BANK | Upgrade | PHNUM_LIEB_KEUT | BMC1092PNP | Banteay Meanchey | 13.5954 | 103.3565 | Metfone site sharing | 2025-03-24 | Kao Hual
2 | SRP3156SRP | SIE106 | Upgrade | THNAL_DACH | BMC1094TPK | Banteay Meanchey | 14.0094 | 103.0998 | Metfone site sharing | 2025-03-24 | Kao Hual
3 | SRP5539SRP | SIE379 | Upgrade | SAMBO_PREYKUK | KGT0339PSB | Kampong Thom | 12.8829 | 105.0661 | Metfone site sharing | 2025-03-24 | Kao Hual
4 | KGT6164SSN | THO184 | Upgrade | SANKOR | KGT0134KPS | Kampong Thom | 12.8057 | 104.7524 | Metfone site sharing | 2025-03-24 | Kao Hual
5 | COW6 | COW6 | Upgrade | OU_POUR | PVH2247RVG | Preah Vihear | 13.1928 | 105.0401 | Metfone site sharing | 2025-03-24 | Kao Hual
6 | KGT0339PSB | SAMBO_PREYKUK | Upgrade | SRE_NOY | SRP0264VRI | Siem Reap | 13.8064 | 104.0357 | Already Upgrade with 78 MM upgrade project | 2025-04-08 | Kao Hual
7 | KGT0134KPS | SANKOR | Upgrade | SANTEY | SRP2156SNK | Siem Reap | 13.2396 | 104.091 | Already Upgrade with 78 MM upgrade project | 2025-04-08 | Kao Hual
8 | SRP5630BSR | CTL8 | Upgrade | BOSS | SRP1425SNK | Siem Reap | 13.2391 | 104.1368 | Already Upgrade with 78 MM upgrade project | 2025-04-08 | Kao Hual
9 | SRP3319SRP | CTL07_SRAH_SRANG | Upgrade | TBC by Cellcard |  |  |  |  | Already Upgrade with 78 MM upgrade project | 2025-04-08 | Kao Hual
10 | KRT0947CLG | CHHLONG_MARKET | ALU Swap (Under 185 Sites) | GPP43 | PNH6358SSK | Phnom Penh | 11.5915 | 104.8608 | Relocated | 2025-03-19 | Kao Hual
11 | SVR0143RMH | ROMEAS_HEK | ALU Swap (Under 185 Sites) | TBC by Cellcard |  |  |  |  | Relocated | 2025-03-19 | Kao Hual
12 | KRT0715KRC | KRATIE3 | HW Swap (Under 185 Sites) | TKR001 | KRT6461KRC | Kratie | 12.4917 | 106.0177 | Relocated | 2025-03-19 | Kao Hual
13 | RTK1493BNL | PHUM_BEI | ALU Swap (Under 185 Sites) | TRR001 | RTK6468BNL | Kratie | 13.7345 | 106.9805 | Relocated | 2025-03-19 | Kao Hual